## NAMED RANGES (hidden)
Economic Affairs | Office of Infrastructure | Traffic Management and Transportation | Economic Affairs
General Public Services | Lagos Metropolitan Area Transport Authority | Traffic Management and Transportation | Economic Affairs
Public Order and Safety | Ministry of Transportation | Traffic Management and Transportation | Economic Affairs
Environmental Protection | Office of Sustainable Development Goals | Making Lagos a 21st Century Economy | Economic Affairs
Social Protection | Ministry of Waterfront Infrastructure Development | Traffic Management and Transportation | Economic Affairs
Housing and Community Amenities | Office of Works | Traffic Management and Transportation | Economic Affairs
Health Sector | Public Works Corporation | Traffic Management and Transportation | Economic Affairs
Education Sector | Ministry of Agriculture | Making Lagos a 21st Century Economy | Economic Affairs
Recreation Culture and Religion | Ministry of Wealth Creation and Employment | Education and Technology | Economic Affairs
| Ministry of Energy and Mineral Resources | Making Lagos a 21st Century Economy | Economic Affairs
| Ministry of Commerce, Industry and Cooperatives | Making Lagos a 21st Century Economy | Economic Affairs
| Lagos State Infrastructure Asset Management Agency | Making Lagos a 21st Century Economy | Economic Affairs
| Ministry of Finance | Security and Governance | General Public Services
| Office of Chief of Staff | Security and Governance | General Public Services
| Ministry of Economic Planning and Budget | Security and Governance | General Public Services
| Public Procurement Agency | Security and Governance | General Public Services
| Office of the Deputy Governor | Security and Governance | General Public Services
| Ministry of Local Government and Community Affairs | Security and Governance | General Public Services
| Civil Service Commission | Security and Governance | General Public Services
| Ministry of Information and Strategy | Entertainment and Tourism | General Public Services
| Ministry of Science and Technology | Education and Technology | General Public Services
| Public Service Office | Security and Governance | General Public Services
| Office of Civic Engagement | Security and Governance | General Public Services
| Ministry of Establishments and Training | Security and Governance | General Public Services
| Ministry of Special Duties and Intergovernmental Relations | Security and Governance | Public Order and Safety
| Lagos State Judiciary | Security and Governance | Public Order and Safety
| Ministry of Justice | Security and Governance | Public Order and Safety
| Lagos State Parks and Garden Agency | Health and Environment | Environmental Protection
| Office of Environmental Services | Health and Environment | Environmental Protection
| Office of Drainage Services | Health and Environment | Environmental Protection
| Lagos State Waste Management Authority | Health and Environment | Environmental Protection
| Ministry of Youth and Social Development | Entertainment and Tourism | Social Protection
| Ministry of Women Affairs and Poverty Alleviation | Education and Technology | Social Protection
| New Town Development Authority | Making Lagos a 21st Century Economy | Housing and Community Amenities
| Lands Bureau | Making Lagos a 21st Century Economy | Housing and Community Amenities
| Ministry of Physical Planning and Urban Development | Making Lagos a 21st Century Economy | Housing and Community Amenities
| Ministry of Housing | Making Lagos a 21st Century Economy | Housing and Community Amenities
| Office of the State Surveyor General | Making Lagos a 21st Century Economy | Housing and Community Amenities
| Ministry of Health | Health and Environment | Health Sector
| Ministry of Health (DPS) | Health and Environment | Health Sector
| Ministry of Health (EPID, BIOSAFETY & GLOBAL HEALTH) | Health and Environment | Health Sector
| Ministry of Health (DMAT) | Health and Environment | Health Sector
| Ministry of Health (DDC) | Health and Environment | Health Sector
| Ministry of Health (DFH&N) | Health and Environment | Health Sector
| Ministry of Health (O & E HS) | Health and Environment | Health Sector
| Ministry of Health (SHS) | Health and Environment | Health Sector
| Ministry of Health (LASAMBUS) | Health and Environment | Health Sector
| Ministry of Health (DHCPRS) | Health and Environment | Health Sector
| Ministry of Health (PIU) | Health and Environment | Health Sector
| Ministry of Health (DNS) | Health and Environment | Health Sector
| Ministry of Health (LSACA PREVENTIVE SERVICES) | Health and Environment | Health Sector
| Ministry of Health (HEFAMAA QUALITY ASSURANCE) | Health and Environment | Health Sector
| Ministry of Health (LASHMA HEALTH FINANCING) | Health and Environment | Health Sector
| Ministry of Health (LSBTS CURATIVE SERVICES) | Health and Environment | Health Sector
| Ministry of Health (LSBTS PREVENTIVE SERVICES) | Health and Environment | Health Sector
| Ministry of Health (LSBTS HEALTH QUALITY SERVICES) | Health and Environment | Health Sector
| Ministry of Health (LSBTS EMERGENCY SERVICES) | Health and Environment | Health Sector
| Ministry of Health (LSBTS HEALTHCARE PLANNING, RESEARCH AND STATISTICS) | Health and Environment | Health Sector
| Ministry of Health (LASUTH - Medical Gas (CURATIVE)) | Health and Environment | Health Sector
| Ministry of Health (LASUTH (EMERGENCY SERVICES)) | Health and Environment | Health Sector
| Ministry of Health (LASUTH (QUALITY ASSURANCE)) | Health and Environment | Health Sector
| Ministry of Health (LASUCOM (QUALITY ASSURANCE)) | Health and Environment | Health Sector
| Ministry of Health (PHCB) | Health and Environment | Health Sector
| Ministry of Health (HSC (HEALTHCARE PLANNING, RESEARCH and STATISTICS)) | Health and Environment | Health Sector
| Ministry of Health (LASAEC (EMERGENCY SERVICES)) | Health and Environment | Health Sector
| Ministry of Education | Education and Technology | Education Sector
| Ministry of Tertiary Education | Education and Technology | Education Sector
| Special Committee on Rehabilitation of Public Schools (SCRPS) | Education and Technology | Education Sector
| Ministry of Home Affairs | Entertainment and Tourism | Recreation Culture and Religion
| Lagos State Sports Commission | Entertainment and Tourism | Recreation Culture and Religion
| Ministry of Tourism, Arts and Culture | Entertainment and Tourism | Recreation Culture and Religion

## THEMES PILLAR (hidden)
LAGOS STATE PERFORMANCE MANAGEMENT REPORT |  | Y2023
Q1 Budget Performance | TOTAL NUMBER OF MDAs | TOTAL NUMBER OF KPIs | AVERAGE OUTPUT PERFORMANCE | SUM of OUTPUT TARGET2 | SUM of ACTUAL OUTPUT3 | AVERAGE BUDGET PERFORMANCE
Grand Total | [5 empty] | #DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!

## PMR
LAGOS STATE PERFORMANCE MANAGEMENT REPORT |  |  | Y2024
Sector | MDA | State Level Goal | Outcome | Programme / Project | Full Year Output Targets for Programme / Project Activities | Q1 Output Target (in numbers) | Q1 Actual Output | OUTPUT TARGET2 | ACTUAL OUTPUT3 | Y2024 Approved Budget | Cummulative Budget Released as at Q1 | Q1 Output Performance | Q1 Budget Performance | Remarks | Planned Q1 Perf | Cummulative TPR Score | COFOG | MDA REVISED
General Public Services | Ministry of Finance | Thriving Economy | Enhanced creditworthiness | Bond Administration | 7 billion Bond capital repayment | 1.75 | 0.8 billion Bond capital repayment | 7 | 0.8 | 7000000000 | 80981100 | 11.43% | 1.157% |  | 25% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Fiscal deficit mitigation | Debt charges (internal) | 72 billion interest to be paid on domestic loans | 18.06 | 10.8 billion interest paid | 72 | 10.8 | 72246757140.22 | 10807984706.68 | 15% | 14.96% |  | 25.08% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Fiscal deficit mitigation | Debt charges (External) | 11 billion interest to be paid on external loans | 2.95 | 7.4 billion interest paid | 11 | 7.4 | 11826638433.28 | 7434680408.81 | 67.27% | 62.86% |  | 26.82% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Fiscal deficit mitigation | Principal Repayment (Internal) | 182 billion to be paid on domestic loans principal repayments | 45.6 | 8.5 billion paid | 182 | 8.5 | 182421067698.04 | 8501135372.61 | 4.67% | 4.66% |  | 25.05% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Fiscal deficit mitigation | Principal Repayment (external) | 43 billion to be paid on external loans principal repayments | 10.95 | 16.2 billion paid | 43 | 16.2 | 43825920602.55 | 16232843450.48 | 37.67% | 37.04% |  | 25.47% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Streamlined debt servicing | Consolidated Debt Service Account | 114 billion to be used to service Bonds- Consolidated Debt Service Account | 28.56 | 8.1 billion used | 114 | 8.1 | 114257689858.3 | 8100000000 | 7.105% | 7.089% |  | 25.05% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Enhanced fiscal stability | Bond Issuance (Repayment) | 27 Billion Bond capital to be repaid | 6.85 | 0 Billion Bond capital repaid | 27 | 0 | 27388246412 | 0 | 0% | 0% |  | 25.37% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Increased revenue streams | Revenue Generation | 900 million properties to be enumerated | 247 | 340 million properties enumerated | 900 | 340 | 989533991 | 340381949.69 | 37.78% | 34.4% |  | 27.44% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Increased revenue streams | Revenue Generation | 50 billion to be generated through land use charge | 12.5 | 4.5 billion generated | 50 | 4.5 | 50000000000 | 4538425996 | 9% | 9.077% |  | 25% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Optimized investment returns | Investing and Revenue Monitoring | 7 billion Returns on Investment Income Target | 1.7 | 0 billion Returns | 7 | 0 | 7045350000 | 0 | 0% | 0% |  | 24.29% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Comprehensive risk management | Insurance | 3 months period for Settlement of claims | 3 | 3 months period | 3 | 3 | 3642455835 | 3113719335 | 100% | 85.48% |  | 100% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Financial support for international engagements | International Travels | 100% Financial Backing for State Approved International Travels | 0.25 | 25% Financial Backing | 100% | 25% | 600000000 | 587687788 | 25% | 97.95% |  | 25% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Accelerated payment processing | Accounting Management | 5 working days disbursement of payment (cheque/ bank transfer) to MDAs, contractors/suppliers | 5 | 5 working days disbursement of payment | 5 | 5 | 350000000 | 106250000 | 100% | 30.36% |  | 100% |  | General Public Services | Ministry of Finance
General Public Services | Ministry of Finance | Thriving Economy | Improved financial reporting | Resource Management | 25 days after the end of quarter or at the end of the quarter, prepare and submit quarterly Management Financial Statement | 25 | 25 days after the end of quarter or at the end of the quarter | 25 | 25 | 65000000 | 5423300 | 100% | 8.344% |  | 100% |  | General Public Services | Ministry of Finance
General Public Services | Civil Service Commission | Human-Centric City | Enhanced Career Progression for GL 07+ Officers | Career Management (CMD) | 4,301 Eligible Officers to be trained & interviewed for Promotion |  | 2,064 Eligible Officers promoted (1st January, 2024 notional date) but yet to collect promotion letter | 4,301 | 2,064 | 135000000 | 0 | 47.99% | 0% | Awaiting Processing of funds from STO | 0% |  | General Public Services | Civil Service Commission
General Public Services | Civil Service Commission | Human-Centric City | Streamlined Policy Decision Making | Documentation (Secretariat) | 24 Directives to be taken |  | 3 Directives to be taken | 24 | 3 | 9000000 | 0 | 12.5% | 0% |  | 0% |  | General Public Services | Civil Service Commission
General Public Services | Civil Service Commission | Human-Centric City | Streamlined Policy Decision Making | Documentation (Secretariat) | 19,485 Decisions to be arrived at |  | 2,336 Decisions to be arrived at | 19,485 | 2,336 |  |  | 11.99% |  | Awaiting Processing of funds from STO | 0% |  | General Public Services | Civil Service Commission
General Public Services | Civil Service Commission | Human-Centric City | Efficient File Management via Digitization | Digitization | 3,187 Files to be digitized |  | Nil Files to be digitized | 3,187 | Nil | 80000000 | 0 |  | 0% | Work in Progress. Awaiting Processing of funds from STO | 0% |  | General Public Services | Civil Service Commission
General Public Services | Civil Service Commission | Human-Centric City | Enhanced Workforce Quality | Recruitment & Appeal | 1,500 Officers to be recruited (subject to requirement from MDAs) |  | Nil Officers to be recruited | 1,500 | Nil | 33500000 | 0 |  | 0% | Work in Awaiting Processing of funds from STO | 0% |  | General Public Services | Civil Service Commission
General Public Services | Civil Service Commission | Human-Centric City | Enhanced Workforce Quality | Recruitment & Appeal | 488 Officers scheduled to be confirmed |  | 260 Officers to be confirmed | 488 | 260 | 2000000 | 0 | 53.28% | 0% | Awaiting Processing of funds from STO | 0% |  | General Public Services | Civil Service Commission
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Planning & Policy Management | 201 planners, Statisticians & Statistical Officers to be trained on planning Reform & Budgeting process |  | Nil planners, Statisticians & Statistical Officers trained | 201 | Nil | 4051500 | 0 |  | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Planning & Policy Management | 4 planning officers meetings to be held |  | 1 planning officers meetings held | 4 | 1 | 2560000 | 0 | 25% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Planning & Policy Management | 6 Heads of planning units meetings to be held |  | 1 Heads of planning units meetings held | 6 | 1 | 4389200 | 0 | 16.67% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Planning & Policy Management | 187 Heads of planning units to be trained on managerial units |  | 0 Heads of planning units trained on managerial units | 187 | 0 | 8758000 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Planning & Policy Management | 4 meetings to be held to track LSDP 2052 initiatives |  | 1 meetings held to track LSDP 2052 initiatives | 4 | 1 | 8752000 | 3899500 | 25% | 44.56% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Planning & Policy Management | 1 parley with stakeholders on the implementation of LSDP 2052 initiatives to be held in Y2024 |  | 0 parley with stakeholders | 1 | 0 | 3812375 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Planning & Policy Management | 30 officers to be trained on the usage of the MTSS milestone tracking template |  | 30 officers trained | 30 | 30 | 3000000 | 3000000 | 100% | 100% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Planning & Policy Management | 31 Core-Team members to be trained |  | 0 Core-Team members trained | 31 | 0 | 4014375 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Planning & Policy Management | 44 MDAs MTSS Rollover documents to be submitted |  | 0 MDAs MTSS Rollover documents submitted | 44 | 0 | 13057575 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Planning & Policy Management | 1 Collaboration with Regional & National bodies to be initiated |  | 0 Collaborations with Regional & National bodies initiated | 1 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Economic Intelligence Programme | 1 MTEF document to be produced |  | 0 MTEF documents produced | 1 | 0 | 11500000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Economic Intelligence Programme | 1 LEDU report to be produced/published |  | 0 LEDU reports produced/published | 1 | 0 | 5000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Economic Intelligence Programme | 1 Report on State policy to be reviewed |  | 0 Reports on State policy reviewed | 1 | 0 | 4000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Economic Intelligence Programme | 1 Report on policy impact assessment to be produced |  | 0 Reports on policy impact assessment produced | 1 | 0 | 2500000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Economic Intelligence Programme | 1 Report on empirical research to be produced |  | 0 Reports on empirical research produced | 1 | 0 | 1726540 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Economic Intelligence Programme | 1 Economic Discuss to be conducted |  | 0 Economic Discuss conducted | 1 | 0 | 4000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Economic Intelligence Programme | 4 Macroeconomic indicators reports to be tracked and produced |  | 1 reports on Macroeconomic indicators tracked and produced | 4 | 1 | 1200000 | 0 | 25% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Economic Intelligence Programme | 1 Macroeconomic indicators report flier to be published |  | 1 fliers of Macroeconomic indicators report published | 1 | 1 | 3100000 | 0 | 100% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Economic Intelligence Programme | 6 Collaborations with research institutes and institutions to be conducted |  | 0 Collaborations with research institutes and institutions conducted | 6 | 0 | 1500000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Economic Intelligence Programme | 2 Study tours to other states to be attended |  | 0 Study tours to other states attended | 2 | 0 | 1500000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Economic Intelligence Programme | 8 officers' capacity to be enhanced |  | 0 officers' capacity enhanced | 8 | 0 | 2678017 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Resource & Management Control | 5 Consultative Forums on Budget to be organized in 5 divisions of Lagos State |  | 0 Consultative Forums organized | 5 | 0 | 31647220 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Resource & Management Control | 184 MDAs Annual Budget to be uploaded into Oracle PSB Modules |  | 184 MDAs Annual Budget uploaded | 184 | 184 | 0 | 0 | 100% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Resource & Management Control | 1 Annual Budget Estimate (Document) to be prepared |  | 0 Annual Budget Estimates (Documents) prepared | 1 | 0 | 19001874 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Resource & Management Control | 1 Annual Budget Estimate (Document) to be produced |  | 0 Annual Budget Estimates (Documents) produced | 1 | 0 | 0 | 0 | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Resource & Management Control | 3000 Annual Budget estimates documents to be published |  | 1600 Annual Budget estimates documents published | 3000 | 1600 | 3701888.5 | 3300000 | 53.33% | 89.14% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Resource & Management Control | 1 Pre-Budget workshop to be organized for Officers in the Planning Unit Service-wide |  | 0 Pre-Budget workshop organized | 1 | 0 | 10257000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Resource & Management Control | 5,831 Expenditure Requests to be received |  | 1905 Expenditure Requests received | 5,831 | 1905 |  | 0 | 32.67% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Resource & Management Control | 4,650 Expenditure Requests to be approved |  | 916 Expenditure Requests approved | 4,650 | 916 |  | 0 | 19.7% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Resource & Management Control | 234 Expenditure Requests to be declined |  | 187 Expenditure Requests declined | 234 | 187 |  | 0 | 79.91% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | Resource & Management Control | 4 quarterly Appraisals of Budget to be prepared |  | 1 quarterly Appraisals of Budget prepared | 4 | 1 |  | 0 | 25% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 43 MDAs PMR to be submitted |  | 46 MDAs PMR submitted | 43 | 46 | 119861339.7 | 11531000 | 100% | 9.62% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 43 MDAs PMR to be reviewed |  | 46 MDAs PMR reviewed | 43 | 46 |  |  | 100% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 4 MDAs PMR Reports to be produced (1 quarterly) |  | 0 MDAs PMR Reports produced (1 quarterly) | 4 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 4 Evaluation Studies/Impact assessments to be conducted |  | 0 Evaluation Studies/Impact assessments conducted | 4 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 4 Evaluation Studies/Impact assessment reports to be produced |  | 0 Evaluation Studies/Impact assessment reports produced | 33 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 33 MDAs TPR Self-Assessments on programmes & projects to be submitted |  | 32 MDAs TPR Self-Assessments on programmes & projects submitted |  | 32 | [7 empty] | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 33 MDAs TPR Self-Assessments on programmes & projects to be reviewed |  | 0 MDAs TPR Self-Assessments on programmes & projects reviewed | 33 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 4 MDAs TPR Reports to be produced (1 quarterly) |  | 0 MDAs TPR Reports produced (1 quarterly) | 4 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 21 MDAs TPR Revenue Major Initiatives to be submitted |  | 21 MDAs TPR Revenue Major Initiatives submitted | 21 | 21 |  |  | 100% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 21 MDAs TPR Revenue Major Initiatives to be reviewed |  | 21 MDAs TPR Revenue Major Initiatives reviewed | 21 | 21 |  |  | 100% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 12 MDAs TPR Revenue Major Initiatives reports to be produced (monthly) |  | 12 MDAs TPR Revenue Major Initiatives produced | 12 | 12 |  |  | 100% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 5 Advance Payment inspections to be conducted |  | 0 Advance Payment inspections conducted | 5 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 1 Stakeholders meeting to be organized |  | 1 Stakeholders meetings organized | 1 | 1 |  |  | 100% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 750 Projects to be inspected |  | 114 Projects inspected | 750 | 114 |  |  | 15.2% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 750 Projects to be certified |  | 114 Projects certified | 750 | 114 |  |  | 15.2% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust policies implemented, resources managed efficiently, value for money ensured, and MDAs' reporting improved. | State Performance Management inclusive of (TPR) The peer Review | 4 Trainings/Workshops on Monitoring and Evaluation to be attended |  | 1 Trainings/Workshops on Monitoring and Evaluation attended | 4 | 1 |  |  | 25% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 250 Copies of Consumer Price Index and Inflation fliers to be produced and made available on the State’s website |  | 0 Copies of Consumer Price Index and Inflation fliers produced and made available on the State’s website | 250 | 0 | 8000000 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 250 Macro-Economic flyers to be produced and made available on the State’s website |  | 0 Macro-Economic flyers produced and made available on the State’s website | 250 | 0 | 1000000 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 1 Lagos State welfare & service Delivery (Household/poverty) survey to be conducted |  | 0 Lagos State welfare & service Delivery (Household/poverty) surveys conducted | 1 | 0 | 64760752 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 200 Lagos State welfare & service delivery (Household/poverty) survey reports to be produced and made available on the State’s website |  | 0 Lagos State welfare & service delivery (Household/poverty) survey reports produced and made available on the State’s website | 200 | 0 | 6150000 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 200 welfare & service delivery (Household/poverty) survey Compact Disks (CDs) to be produced |  | 0 welfare & service delivery (Household/poverty) survey Compact Disks (CDs) produced | 200 | 0 |  |  | 0% |  | Outdated | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 1 Demographic & Health survey to be conducted |  | 0 Demographic & Health surveys conducted | 1 | 0 | 46254356 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 200 Demographic & Health survey reports to be produced and made available on the State’s website |  | 0 Demographic & Health survey reports to be produced and made available on the State’s websiteconducted | 200 | 0 | 14600000 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 1 Consumption Expenditure survey to be conducted |  | 0 Consumption Expenditure surveys conducted | 1 | 0 | 52490000 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 1 Consumption Expenditure survey reports to be produced and made available on the State’s website |  | 0 Consumption Expenditure survey reports to be produced and made available on the State’s website | 1 | 0 | 6950000 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 50 monthly price statistics bulletins to be produced and made available on the State’s website |  | 0 monthly price statistics bulletins produced and made available on the State’s website | 50 | 0 | 8000000 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 1 Annual Gross Domestic Product (GDP) (Data gathering Process) to be conducted |  | 0 Annual Gross Domestic Product (GDP) (Data gathering Processes) conducted | 1 | 0 | 3000000 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 125 copies of Quarterly Gross Domestic Product (GDP) (Data gathering process) reports to be produced and made available on the State’s website |  | 0 copies of Quarterly Gross Domestic Product (GDP) (Data gathering process) reports produced and made available on the State’s website | 125 | 0 | 40000000 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 100 copies of Digest of Statistics Publication to be produced, with a soft copy to be made available on the State’s website |  | 0 copies of Digest of Statistics Publications produced, with a soft copy made available on the State’s website | 100 | 0 |  |  | 0% |  | Not Budgeted for | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 100 copies of Transport Statistics publication to be produced, with a soft copy to be made available on the State’s website |  | 0 copies of Transport Statistics publications produced, with a soft copy made available on the State’s website | 100 | 0 | 0 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 100 copies of Local Government Abstract Statistics Publication to be produced, with a soft copy to be made available on the State’s website |  | 0 copies of Local Government Abstract Statistics Publications produced, with a soft copy made available on the State’s website | 100 | 0 | 0 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 100 copies of the Spotlight of Lagos Statistics to be produced, with a soft copy to be made available on the State’s website |  | 0 copies of the Spotlight of Lagos Statistics produced, with a soft copy made available on the State’s website | 100 | 0 | 0 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 25% of administrative data to be digitalized |  | 0 administrative data digitalized | 25% | 0 | 22399775.17 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Data Management | 100% production of Demographic Dividend (DD) Roadmap and Estimation Report, made available on the State’s website |  | 0 production of Demographic Dividend (DD) Roadmap and Estimation Reports, made available on the State’s website | 100% | 0 | 16327500 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Development Partnership Coordination | 23 Development Partners to be sourced |  | 3 Development Partners sourced | 23 | 3 | 53468536.83 | 0 | 13.04% | 0% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Development Partnership Coordination | 35 Grants to be received |  | 0 Grants received | 35 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Development Partnership Coordination | 10 Loans to be received |  | 0 Loans received | 10 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Development Partnership Coordination | 33 Counterpart Fundings to be received |  | 0 Counterpart Fundings received | 33 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Lagos Resilience | 1000 copies of Resilience Assessment Reports to be produced |  | 0 copies of Resilience Assessment Reports produced | 1000 | 0 | 456100000 | 3820000 | 0% | 0.8375% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Facilitated data banking to ensure that Lagos state enjoys significant support from development partners | Lagos Resilience | 6 Resilience workshops to be conducted |  | 1 Resilience workshop conducted | 6 | 1 |  |  | 16.67% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Improved resilience of individuals, communities, institutions, businesses and systems within Lagos State | Lagos Resilience | 25 MDAs to be reached |  | 25 impementing MDAs reached | 25 | 25 |  |  | 100% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Improved resilience of individuals, communities, institutions, businesses and systems within Lagos State | Lagos Resilience | 40 Stakeholders to be engaged |  | 5 Stakeholders engagement conducted | 40 | 5 |  |  | 12.5% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Improved resilience of individuals, communities, institutions, businesses and systems within Lagos State | Lagos Resilience | 4 Resilience Risk Assessments to be conducted |  | 0 Resilience Risk Assessments conducted | 4 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Improved resilience of individuals, communities, institutions, businesses and systems within Lagos State | Social Protection Coordination | 20 SFMDAs Social Intervention to be Mapped |  | 5 SFMDAs that included SP into their programmes | 20 | 5 | 83818581.27 | 43258251 | 25% | 51.61% |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Improved resilience of individuals, communities, institutions, businesses and systems within Lagos State | Social Protection Coordination | 10 SP Stakeholders Advocacy and Sensitisation to be conducted(including 5 Ibile Division SP campaign) |  | 5 SFMDAs that aligned SP measures with their interventions | 10 | 5 |  |  | 50% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust and sustainable policies, efficient & effective Resource management while ensuring value for money and improve reporting system of MDAs | Social Protection Coordination | 20 SFMDAs to be Alligned their SP Programs with SP Measures |  | 0 High level social Protection Dialogue with SFMDAs, Accounting officers and Local Government | 20 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust and sustainable policies, efficient & effective Resource management while ensuring value for money and improve reporting system of MDAs | Social Protection Coordination | 300 SP Practitioners to be trained |  | 57 Sytem strengthening of Social Protection services at local Government level (MIS & M&E equipment and facilities) | 300 | 57 |  |  | 19% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Economic Planning and Budget | Effective Governance | Robust and sustainable policies, efficient & effective Resource management while ensuring value for money and improve reporting system of MDAs | Social Protection Coordination | 6 Intervention Programmes to be tracked and documented |  | 0 Intervention Programmes tracked and documented | 6 | 0 |  |  | 0% |  |  | 0% |  | General Public Services | Ministry of Economic Planning and Budget
General Public Services | Ministry of Information and Strategy | Thriving Economy | Promoted and propagated online access to government information on social media | Corporate Media | 600,000 Lasg facebook followers |  | 511,014 Lasg facebook followers | 600,000 | 511,014 | 149330100 | 0 | 85.17% | 0% |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Promoted and propagated online access to government information on social media | Corporate Media | 1,200,000 Lasg x followers |  | 1,070,567 Lasg x followers | 1,200,000 | 1,070,567 |  |  | 89.21% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Promoted and propagated online access to government information on social media | Corporate Media | 240,000 Lasg instagram followers |  | 251,304 Lasg instagram followers | 240,000 | 251,304 |  |  | 100% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Promoted and propagated online access to government information on social media | Corporate Media | 3,600 Lasgpage youtube followers |  | 3,776 Lasgpage youtube followers | 3,600 | 3,776 |  |  | 100% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Awareness created on all government programmes and policies. | Public Sensitization | 3000 Public advocacy visited |  | 800 Public Advocacy visited | 3000 | 800 | 1300000000 | 0 | 26.67% | 0% |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Awareness created on all government programmes and policies. | Public Sensitization | 2800 meetings with focus group: Artisan group, CDCS/CDAS,Lagos State Parks & Garage Managemnet Authority (LSPGMA) |  | 600 Meetings with focus group | 2800 | 600 |  |  | 21.43% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Awareness created on all government programmes and policies. | Public Sensitization | 1000 markets sensitized |  | 300 Markets Sensitized | 1000 | 300 |  |  | 30% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Awareness created on all government programmes and policies. | Public Sensitization | 750 Public Sensitization |  | 150 Public Sensitization | 750 | 150 |  |  | 20% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Visualized Government progress and initiatives through graphical representation | Public Sensitization | 4000 executives charts to be produced |  | 4000 Executives charts produced | 4000 | 4000 |  |  | 100% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Branded Government and public through informative statement/ Corporate gift items. | Public Sensitization | 5000 facts and figures charts to be produced |  | 5000 Facts and figures charts produced | 5000 | 5000 |  |  | 100% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Branded Government and public through informative statement/ Corporate gift items. | Advertorial Service | 2780 Press releases issued to the Media |  | 560 Press releases issued to the Media | 2780 | 560 |  |  | 20.14% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Branded Government and public through informative statement/ Corporate gift items. | Advertorial Service | 200 Features stories to the Media |  | 45 Features stories to the Media | 200 | 45 |  |  | 22.5% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Branded Government and public through informative statement/ Corporate gift items. | Advertorial Service | 123 Documentaries to be produced |  | 25 Documentaries Produced | 123 | 25 |  |  | 20.33% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Branded Government and public through informative statement/ Corporate gift items. | Advertorial Service | 50 Jingles to be Produced |  | 5 Jingles Produced | 50 | 5 |  |  | 10% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
General Public Services | Ministry of Information and Strategy | Thriving Economy | Branded Government and public through informative statement/ Corporate gift items. | Public Sensitization. | 4 (Quarterly) Citizens Engagement to be held |  |  | 4 |  | 63326524 |  | 0% |  |  | 0% |  | General Public Services | Ministry of Information and Strategy
Health Sector | Ministry of Health (DFH&N) | Human-Centric City | Availability of medicines for the patients in the rehabilitation centre to ensure they're restored to health and relapse prevented | Supply Drugs/Medicines and Medical Consunmables to Majidun Rehabilitation Centre annually | 17 Classes of Medicines to be supplied | 0 | Nil supplied | 17 | Nil | 14701223.9 | 0 |  | 0% | To be done in Q2 | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | coordinated and implemented strategies to combat drug abuse and ensuring the effective enforcement of drug control laws within the State. | Conduct Quarterly Meeting of The Lagos State Interministerial Drug Abuse Control Committee (LSIDACC) in conjuction with NDLEA and Relevant Stakeholders (Ministry of Basic and Secondary education and Office of Education Quality Assurance) in attendance to develop and work out implementation of road maps and activities for drug abuse prevention and control in the State with 25 Stakeholders in attendance | 4 meetings held before the year ends | 0.25 | Nil meeting held | 4 | Nil | 650000 | 0 |  | 0% | To be done in Q3 | 6.25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Awareness about the dangers of drug abuse and its harmful impact on individuals amongst the residence of Lagos State. | Commemorate the UN International Day against Drug Abuse and Illicit Trafficking for Awareness Creation and health promotion on drug abuse prevention and control annually for 150 participants including LSDACC members,invited guests and 2 facilitators | 150 participants to take part in the Drug Abuse and Illicit Trafficking Awareness Creation program |  | NIl participants | 150 | NIl | 4825000 | 0 |  | 0% | planned for Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | increased awareness and understanding of the risks associated with hard drugs use, leading to healthier decision-making | Organize a 2-Days Youth summit on drug/substance abuse prevention & control for health promotion with 40 participants and 10 LSDACC members and 2 facilitators annually | 40 youths with improved knowledge on drug/substance abuse prevention & control for health promotion |  | Nil Youths | 40 | Nil | 6646864 | 0 |  | 0% | Done in Q4 Awaiting approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Smooth transportation of task force personnel for daily operational activities | Carry out maintainance of 2 existing utility vehicles for daily operational activities bi-annually | 100% work done on service of utility vehicles |  | Nil work done | 100% | Nil | 1472608 | 0 |  | 0% | Done Q2 and Q4 Awaiting approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Efficient Wastewater Treatment with no backups or blockages and reduced risk of Health deffect | Conduct a one-off renovation of the septic tank | 100% renovation work to be done |  | Nil work done | 100% | Nil | 500000 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Top notch security for the task force office and premises | Purchase of 2 high quality padded and durable security doors for the Office block entrances | 100% work to be done |  | Nil work done | 100% | Nil | 1000000 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Efficient and Functional vehicles for taskforce | Conduct one-off overhaulling of 2 Utility vehicle engines to enhance daily workflow | 2 Utility vehicle engines to be overhauled |  | Nil engines overhauled | 2 | Nil | 4883235 | 0 |  | 0% | Awaiting Approval to be done in Q3 |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Improved regulated public health surveillance feedback | Carry out Tri-annual Pre-Task-force Enforcement surveilance activity to identify locations needing enforcement | 3 surveillance activities to be carried out to cover a wide range of communities and locations |  | Nil surveillance activities carried out | 3 | Nil | 360000 | 0 |  | 0% | Done in Q2-Q4 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | The task force is well-prepared, coordinated, and aligned for effective and efficient enforcement actions. | Conduct Task Force review and planning meeting with 10 committee members in attendance to plan the tri-annual enforcement exercise | 3 meetings to be conducted |  | Nil meetings held | 3 | Nil | 600000 | 0 |  | 0% | Done in Q2-Q4 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Improved compliance with regulatory standards, enhanced public health safety, and a reduction in the distribution of substandard or unapproved medicines. | Conduct Tri-annual Task-force Enforcement activities to Pharmacies, and PPMVs as well unregistered medicine stores to enforce adeherence to prescribed standards with 22 personnel in attendance | 90 Facilities to be inspected |  | Nil facilities inspected | 90 | Nil | 5572000 | 0 |  | 0% | Done in Q2-Q4 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | comprehensive evaluation of the enforcement operation’s effectiveness, identifying successes, challenges, and areas for improvement | Conduct Task Force Post operation meeting with 10 committee members in attendance to conclude on the task force enforcement activities conducted | 90 Facilities to be inspected completely evaluated |  | Nil facilities inspected and evaluated | 90 | Nil | 600000 | 0 |  | 0% | Done in Q2-Q4 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Quality Assurance of medicines, water and other medical products | Carry out a one-off equipping of the Drug Quality Control Laboratory (DQCL) to carry out Quality Assurance of medicines, water and other medical products | 100% work to be done |  | Nil work done | 100% | Nil | 23065517 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Efficient drug analysis and other opreations | Carry out annual Maintenance of Specialised Equipment of the Drug Quality Control Laboratory (DQCL) for efficient drug analysis and opreations | 100% Maintainance to be done |  | Nil work done | 100% | Nil | 6115955 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Availability of required reagents and chemicals needed for efficient drug analysis and other operations | Carry out annual procurement of chemicals & reagents for drug analysis and opreations at the Drug Quality Control Laboratory (DQCL) | 100% Procurement of chemicals and reagents |  | Nil Procurement | 100% | Nil | 8377898 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Improved awareness on enhanced public health safety, and Quality testing of drugs to deem it fit for public distribution, along side compliance with regulatory standards | Carry out promotion and advocacy for the activities of Drug Quality Control Laboratory (DQCL) and Pharmaceutical Inspectorate Unit for awareness creation of Task Force on counterfeit and fake drugs annually for safeguarding the health of the general populace | 211 Samples to be analyzed annually |  | Nil samples analyzed | 211 | Nil | 584770.9 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Enhanced access to authoritative resources that support accurate and up-to-date quality control testing, ensuring compliance with industry standards and improving the overall effectiveness of the laboratory's Quality Assurance (QA) processes. | Purchase annually reference books for Drug Quality Control Laboratory (DQCL) Library Services for Quality Assurance check | 100% of the reference books to be purchased |  | Nil reference books purchased | 100% | Nil | 3216240 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Improved capacity to conduct essential preclinical safety and efficacy testing, ensuring that medicines and health products meet regulatory standards before reaching the market. | Purchase Laboratory Animals used in carrying out quality assurance testing of medicines and other health products annually | 47 Animals (11 Rabbits, 26 Mice, and 10 Animal feed pellets to be purchased) |  | Nil animals purchased | 47 | Nil | 696595 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Ensured public health protection through the consistent delivery of safe, high-quality drinking water, meeting regulatory standards. | Monitor & evaluate portable water produced by the Lagos State Water Coopreation (LWC) for Safety & Quality Assurance annually | 296 water units to be monitored and evaluated |  | Nil water units monitored and evaluated | 296 | Nil | 2207978 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Enhanced patient safety through the early detection, evaluation, and management of drug-related risks | Conduct Biannual Pharmacovigilance Review Meetings for the purpose of ensuring the safety of medicines and public health with 40 participants in attendance | 2 meetings to be conducted yearly |  | Nil meetings conducted | 2 | Nil | 1164259 | 0 |  | 0% | Done in Q3 & Q4 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | A more integrated and efficient NHLMIS, enhancing the accuracy, visibility, and real-time management of health program (HIV & Malaria) data across the supply chain | Conduct a quarterly HIV & Malaria LMIS review meetings for SHF & LGA Pharmacists & Lab Scientists for 60 participants to ensure all health programmes data mangement including vaccines, Essential Medicines and other supply chain functionalities integrated into NHLMIS | 4 meetings to be conducted annually Review of LMIS reports | 0.25 | Nil meetings conducted | 4 | Nil | 3440000 | 0 |  | 0% | Awaiting Approval | 6.25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Improved strategic alignment and decision-making in procurement and logistics operations, leading to more efficient, cost-effective, and timely supply chain management. | Conduct Quarterly Procurement and Supply Chain Management Technical Working Group Meeting for Supply Chain & Logistics Management decision making with 40 particpants in attendance | 4 Quartely Procurement and Supply Chain Management Technical Working Group meetings held | 0.25 | Nil meetings conducted |  | Nil | 920000 | 0 |  | 0% | Awaiting approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Improved strategic alignment and decision-making in procurement and logistics operations, leading to more efficient, cost-effective, and timely supply chain management. | Conduct Quarterly LMCU meetings with supply chain implementing partners for the optimization of Logistics and Supply Chain with 24 participants in attendance | Four (4) meetings with Supply Chain IP held | 0.25 | Nil meetings conducted | Four | Nil | 324000 | 0 |  | 0% | Awaiting approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Enhanced performance and efficiency of supply chain operations through continuous monitoring, guidance, and corrective actions/ | Quarterly Monitoring and Supportive Supervisory Visits (MSSV) on LMIS and SCM to ensure optimal performance of Supply Chain & Logistics Management activities with 6 officers | 70 health facilities to be visited during MSSV | 0.25 | Nil health facilities visited | 70 | Nil | 696000 | 0 |  | 0% | Awaiting approval | 0.3571% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | A more cohesive and streamlined logistics and supply chain management system, with aligned processes, protocols, and data standards across all stakeholders. | Conduct annual LGA LMCU Review Meeting for Logistics & Supply Chain Management harmonization with 90 particpants | 1 meeting to be conducted |  | Nil meetings conducted | 1 | Nil | 1343500 | 0 |  | 0% | Done In Q4 |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Increased access to life-saving medications at the community level, ensuring that malaria and essential medicines are readily available to remote and underserved populations. | Conduct tri-annual Integrated Last Mile Distribution of Malaria and Essential Medicines to ensure medicine availability at the last mile | 3 LMD of malaria medicines and health commodities to be conducted |  | Nil LMD conducted | 3 | Nil | 8850000 | 0 |  | 0% | Done in O2-Q4 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Enhanced safety and functionality, securing a durable environment for security personnel to perform their duties effectively. | Execute a one-off replacement of the dilapidated roof at the security post in the Lagos State Central Medical Warehouse | 100% Replacement |  | Nil replacement | 100% | Nil | 333161 | 0 |  | 0% | Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Extension of the stock capacity in-store and meeting global standards of medical warehousing | Execute a one-off renovation of Warehouse B of the Lagos State Central Medical Store | 100% renovation work to be done |  | Nil work done | 100% | Nil | 22980000 | 0 |  | 0% | Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Improved efficiency and effectiveness in inventory management | Conduct a 1 day quarterly non-residential capacity building for 25 LSMS staff on optimising warehousing operational processes. | 4 capacity building training on optimising warehousing operational processes conducted | 0.25 | Nil capacity building trainings held | 4 | Nil | 3859959 | 0 |  | 0% | Awaiting Approval | 6.25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Improved coordination and streamlined logistics | Carry out local movements for daily operational activities outside of the warehouse by staff monthly running cost. | 100% logistics & transportation | 0.25 | Nil logistics | 100% | Nil | 1800000 | 0 |  | 0% | Awaiting Approval | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Consistent operational efficiency and a safe, functional environment across both the office and warehouse facilities. | Maintain 3 office buildings and 7 warehouses quarterly running cost | 4 Complete maintainance of offices and warehouses to be carrried out | 0.25 | Nil maintenance | 4 | Nil | 3800000 | 0 |  | 0% | Awaiting Approval | 6.25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | enhanced staff safety, professionalism, and efficiency. | Purchase 2 pairs of warehouse uniform and protective gear for 20 staff of the warehouse annually | 100% Purchase |  | Nil purchase | 100% | Nil | 1400000 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | increased operational efficiency and compliance in the medical warehouses | Conduct a one-off equipping of the 2 newly renovated Pharmagrade warehouses D and E to enable operationalization for Logistics and Supply chain Activities | 100% equipment of warehouse |  | NIl equipment of warehouse | 100% | NIl | 9000000 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Improved documentation, accountability, and traceability. | Print 19,769 reporting and requisition tools (SRIV booklets, Store form 3, Gate Pass) for warehouse operational activities annually | 19,769 reporting and requisition tools to be printed | 0.25 | Nil printing | 19,769 | Nil | 4559030 | 0 |  | 0% | Awaiting Approval | 0.001265% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Smooth and uninterrupted office operations, | Purchase of office running consumables anually | 100% of office running consumables to be purchased |  | Nil purchase | 100% | Nil | 3600000 | 0 |  | 0% | Done in Q2 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Improved organization, storage efficiency, and inventory management. | Purchase of 200 Pallets for The Medical Store / Warehouse Annually | 200 Pallets for The Medical Store / Warehouse to be purchased |  | Nil purchase | 200 | Nil | 6000000 | 0 |  | 0% | Done in Q3 Awaiting Approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | An improved, safe, and well-maintained environment, | Maintain the warehouse surrounding by mowing monthly | 100% maintainace of warehouse surroundings | 0.25 | Nl purchase | 100% | Nl | 1800000 | 0 |  | 0% | Awaiting Approval | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | An improved, safe, and well-maintained environment, | Maintain the warehouse surrounding by mowing monthly | 100% utilization | 0.05 | Nil utilization | 100% | Nil | 100000000 | 0 |  | 0% |  | 5% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Leadership, policy, and regulatory framework development | Healthcare Planning (Policy development and review, Implementation of HRH strategic plan, Development of health plans) | 67% compliance to be achieved on submission of all required reports according to the schedule | 0.2 | Nil compliance | 67% | Nil | 73760851.67 | 0 |  | 0% |  | 29.85% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Enhanced data reporting and quality through training | Monitoring and Evaluation Unit | 67% compliance to be achieved on submission of all required reports according to the schedule | 0.5 | Nil compliance | 67% | Nil | 65000000 | 0 |  | 0% |  | 74.63% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Improved alternative funding acquisition for healthcare | Health Financing (TWG meetings, Development of business case for health, capacity building on health financing and economics, operational research) | 4 TWG meetings to be held with a minimum attendance rate of 80% | 1 | Nil TWG meetings held | 4 | Nil | 58356044.55 | 0 |  | 0% |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Establishment of legislative framework for quality healthcare | Quality initiatives programmes and projects (Monitoring visits, integrated supportive supervision, capacity building of healthcare workers, review of health care standards) | 60% of healthcare facilities to possess and actively utilize the quality document and guideline | 0.15 | Nil healthcare facilities possess and actively utilize the quality document and guideline | 60% | Nil | 16761228.89 | 0 |  | 0% |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Enhanced compliance with service standards and policies | Service Charter Initiatives (sensitization on strategic service improvement plans, customer care service, capacity building) | 100% operationalization of the Strategic Service Improvement Plans (SIPs) to be achieved in cascade health facilities | 0.25 | 59% operationalization of SIPs achieved | 100% | 59% | 15141165.09 | 0 | 59% | 0% |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Enhanced healthcare accessibility and quality | New Projects in Health (Renovation and Construction) | 30% of new secondary health facilities renovation/construction works to be completed | 5 | 10% of new secondary health facilities renovation/construction works completed | 30% | 10% | 5050019695.86 | 0 | 33.33% | 0% |  | 100% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Enhanced healthcare accessibility and quality | Ongoing Projects in Health (Renovation and Construction) | 50% of ongoing targeted secondary health facilities renovation/construction works to be completed | 6 | 12.5% ongoing targeted secondary health facilities renovation/construction works completed | 50% | 12.5% | 13799346388.61 | 0 | 25% | 0% |  | 100% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Enhanced healthcare accessibility and quality | Liability Projects in Health | 75% of reduction in the outstanding liability related to health projects | 3 | Nil reduction in the outstanding liability | 75% | Nil | 950000000 | 0 |  | 0% |  | 100% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DPS) | Human-Centric City | Enhanced healthcare system responsiveness through evidence-based policy decisions and targeted capacity expansion | Annual Operational Research | 100% completion of the operational report | 0.25 | Nil completion | 100% | Nil | 2875000 | 0 |  | 0% | funds not available, memos raised | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DNS) | Thriving Economy | Enhanced healthcare system responsiveness through evidence-based policy decisions and targeted capacity expansion | Supportive Supervision for midwives who went through ALSS program. | 60% of midwives to be trained on ALSS who received both 6-week and 6-month supportive supervision visits | 0.15 | Nil midwives trained | 60% | Nil | 16307300 | 0 |  | 0% | funds not available, memos raised | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (DNS) | Human-Centric City | Enhanced healthcare system responsiveness through evidence-based policy decisions and targeted capacity expansion | Monthly supervisory visits to PHCS for mandatory community services for Midwives. | 12 scheduled supervisory visits for midwives' mandatory community services conducted per month | 3 | Nil supervisory visits | 12 | Nil | 1876800 | 0 |  | 0% | funds not available, memos raised | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSACA PREVENTIVE SERVICES) | Human-Centric City | Reduced HIV Stigma and Increased Testing: Achieving Epidemic Control by 2025 | Advocacy and Sensitization | 70% increase in the number of individuals correctly identifying modes of HIV transmission and prevention methods post-campaign. |  | Nil increase | 70% | Nil | 77017564 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSACA PREVENTIVE SERVICES) | Human-Centric City | Reduced HIV Stigma and Increased Testing: Achieving Epidemic Control by 2025 | 3HTS Scale-up | 70% increase in the number of individuals undergoing HIV testing |  | Nil increase | 70% | Nil | 48563322.98 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSACA PREVENTIVE SERVICES) | Human-Centric City | Reduced HIV Stigma and Increased Testing: Achieving Epidemic Control by 2025 | Adolescent and young people interventions | 75% increase in knowledge retention among adolescents and young people regarding HIV prevention methods following intervention sessions |  | Nil increase | 75% | Nil | 33760265 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSACA PREVENTIVE SERVICES) | Human-Centric City | Reduced HIV Stigma and Increased Testing: Achieving Epidemic Control by 2025 | Special Event and Celebration | 70% increase in HIV awareness among event attendees measured through pre- and post-event surveys |  | Nil increase | 70% | Nil | 39930000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSACA PREVENTIVE SERVICES) | Human-Centric City | Reduced HIV Stigma and Increased Testing: Achieving Epidemic Control by 2025 | Support for PLWHAs and support groups | 70% increase in PLWHA engagement in support groups and utilization of support services |  | Nil increase | 70% | Nil | 27665825 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSACA PREVENTIVE SERVICES) | Human-Centric City | Enhanced HIV Testing Access: Fulfilling the 90-90-90 Initiative by 2025 | Procurement of HIV rapid test kits and consumables | 85% increase in the number of HIV tests conducted using procured rapid test kits and consumables |  | Nil increase | 85% | Nil | 111782880 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSACA PREVENTIVE SERVICES) | Human-Centric City | HIV Prevention Along Major Routes | Lagos Abidjan Corridor (ALCO) Project | 3% decrease in the HIV positivity rate among individuals tested along the Lagos Abidjan Corridor |  | Nil decrease | 3% | Nil | 15088764.92 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSACA PREVENTIVE SERVICES) | Human-Centric City | Condom Distribution for Safer Practices: Stemming HIV Transmission: Stemming HIV Transmission | Procurement of condom | 3% decrease in the incidence of new HIV infections attributed to unprotected sexual activity |  | Nil decrease | 3% | Nil | 39960000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSACA PREVENTIVE SERVICES) | Human-Centric City | Informed Interventions through Research: Informing Policy for Effective Programs | Operational Research | 3% decrease in the rate of HIV transmission among targeted populations as a result of operational research findings implemented into practice |  | Nil decrease | 3% | Nil | 12749000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSACA PREVENTIVE SERVICES) | Human-Centric City | Elevated HIV Awareness: Preventing Infections through Public Engagement | HIV and AIDS Publication, Publicity & Awareness | 3% decrease in HIV positivity rates in areas with high exposure to HIV and AIDS publications and awareness campaigns |  | Nil decrease | 3% | Nil | 28930000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSACA PREVENTIVE SERVICES) | Human-Centric City | Elevated HIV Awareness: Preventing Infections through Public Engagement | Project Support Activities and Procurement of Operational Vehicles | 50% increase in the timely delivery of HIV-related services facilitated by the availability of operational vehicles |  | Nil increase | 50% | Nil | 160052500 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (HEFAMAA QUALITY ASSURANCE) | Human-Centric City | Enhanced healthcare quality through standardized regulations | HEFAMAA Accreditation | 10% of health facilities to be accredited |  | Nil health facilities accredited | 10% | Nil | 44000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (HEFAMAA QUALITY ASSURANCE) | Human-Centric City | Enhanced healthcare quality through standardized regulations | Monitoring and Inspection of Health facilities | 82% of health facilities to be inspected for compliance with regulatory standards |  | Nil health facilities inspected | 82% | Nil | 44000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (HEFAMAA QUALITY ASSURANCE) | Human-Centric City | Enhanced healthcare quality through standardized regulations | Establishment of Zonal offices. | 3 zonal offices to be established and fully operational |  | Nil zonal offices established | 3 | Nil | 86000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (HEFAMAA QUALITY ASSURANCE) | Human-Centric City | Enhanced healthcare quality through standardized regulations | Electronic Health Facilities Evaluation tool. | 100% development and operationalization of the Electronic Health Facilities Evaluation tool completed |  | Nil development and operationalization | 100% | Nil | 30000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (HEFAMAA QUALITY ASSURANCE) | Human-Centric City | Enhanced healthcare quality through standardized regulations | Upgrade of e – HEFAMAA Portal | 100% of identified health facilities to be renewed and registered through the upgraded e-HEFAMAA Portal |  | Nil identified health facilities renewed and registered | 100% | Nil | 30000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (HEFAMAA QUALITY ASSURANCE) | Human-Centric City | Enhanced healthcare quality through standardized regulations | Health Facilities Identification Logo | 90% of registered health facilities equipped with the official identification logo to be displayed visibly |  | Nil registered health facilities equipped | 90% | Nil | 10000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (HEFAMAA QUALITY ASSURANCE) | Human-Centric City | Enhanced healthcare quality through standardized regulations | Research on quality of health care delivery in the state. | 100% of research milestones to be achieved, including data collection, analysis, and reporting on the quality of healthcare delivery in the state |  | Nil research milestones achieved | 100% | Nil | 15000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASHMA HEALTH FINANCING) | Human-Centric City | Enhanced participation in Lagos Health Insurance Scheme through community-driven advocacy and leadership collaboration | ICT Equipment | 100% reduction in downtime experienced as a result of ICT equipment failures |  | Nil reduction in downtime experienced | 100% | Nil | 117044696 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASHMA HEALTH FINANCING) | Human-Centric City | Enhanced participation in Lagos Health Insurance Scheme through community-driven advocacy and leadership collaboration | Relocation of Office Space | 100% completion of office relocation project |  | Nil completion | 100% | Nil | 50000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASHMA HEALTH FINANCING) | Human-Centric City | Enhanced participation in Lagos Health Insurance Scheme through community-driven advocacy and leadership collaboration | Set up Grassroot Presence | 100% of identified grassroots communities reached by the outreach program |  | Nil grassroots communities reached | 100% | Nil | 30000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSBTS CURATIVE SERVICES) | Human-Centric City | Boosted voluntary blood donor numbers, dispelling myths and increasing awareness | Voluntary Blood Donation Advocacy (publicity / educate senior secondary school students on VBDD) | 312 Advocacy sessions to be conducted in community venues, secondary schools, and workplaces |  | Nil Advocacy sessions conducted | 312 | Nil | 35000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSBTS CURATIVE SERVICES) | Human-Centric City | Boosted voluntary blood donor numbers, dispelling myths and increasing awareness | Voluntary Blood Donor Recruitment & Drive | 234 Voluntary blood donation drives to be organized and completed |  | Nil Voluntary blood donation drives organized and completed | 234 | Nil | 100000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSBTS PREVENTIVE SERVICES) | Human-Centric City | Enhanced blood transfusion safety through certified screening and increased voluntary donor participation | Screening and Certification of all donated blood (PPP) | 180,000 units of blood to be released from screening and certification free of Transfusion Transmissible Infections (TTIs) before use. |  | Nil units of blood released | 180,000 | Nil | 30000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSBTS PREVENTIVE SERVICES) | Human-Centric City | Enhanced blood transfusion safety through certified screening and increased voluntary donor participation | Sensitization on Health Celebration Days | 10 World Health Observance Days to be celebrated with dedicated sensitization campaigns. |  | Nil World Health Observance days celebrated | 10 | Nil | 20000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSBTS HEALTH QUALITY SERVICES) | Human-Centric City | Enhanced Blood Bank Regulation: Ensured compliance with LSBTS Law & International Standards. | Monitoring and Enforcement | 95% of licensed blood transfusion facilities to achieve full compliance with regulatory standards |  | Nil licensed blood transfusion facilities achieved full compliance | 95% | Nil | 85000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSBTS HEALTH QUALITY SERVICES) | Human-Centric City | Heightened Blood Donation Awareness: Increased community, corporate, & NGO engagement. | Stakeholder & Partnership Engagement with communities, Corporate & NGO | 3 participating organizations in stakeholder meetings, indicating the breadth of engagement and collaboration across sectors. |  | Nil participating organizations in stakeholder meetings | 3 | Nil | 30000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LSBTS HEALTH QUALITY SERVICES) | Human-Centric City | Sustainable Blood Donation Environment: Expanded voluntary donation centers for long-term support. | Expansion of Voluntary Blood Donation centres | 100% completion of expansion work on voluntary blood donation centers |  | Nil completion | 100% | Nil | 75000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (EMERGENCY SERVICES)) | Human-Centric City | Improved healthcare access and services through infrastructure enhancement and specialized equipment procurement | Medical Gas | 95% uptime for uninterrupted and reliable supply of medical gases |  | Nil uptime | 95% | Nil | 90000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (EMERGENCY SERVICES)) | Human-Centric City | Improved healthcare access and services through infrastructure enhancement and specialized equipment procurement | Expansion of Medical Emergency Unit/Renovation of Surgical Emergency | 100% completion of renovation work |  | Nil completion | 100% | Nil | 116000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (EMERGENCY SERVICES)) | Human-Centric City | Improved healthcare access and services through infrastructure enhancement and specialized equipment procurement | Procurement of Specialized Medical equipment | 100% identified specialized medical equipment to be procured and installed |  | Nil equipment procured | 100% | Nil | 506237000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (EMERGENCY SERVICES)) | Human-Centric City | Improved healthcare access and services through infrastructure enhancement and specialized equipment procurement | Renovation of Burns Units LASUTH Ikeja | 100% completion of renovation work |  | Nil completion | 100% | Nil | 19120516.66 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (EMERGENCY SERVICES)) | Human-Centric City | Improved healthcare access and services through infrastructure enhancement and specialized equipment procurement | Renovation of ENT (Ear, Nose & Throat) Extension | 100% completion of renovation work |  | Nil completion | 100% | Nil | 22022520 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (EMERGENCY SERVICES)) | Human-Centric City | Improved healthcare access and services through infrastructure enhancement and specialized equipment procurement | Upgrading of Dental Complex | 100% of dental complex to be upgraded |  | Nil upgrade of dental complex | 100% | Nil | 15000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (EMERGENCY SERVICES)) | Human-Centric City | Improved healthcare access and services through infrastructure enhancement and specialized equipment procurement | Renovation of Eye Clinic | 100% completion of renovation work |  | Nil completion | 100% | Nil | 15000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (EMERGENCY SERVICES)) | Human-Centric City | Improved healthcare access and services through infrastructure enhancement and specialized equipment procurement | Renovation of Pharmacy Building | 100% completion of renovation work |  | Nil completion | 100% | Nil | 7000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (EMERGENCY SERVICES)) | Human-Centric City | Improved healthcare access and services through infrastructure enhancement and specialized equipment procurement | Provision of Medical Oxygen Pipeline to Ayinke House | 100% of medical oxygen pipeline installation to be completed |  | Nil completion | 100% | Nil | 55763000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (QUALITY ASSURANCE)) | Human-Centric City | Improved public health services and increased patient accessibility | Accreditation/International Accreditation of departments | 100% Progress towards meeting accreditation standards |  | Nil Progress | 100% | Nil | 32377963.34 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (QUALITY ASSURANCE)) | Human-Centric City | Improved public health services and increased patient accessibility | Funding Research programmes/Continuing Medical Education (CME) | 100% of identified Research programmes/Continuing Medical Education (CME) to be conducted |  | Nil Research programmes/Continuing Medical Education (CME) conducted | 100% | Nil | 33000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (QUALITY ASSURANCE)) | Human-Centric City | Improved public health services and increased patient accessibility | Upgrading of Engineering Workshop | 100% of engineering workshop to be upgraded |  | Nil upgrade of engineering workshop | 100% | Nil | 20000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (QUALITY ASSURANCE)) | Human-Centric City | Improved public health services and increased patient accessibility | Internal & External Branding | 100% of internal branding initiatives and external branding campaigns to be completed |  | Nil branding completed | 100% | Nil | 30000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (QUALITY ASSURANCE)) | Human-Centric City | Improved public health services and increased patient accessibility | Process Mapping and Automation of LASUTH | 100% of identified processes mapped and automated |  | Nil processes mapped and automated | 100% | Nil | 241000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (QUALITY ASSURANCE)) | Human-Centric City | Improved public health services and increased patient accessibility | Installation of Solar System | 100% of required solar panels to be installed |  | Nil installation | 100% | Nil | 135000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (QUALITY ASSURANCE)) | Human-Centric City | Improved public health services and increased patient accessibility | Radiotherapy Project | 100% of radiotherapy project to be completed |  | Nil completion | 100% | Nil | 25000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (QUALITY ASSURANCE)) | Human-Centric City | Improved public health services and increased patient accessibility | Re-connecting to PHCN | 100% of disconnected facilities re-connected to the PHCN grid |  | Nil re-connection | 100% | Nil | 65000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (QUALITY ASSURANCE)) | Human-Centric City | Improved public health services and increased patient accessibility | Renovation of Consultant Clinics, Call room and Hospital Laboratory | 100% completion of renovation |  | Nil completion | 100% | Nil | 60000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUTH (QUALITY ASSURANCE)) | Human-Centric City | Improved public health services and increased patient accessibility | Maintenance of resident Doctors quarters | 100% of maintenance tasks to be completed on resident doctors' quarters |  | Nil completion | 100% | Nil | 15000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUCOM (QUALITY ASSURANCE)) | Human-Centric City | Sustained Program Continuity | Accreditation and Re-Accreditation of programs; BDS, MBB; BS, Nursing, Physiology, Pharmacology | 100% Progress towards meeting accreditation standards |  | Nil Progress | 100% | Nil | 245000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUCOM (QUALITY ASSURANCE)) | Human-Centric City | Sustained Program Continuity | Resources assessment of Pharmacy and allied health programs | 100% completion of resource assessment reports for pharmacy and allied health programs |  | Nil completion | 100% | Nil | 125000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUCOM (QUALITY ASSURANCE)) | Human-Centric City | Sustained Program Continuity | Upgrade of Laboratories and animal house to international standard | 100% completion of upgrade |  | Nil completion | 100% | Nil | 60000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUCOM (QUALITY ASSURANCE)) | Thriving Economy | Enhanced Student Welfare | Construction of Hostel building at Agbowa for Rural Posting | 100% completion of construction |  | Nil completion | 100% | Nil | 150000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUCOM (QUALITY ASSURANCE)) | Human-Centric City | Sustained Program Continuity | Procurement of Biomedical equipment, Teaching Journals and Library Books | 100% of required Biomedical equipment, Teaching Journals and Library Books to be procured |  | Nil procurement | 100% | Nil | 120000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUCOM (QUALITY ASSURANCE)) | Human-Centric City | Sustained Program Continuity | Procurement of Medical, Dental and Laboratory Chemicals, Equipment and Clinical Simulators. | 100% of required Medical, Dental and Laboratory Chemicals, Equipment and Clinical Simulators to be procured |  | Nil procurement | 100% | Nil | 384000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASUCOM (QUALITY ASSURANCE)) | Human-Centric City | Sustained Program Continuity | Procurement of 10 Official Vehicles and 2 staff Buses | 100% of official vehicles and staff buses to be procured and delivered |  | Nil official vehicles and staff buses procured and delivered | 100% | Nil | 330000000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Enabling Environment for Staff | Construction of PHCB HQ | 70% Completion of Construction of PHCB HQ | 0.5 | 40% progroess | 70% | 40% | 692201292.84 | 0 | 57.14% | 0% |  | 71.43% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Continuity of Programmes | Construction and Rehabilitation of PHCCs | 100% work to be done (19 PHCs to be renovated and adequately equipped) | 0.7 | 75.3% progress for the 19 PHCs being renovated | 100% | 75.3% | 845005739.14 | 0 | 75.3% | 0% |  | 70% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Continuity of Programmes | Construction & equipping of PHCCs/ Outstanding Liabilities of PHCCs | 100% liability commitment to be concluded based on Project progress | 0.25 | Nil Liability serviced (4 PHCs constructions ongoing ) | 100% | Nil | 177373511.02 | 0 |  | 0% |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Improved Medical Service Delivery | Medical Laboratory Equipment | 100% of required consumables, Completion PEPs and Smearing Shade to be procured | 0.25 | Nil procured Awaiting approval | 100% | Nil | 28000000 | 0 |  | 0% |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Accessible Storage Facilities | Renovation of cold chain store | 100% Stable and Safe Temperature Range for Vaccines Recorded | 0.25 | 100% Stable and Safe Temperature Range Recorded | 100% | 100% | 235000000 | 0 | 100% | 0% |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Preparedness for Outbreaks | Emergency Preparedness/Response to Outbreak Diseases at PHC level | 100% PHCs to be equipped with necessary resources for outbreak response (e.g., emergency supplies, trained personnel). | 0.25 | Nil PHCs equipped this quarter | 100% | Nil | 0 | 0 |  |  |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Promotion of Infant Nutrition | Procurement of food demonstration equipment for 57 PHCs | 100% of food demonstration equipment procured for 57PHCS | 0.25 | Nil procument done - awaiting approval | 100% | Nil | 20000000 | 0 |  | 0% |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Continuity of Family Planning Services | Family Planning | 100% of FP consumables for all PHCS offering family planning services to be procured | 0.25 | Nil procurement done - Awaiting approval | 100% | Nil | 30000000 | 0 |  | 0% |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Ensured Access to Essential Medicines and Vaccines | Procurement of Essential Medicines and Others (Drugs & Vaccines) | 100% Essential Medicines and Others (Drugs & Vaccines) to be procured | 0.25 | Nil procurement (1 approval but Awaiting release of approved N2,4NilNil,NilNilNil) | 100% | Nil | 35000000 | 0 |  | 0% |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Support for Immunization Programs | Support for PHC, WMHCP, IMNCH, NIPDS & Immunisation at PHC Level (Immunisation) | 80% Coverage of fully immunized under 1yr Children Target Population(n=655,608) | 0.25 | Nil coverage | 80% | Nil | 27492000 | 0 |  | 0% |  | 31.25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Implementation of Standard Infection Control Measures | Standard Infection Control Programme (Special Programmes | 100% Attendance at the Annual Management meeting of Tuberculosis and Leprosy Supervisors | 0 | Nil meeting - Awaiting approval | 100% | Nil | 7533600 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Support for School Health Programs | Support For School Health Programme (Public Health Education) | 20 Community dialogues with LGHA chairman and ward focals | 0.25 | Nil meeting - Awaiting approval | 20 | Nil | 2250000 | 0 |  | 0% |  | 1.25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Promotion of Nutrition and Health in Communities, Schools, and PHCs | Nutrition & Health Promotion In The Communities, Schools And PHCs (Special Programmes) | 100% Completion of Home-Grown school feeding Programme. | 0.25 | Nil engagement - Awaiting approval | 100% | Nil | 9131000 | 0 |  | 0% |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Quality Assurance in Healthcare Services | Quality Assurance | 100% Implementation of Standard Operating Procedure within the Primary Health Care for Quality assurance | 0.25 | Nil - Awaiting approval | 100% | Nil | 22259200 | 0 |  | 0% |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (PHCB) | Human-Centric City | Child Protection Measures Implementation | Child Protection | 100% attendance at Quarterly data Review Meetings for Child Protection Focal Persons in the phcs across 20 LGAs in the year | 0.25 | Nil meeting - Awaiting approval | 100% | Nil | 0 | 0 |  |  |  | 25% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (HSC (HEALTHCARE PLANNING, RESEARCH and STATISTICS)) | Human-Centric City | Enhanced healthcare capacity for managing demand surges while maintaining essential services | Recruitment (Recruitment Expenses) | 100% work to be done -4 recruitment cycles to be done (quarterly) | 1 | 25%- first cycle of recuitement excercise carried out | 100% | 25%- | 83186674 | 0 |  | 0% | Recuitement excercise scheduled for first quarter was carried out | 100% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (HSC (HEALTHCARE PLANNING, RESEARCH and STATISTICS)) | Human-Centric City | Enhanced healthcare capacity for managing demand surges while maintaining essential services | Career Management (Capacity Building and Human Resource Management) | 1,800 health workers to be trained & issued certificates | 0 | Nil health workers trained & issued certificates | 1,800 | Nil | 1209919264 | 0 |  | 0% | funds not available, memos raised | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (HSC (HEALTHCARE PLANNING, RESEARCH and STATISTICS)) | Human-Centric City | Enhanced healthcare capacity for managing demand surges while maintaining essential services | Documentation (Operational Medical Social Welfare) | 28 health care facilities to be monitored | 0 | Nil health care facilities monitored | 28 | Nil | 52285745 | 0 |  | 0% | funds not available, memos raised | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASAEC (EMERGENCY SERVICES)) | Human-Centric City | Enhanced emergency outbreak readiness | Curative Services | 75% of Scheduled Medical Procedures to be Completed |  | Nil completion | 75% | Nil | 7750000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASAEC (EMERGENCY SERVICES)) | Human-Centric City | Enhanced emergency outbreak readiness | Preventive Services | 75% of Preventive Health procedures (health Screenings, sterilization, immunization, capacity training) to be Completed |  | Nil completion | 75% | Nil | 13249834 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (LASAEC (EMERGENCY SERVICES)) | Human-Centric City | Enhanced emergency outbreak readiness | Emergency Services | 75% of Social interventions and digitalisation of social health care services to be carried out (to increase Percentage of Emergency Cases Treated) |  | Nil social interventions and digitalization | 75% | Nil | 174510500 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Improved Effectiveness of Staff | Fueling and quarterly servicing & maintainance of 4 utility vehicles | 4 Utility vehicles serviced and fuelled. |  | Nil vehicles serviced | 4 | Nil | 9574400 | 0 |  | 0% | memo written,awaiting approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Improved Effectiveness of Staff | Purchase of Personal protective equipment for Safety Officers | 40 protective equipments to be purchased for 40 officers |  | Nil purchase | 40 | Nil | 900000 | 0 |  | 0% | memo written,awaiting approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Improved Effectiveness of Staff and reduction in food borne illnesses and improved knowledge on public Health Law and safety laws in the State | Support for OHS Enforcement activities(2 Task force Officers, 5 OHS Officers,information personnel, 2TV station personnel,serving of court notices etc) for revenue generation activities | 100% support on Enforcement activities |  | Nil support | 100% | Nil | 521364.77 | 0 |  | 0% | memo written,awaiting approval |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Increased knowledge on foodborne risks, contributing to food security and human health. | Celebration of World Food Safety Day (June 7th) | 100% work to be done |  | Nil work done | 100% | Nil | 3130000 | 0 |  | 0% | To be done in Q2 | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Increased knowledge on foodborne risks, contributing to food security and human health. | Purchase of Equipments for SEHMU activities | 100% work to be done |  | Nil work done | 100% | Nil | 19644000 | 0 |  | 0% | To be done in Q2 | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Improved Effectiveness of Staff | Printing of 6,000 copies of Information, Education, and Communication (IEC) materials on Occupational Safety, Health, Welfare, and Environmental workers. | 100% work to be done |  | Nil work done | 100% | Nil | 2384787.92 | 0 |  | 0% | To be done in Q2 | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Reduction in infection through disinfection of disaster sites and pickup location of corpses. | Decontamination & disinfection of corpses pick up sites | 100% work to be done |  | Nil work done | 100% | Nil | 10173056.04 | 0 |  | 0% | memo written,awaiting approval | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Improved Knowledge of Staff on Public Health Issues | Training of Unit 5 (Five) staff to meet up with challenges and keep officers abreast of events on the activities of the Directorate | 100% work to be done |  | Nil work done | 100% | Nil | 108573.06 | 0 |  | 0% | memo written,awaiting approval | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Improved Effectiveness of Staff | Provision of ceremonial Outfits for Occupational Health and Safety enforcement Officers | 10 officers to be provided with outfits |  | Nil officers | 10 | Nil | 159762.16 | 0 |  | 0% |  |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Improved food safety and reduction in risks behaviors commonly associated with foodborne illness and outbreaks | Training of 800 food handlers annually for the protection of Public Health | 800 participants |  | Nil Participants | 800 | Nil | 2000000 | 0 |  | 0% |  |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Increased knowledge on Food Safety and Hygiene | Sensitization on HACCP For 800 Food/Water/Beverages Companies. | 800 participants |  | Nil Participants | 800 | Nil | 5744000 | 0 |  | 0% |  |  |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | To reduce environmental nuicaces and pollution through prompt (within 24hrs of notification) removal of unclaimed corpses | Purchase of 2,283 Adult Body bags (100×40 inch.) | 2,283 adult body bags to be purchased |  | Nil body bags | 2,283 | Nil | 57075000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Improved Effectiveness of Staff | Purchase of Equipment for Monitoring of Food safety & Environmental Pollution in Workplaces | 100% purchase of 5 Canon XixiaHFR50HD Camcoder 25units of BBQ Food robe thermometer 4 Airborne particle counter handheld 10 units of Gas probe and 10 units Dosimeter. |  | Nil purchase | 100% | Nil | 50990000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | To reduce environmental nuicaces and pollution through prompt (within 24hrs of notification) removal of unclaimed corpses | Carting away of unclaimed bodies from highways and decongestion of mortuaries. | 100% work to be done |  | Nil work done | 100% | Nil |  | 0 |  |  |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Raised awareness regarding the health of our environment. | Celebration of World Environmental Health Day | 100% work to be done |  | Nil work done | 100% | Nil | 3050000 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Improved Effectiveness of Staff | .Repairs and ovehauling of 4 SEHMU Vehicles | 100% work to be done |  | Nil work done | 100% | Nil | 4043625.88 | 0 |  | 0% |  | 0% |  | Health Sector | Ministry of Health
Health Sector | Ministry of Health (O & E HS) | Human-Centric City | Improved Effectiveness of Staff | Purchase of Equipments for Occupational /Health Services | 100% work to be done |  | Nil work done | 100% | Nil | 51440000 |  |  |  |  | 0% |  | Health Sector | Ministry of Health
Environmental Protection | Lagos State Waste Management Authority | Human-Centric City | Environmetally sound and Cleaner Environment | Waste Management Services (Public Market/Medical Waster Collection Domestic PSP (Subsidy Gap) Programme, Marine Waste Evacuation, Management of Landfill/Recycling, Waste Collection in CBD, Public School waste Programme/Backlog waste collection, Enlightment and Advocacy/policing, Capacity building, Street Sweeper, Highway Sanitation, Highway Managers). | 2,000,000 Metric Tonnes of waste to be collected and deposited at various Landfills. |  | 369,201 Metric Tonnes of waste collected and deposited | 2,000,000 | 369,201 | 16312848252 | 4084467125 | 18.46% | 25.04% | On going | 0% |  | Environmental Protection | Lagos State Waste Management Authority
Environmental Protection | Lagos State Waste Management Authority | Human-Centric City | Environmetally sound and Cleaner Environment | Construction of New Material Recovery Facility/Transfer Loading Stations (MRF/TLS) | 100% work to be done |  | Nil MRF/TLS constructed | 100% | Nil |  | 0 |  |  | Yet to commence | 0% |  | Environmental Protection | Lagos State Waste Management Authority
Environmental Protection | Lagos State Waste Management Authority | Human-Centric City | Environmetally sound and Cleaner Environment | Rehabilitation of HQ Workshop building | 100% work to be done |  | Nil work done | 100% | Nil |  | 0 |  |  | Yet to commence | 0% |  | Environmental Protection | Lagos State Waste Management Authority
Environmental Protection | Lagos State Waste Management Authority | Human-Centric City | Environmetally sound and Cleaner Environment | Purchase of 200 new Gas powered trucks | 200 LASG contribution for new Gas powered to be purchased. |  | Nil new Gas powered trucks purchased | 200 | Nil |  | 0 |  |  | Yet to commence | 0% |  | Environmental Protection | Lagos State Waste Management Authority
Environmental Protection | Lagos State Waste Management Authority | Human-Centric City | Environmetally sound and Cleaner Environment | Landfill Project (Demolition and Evacuation of illegal dump site at Lekki tollgate, Awoyaya bustop, lekki-epe express way,; illegal dumpsites from mile 2 bustop to Afromida bustop on Lagos Badagry Express way, Lagos, and Illegal dumpsites at Anthony Oke, Opposite TREM Church, Lagos | 100% work to be done |  |  | 100% |  | 1150000000 |  | 0% |  |  | 0% |  | Environmental Protection | Lagos State Waste Management Authority
Environmental Protection | Lagos State Waste Management Authority | Human-Centric City | Environmetally sound and Cleaner Environment | Adopt a bin (Purchase of 86,325 digitalized two wheeler smart bins)alozed | 100% work to be done |  |  | 100% |  | 6379957031.24 |  | 0% |  |  | 0% |  | Environmental Protection | Lagos State Waste Management Authority
Environmental Protection | Lagos State Waste Management Authority | Human-Centric City | Environmetally sound and Cleaner Environment | Refurbishment of Motor Vehicle (For Purchase of 315/80R22.5 (400 tyres) and 150 Amp Battery (136)) | 100% work to be done |  |  | 100% |  | 192860014.76 |  | 0% |  |  | 0% |  | Environmental Protection | Lagos State Waste Management Authority
Economic Affairs | Lagos State Infrastructure Asset Management Agency | Modern Infrastructure | Enhanced state infrastructure resilience | Facility Management of 22 state infrastructure | 6 MDAs planned maintenance activities to be completed |  | Nil MDAs planned maintenance activities completed |  | Nil | 4745083716.81 | 0 |  | 0% | delay in approval |  |  | Economic Affairs | Lagos State Infrastructure Asset Management Agency
Economic Affairs | Lagos State Infrastructure Asset Management Agency | Modern Infrastructure | Enhanced state infrastructure resilience | Facility Management of 22 state infrastructure | 14 health facilities planned maintenance activities to be completed |  | Nil health facilities planned maintenance activities completed | 14 | Nil |  |  |  |  | delay in approval | 0% |  | Economic Affairs | Lagos State Infrastructure Asset Management Agency
Economic Affairs | Lagos State Infrastructure Asset Management Agency | Modern Infrastructure | Enhanced state infrastructure resilience | Facility Management of 22 state infrastructure | 2 Educational facilities planned maintenance activities to be completed |  | Nil Educational facilities planned maintenance activities completed | 2 | Nil |  |  |  |  | delay in approval | 0% |  | Economic Affairs | Lagos State Infrastructure Asset Management Agency
Economic Affairs | Lagos State Infrastructure Asset Management Agency | Modern Infrastructure | Improved educational facility sustainability | Operation and maintainance of 50 educational facilities | 15% reduction to be achieved in unhealthy environments within the identified 50 public schools |  | 0% reduction to be achieved in unhealthy environments within the identified 50 public schools | 15% | 0% | 254916283.19 | 0 | 0% | 0% | delay in approval | 0% |  | Economic Affairs | Lagos State Infrastructure Asset Management Agency
Economic Affairs | Ministry of Transportation | Modern Infrastructure | Improved Level of Driving Culture | Public Road Safety Programme | 130 Zebra Crossing to be Marked |  | 0 Zebra Crossings Marked | 130 | 0 | 110000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Transportation
Economic Affairs | Ministry of Transportation | Modern Infrastructure | Improved Level of Driving Culture | Public Road Safety Programme | 60 Roads Lane to be Marked |  | 0 roads lanemarked | 60 | 0 | 1018907965 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Transportation
Economic Affairs | Ministry of Transportation | Modern Infrastructure | Discipline and Sanity amongst Citizenry | Provision of Traffic Infrastructure | 2 new Intelligent Traffic Signal Lights to be installed |  | 0 intelligent traffic signal lights installed | 2 | 0 | 375382013 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Transportation
Economic Affairs | Ministry of Transportation | Modern Infrastructure | Discipline and Sanity amongst Citizenry | Provision of Traffic Infrastructure | 2 existing junctions to be Upgraded |  | 0 existing junctions Upgraded | 2 | 0 |  | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Transportation
Economic Affairs | Ministry of Transportation | Modern Infrastructure | Reduced Travel Time | Traffic Improvement Scheme | 100% work to be done on Junction Improvement Work (JIW) at Ikorodu |  | 0% work done | 100% | 0% | 338454215 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Transportation
Economic Affairs | Ministry of Transportation | Modern Infrastructure | Reduced Travel Time | Traffic Improvement Scheme | 100% work to be done on Junction Improvement Work (JIW) at Allen/Toyin Round about, Ikeja |  | 0% work done | 100% | 0% | 979454215 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Transportation
Economic Affairs | Ministry of Transportation | Modern Infrastructure | Reduced Travel Time | Traffic Improvement Scheme | 100% work to be done on Junction Improvement Work (JIW) at Ketu segment of Ikorodu Road |  | 0% work done | 100% | 0% | 462437121 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Transportation
Economic Affairs | Ministry of Transportation | Modern Infrastructure | Reduced Travel Time | Traffic Improvement Scheme | 100% Completion of Demarcation of Parking Lots and Provision of Parking Space for People with Disability Within Government Institutions |  | 0% Completion of Demarcation of Parking Lots and Provision of Parking Space for People with Disability Within Government Institutions | 100% | 0% | 178739767 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Transportation
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Equal Justice for all citizens; Controlled and reduced crime rate by way of providing Correctional and Rehabilitation Centers. | Administration of justice | 150 inmates to be released for decongestion of Correctional Service Centres |  | Nil inmate released | 150 | Nil | 10000000 | 0 |  | 0% | Decongestion Program scheduled for 2nd and 3rd Quarter | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Equal Justice for all citizens; Controlled and reduced crime rate by way of providing Correctional and Rehabilitation Centers. | Administration of justice | 1,500 to participate in training and workshop |  | 208 participant | 1,500 | 208 | 300000000 | 52875693 | 13.87% | 17.63% | Participation in Training and Workshop on-going | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Equal Justice for all citizens; Controlled and reduced crime rate by way of providing Correctional and Rehabilitation Centers. | Administration of justice | 800 to participate in conference and seminar |  | 3 participant | 800 | 3 | 240000000 | 42857684 | 0.375% | 17.86% | Participation in Conference and Seminar on-going | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Equal Justice for all citizens; Controlled and reduced crime rate by way of providing Correctional and Rehabilitation Centers. | Administration of justice | 1,500 to participate in legal year ceremony |  | Nil Participant | 1,500 | Nil | 40000000 | 0 |  | 0% | Legal Year program takes effect in 3rd Quarter | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Equal Justice for all citizens; Controlled and reduced crime rate by way of providing Correctional and Rehabilitation Centers. | Administration of justice | 1,100 to participate in the organisation of retreats |  | 318 Participants | 1,100 | 318 | 2000000000 | 56741650 | 28.91% | 2.837% | On-Going | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Equal Justice for all citizens; Controlled and reduced crime rate by way of providing Correctional and Rehabilitation Centers. | Administration of justice | 1,200 Books to be purchased for 63 Hon. Judges, 159 Magistrates, Legal Registrars, Lawyers and Staff. |  | LOTS | 1,200 |  | 50000000 | 7285100 | 0% | 14.57% | On-Going | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Equal Justice for all citizens; Controlled and reduced crime rate by way of providing Correctional and Rehabilitation Centers. | Administration of justice | 200 Cases to be disposed via inquest expenses |  | 12 cases disposed | 200 | 12 | 10000000 | 1180000 | 6% | 11.8% | On-Going | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Equal Justice for all citizens; Controlled and reduced crime rate by way of providing Correctional and Rehabilitation Centers. | Administration of justice | 1,200 family court cases to be disposed |  | 203 Cases disposed | 1,200 | 203 | 10000000 | 1663000 | 16.92% | 16.63% | On-Going | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Warehouses provided for Deputy Sheriff attached goods | Construction of Warehouse, Majidun, Ikorodu | 2 Warehouses to be constructed |  | 1 warehouse constructed | 2 | 1 | 450000000 | 0 | 50% | 0% | 1 warehouse completed last Year. Second warehouse on-going | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Houses provided for Judges | Purchase of 14 Judges' Houses | 18 houses to be purchased. |  | Nil Houses purchased | 18 | Nil | 4770000000 | 0 |  | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Conducive Court Environment for Effective Justice delivery | Renovation of Court facilities | 15 Courts to be renovated |  | Nil Court renovated | 15 | Nil | 521153321.52 | 0 |  | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Befitting official residence for Judicial officers | Construction of Magistrates/Judges Quarters (Epe) (2nd Phase) | 1. Twin Duplexes of 4 Bedrooms to be constructed |  | Nil Twin Duplexes constructed | 1. | Nil | 850682981.25 | 0 |  | 0% | Awaiting Mr. Governors' Approval | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Befitting official residence for Judicial officers | Construction of Magistrates/Judges Quarters (Epe) (2nd Phase) | 8 Unit of 2 Bedroom Flat to be constructed |  | Nil 8 Unit of 2 Bedroom Flat constructed | 8 | Nil |  |  |  |  | Awaiting Mr. Governors' Approval | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Befitting official residence for Judicial officers | Construction of Magistrates/Judges Quarters (Epe) (2nd Phase) | 2 Unit of a Room and Parlour Selfcontain to be constructed |  | Nil 2 Unit of a Room and Parlour Selfcontain constructed | 2 | Nil |  |  |  |  | Awaiting Mr. Governors' Approval | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Befitting official residence for Judicial officers | Construction of Magistrates/Judges Quarters (Epe) (2nd Phase) | 8 Unit of One Bedroom Flat to be constructed |  | Nil 8 Unit of One Bedroom Flat constructed | 8 | Nil |  |  |  |  | Awaiting Mr. Governors' Approval | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Additional Courthouses | Construction of Commercial Court Tapa | 10 Courtrooms to be constructed |  | 6 Coutrooms Constructed | 10 | 6 | 430554851.18 | 0 | 60% | 0% | 6 Courtrooms completed last year. Awaiting Mr. Governors' Approval | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Seamless flow of Works | Procurement of Office Equipment and Furniture | 200 Office equipment and Furnitures to be procured |  | Nil Equipment and Furniture procured | 200 | Nil | 870000000 | 0 |  | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Vehicle provided for the convinient mobility and security of Judgesm Magistrates and Principal officers | Procurement of Vehicles for 10 Hon. Judges | 16 Vehicles to be procured |  | Nil vehicle procured | 16 | Nil | 800000000 | 0 |  | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Vehicle provided for the convinient mobility and security of Judgesm Magistrates and Principal officers | Purchase of Vehicles for 20 Magistrates | 20 Vehicles to be procured |  | Nil vehicle procured | 20 | Nil | 600000000 | 0 |  | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Vehicle provided for the convinient mobility and security of Judgesm Magistrates and Principal officers | Purchase of 10 Vehicles for Principal Officers | 10 Vehicles to be procured |  | Nil vehicle procured | 10 | Nil | 250000000 | 0 |  | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Repository storage of large documents for Lagos State Judiciary. | Installation of Electronic Digital Management System (EDMS) for storage of Court informations. | 63 EDMS to be installed in 63 high courts |  | Nil EDMS insstalled | 63 | Nil | 100000000 | 0 |  | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Repository storage of large documents for Lagos State Judiciary. | Installation of Electronic Digital Management System (EDMS) for storage of Court informations. | 159 EDMS to be installed in 159 magistrate courts |  | Nil EDMS insstalled | 159 | Nil | 100000000 | 0 |  | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Enhanced Revenue generation. | Installation of Software for e-Affidavit Software (Ikeja, Lagos Island, Ikorodu, Epe, Badagry, Eti-osa, Osbourne and Yaba) | 7 registaries to be covered for installation |  | 1registary covered for installation | 7 | 1registary | 10000000 | 0 |  | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Full Automation of Court system. | Judiciary ICT Infrastructure Project | 100% work to be done |  | 0% workdone | 100% | 0% | 1532676000 | 0 | 0% | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | ICT Equipment and Technology provided | Procurement of ICT Equipment | 100% work to be done |  | 0% workdone | 100% | 0% | 150000000 | 0 | 0% | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Secured Court and its environment. | Installation of CCTV Camera to 7 High Courts Divisions and in 7 Magisterial Districts | 100% work to be done |  | 0% workdone | 100% | 0% | 100000000 | 0 | 0% | 0% | Awainting release of funds from STO | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Credible Officers Empowerment, Work/Life Balance Equip with Quality and Quantitative right Legal Skills for proper dispensation of Justice at the grassroots. | Recruitment, Career management, Documentation and Pension administration | 150 Officers (Judges, Magistrate and other Judiciary Staff) to be appointed/employed and verification of educational Certificates of Judiciary staff |  | Nilficers Recruited | 150 | Nilficers | 21891874 | 0 |  | 0% | Awaiting Mr. Governor's and Chief Judge approval on appointment process | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Credible Officers Empowerment, Work/Life Balance Equip with Quality and Quantitative right Legal Skills for proper dispensation of Justice at the grassroots. | Recruitment, Career management, Documentation and Pension administration | 225 Judicial officers (Customary Court President and Members) to be trained |  | Nil Judicial Officers Trained | 225 | Nil | 17750000 | 0 |  | 0% | Commences in 2nd quarter | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Credible Officers Empowerment, Work/Life Balance Equip with Quality and Quantitative right Legal Skills for proper dispensation of Justice at the grassroots. | Recruitment, Career management, Documentation and Pension administration | 28 Magistrates to be promoted |  | Nil Magistrate Promoted | 28 | Nil | 5000000 | 0 |  | 0% | Promotion for Magistrates in progress | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Credible Officers Empowerment, Work/Life Balance Equip with Quality and Quantitative right Legal Skills for proper dispensation of Justice at the grassroots. | Recruitment, Career management, Documentation and Pension administration | 310 Judicial Officers to be promoted |  | 302 Officers Promoted | 310 | 302 | 6400000 | 6400000 | 97.42% | 100% | 8 officers couldn’t meet the requirement of the promotion exercise | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Credible Officers Empowerment, Work/Life Balance Equip with Quality and Quantitative right Legal Skills for proper dispensation of Justice at the grassroots. | Recruitment, Career management, Documentation and Pension administration | 104 Officers to be trained |  | 38 Officer Trained | 104 | 38 | 127061845 | 39932315 | 36.54% | 31.43% | Officer to attend workshop in batches | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Credible Officers Empowerment, Work/Life Balance Equip with Quality and Quantitative right Legal Skills for proper dispensation of Justice at the grassroots. | Recruitment, Career management, Documentation and Pension administration | 29 Officers to participate in Conference and Seminar |  | 39 Officer Participated | 29 | 39 | 30100000 | 0 | 100% | 0% | Confefrence commences in 2nd Quarter | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Data management developed and official information protected | Information Technology Database Development | 100% work done on Information system installation |  | Nil workdone | 100% | Nil | 67015261 | 0 |  | 0% | Pending approval in Ministry of Economic Planning and Budget | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Conducive working Environment for Effective Service Delivery | Refurbishment of Office Building (Installation, Painting, Electrical & Plumbing) | 100% work to be done |  | Nil workdone | 100% | Nil | 18000000 | 0 |  | 0% | Pending approval in Ministry of Economic Planning and Budget | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Seamless flow of Works | Procurement of Furniture and Office Equipment | 100 Furnitures to be procured |  | Nil Furnitures procured | 100 | Nil | 13500000 | 0 |  | 0% | Pending approval in Ministry of Economic Planning and Budget | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Vehicles available to facilitate and cover the scope of the Magistrate & Customary Court in all IBILE Divisions in Lagos State | Procurement of Operational Vehicles | 2 Operational Vehicle and Qlink Motorcycle to be procured |  | Nil Operational Vehicle and Qlink Motorcycle procured | 2 | Nil | 19979989 | 0 |  | 0% | Pending approval in Ministry of Economic Planning and Budget | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Decongested Court's docket and Awereness of dispute resolution as a supplement to litigation | Alternative Dispute Resolution (ADR) | Special programmes (Lagos Settlement Week (LSW) |  | Nil cases disposed | Special | Nil | 5000000 | 0 |  | 0% | Pending approval in Ministry of Economic Planning and Budget |  |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Decongested Court's docket and Awereness of dispute resolution as a supplement to litigation | Alternative Dispute Resolution (ADR) | disposed via Netural Remuneration |  | Nil cases disposed | disposed | Nil | 5000000 | 0 |  | 0% | Pending approval in Ministry of Economic Planning and Budget |  |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Decongested Court's docket and Awereness of dispute resolution as a supplement to litigation | Alternative Dispute Resolution (ADR) | to be Cerfitied at Alternative Dispute Resolution (ADR) Workshop & Training |  | Nil Mdiator Cerfitied | to | Nil | 3000000 | 0 |  | 0% | Pending approval in Ministry of Economic Planning and Budget |  |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Seamless flow of Works | Procurement of Furniture | 7 Furniture to be procured |  | Nil Furniture procured | 7 | Nil | 5039660 | 0 |  | 0% | Pending approval in Ministry of Economic Planning and Budget | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Seamless flow of Works | Procurement of Office Equipment | 49 Equipment to be procured |  | Nil Equipment procured | 49 | Nil | 20020000 | 0 |  | 0% | Pending approval in Ministry of Economic Planning and Budget | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Seamless flow of Works | Management Information System | 100% work to be done on Management Information System |  | Nil workdone | 100% | Nil | 24524000 | 0 |  | 0% | Pending approval in Ministry of Economic Planning and Budget | 0% |  | Public Order and Safety | Lagos State Judiciary
Public Order and Safety | Lagos State Judiciary | Human-Centric City | Provision of vehicle for the convinient mobility and security of Principal officers | Procurement of Vehicle | 1 Operational Vehicle to be procured |  | Nil Operational Vehicle procured | 1 | Nil | 45992050 | 0 |  | 0% | Pending approval in Ministry of Economic Planning and Budget | 0% |  | Public Order and Safety | Lagos State Judiciary
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Gberigbe Road (Ewu-Elepe - Gbodu Junction - Gberigbe Town) in Ikorodu LGA (2022) | 99% work to be done |  | 15% work done | 99% | 15% | 171412118.31 |  | 15.15% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Femi Okunnu Road in Ikoyi ,Eti- Osa LGA. (2021) | 99% work to be done |  | 90% work done | 99% | 90% | 80127116.85 |  | 90.91% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Oyinkan Abayomi Drive, Ikoyi ,Eti-Osa LGA. (2021) | 85% work to be done |  | 50% work done | 85% | 50% | 88897566.91 |  | 58.82% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Macpherson Avenue, Ikoyi, in Eti- Osa LGA. (2021) | 87% work to be done |  | 42% work done | 87% | 42% | 24883171.25 |  | 48.28% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Opebi-Mende Link Bridge and Approach Roads in Ikeja LGA (2021) | 90% work to be done |  | 50% work done | 90% | 50% | 5615209018 |  | 55.56% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Alternative Route to Admirality Circle Toll Plaza Lekki (2020) | 100% work to be done |  | 75% work done | 100% | 75% | 24105852.86 |  | 75% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of St Finbarrs Road in Kosofe LGA (Abule Okuta - Soluyi Deeperlife Church) (2020) | 100% work to be done |  | 95% work done | 100% | 95% | 5620371.35 |  | 95% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Church Street in Kosofe LGA (2020) | 100% work to be done |  | 67% work done | 100% | 67% | 10773383.11 |  | 67% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Demurin Road in Kosofe LGA (2020) | 100% work to be done |  | 65% work done | 100% | 65% | 27922302.14 |  | 65% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Agidi Road in Kosofe LGA (2020) | 78% work to be done |  | 70% work done | 78% | 70% | 9900398.36 |  | 89.74% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of St Finbarrs Road in Kosofe LGA (UNILAG Gate - Abule Okuta/Bariga Market) (2020) | 100% work to be done |  | 68% work done | 100% | 68% | 34520074.91 |  | 68% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation/Upgrading of Strategic arterial/inner roads (Phase II) in Epe LGA (2017) | 100% work to be done |  | 95% work done | 100% | 95% | 14015518.11 |  | 95% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation/Upgrading of Mumuni Adio(Buba Marwa) (2021) | 93% work to be done |  | 67% work done | 93% | 67% | 56071245.09 |  | 72.04% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation/Upgrading of Eti-Osa/Lekki/Epe Expressway PhaseII A(Eleko Junction Through Awoyaya to Greensprings, Majek and Ogidan Axis. (2022) | 85% work to be done |  | 75% work done | 85% | 75% | 631331095.15 |  | 88.24% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation/ Re-Construction/Upgrade of Eti - Osa/ Lekki/ Epe Exp.way(Phase IIB) From Greenspring to Abraham Adesanya in Eti-Osa and Ibeju-Lekki Local Government Area. | 89% work to be done |  | 28% work done | 89% | 28% | 4125570552.09 |  | 31.46% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Omu Creek and Bridges ( Phase 1) in Ibeju-Lekki | 100% work to be done |  | 0% work done | 100% | 0% | 9750000000 |  | 0% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction Of 4-Legged-Pedestrian Bridges ..... - Construction of Pedestrian Link Bridge to Otto Community (Phase 2) (2022) | 100% work to be done |  | 1% work done | 100% | 1% | 9885477.49 |  | 1% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Oba Dosunmu, Ikeja GRA (2020) | 100% work to be done |  | 92% work done | 100% | 92% | 7458751.64 |  | 92% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Oduduwa Way and Oduduwa Crescent, Ikeja LGA (2020) | 99% work to be done |  | 72% work done | 99% | 72% | 47247100.56 |  | 72.73% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Reconstruction/Upgrading of Sobo Arobiodu Street, Ikeja GRA, Ikeja LGA (2020) | 100% work to be done |  | 46% work done | 100% | 46% | 41522379.17 |  | 46% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Reconstruction of Lagos Badagry Carriageway (LOT 2A) Segment 3 (2014 & 2021) | 98% work to be done |  | 89% work done | 98% | 89% | 3177165541 |  | 90.82% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Aradagun-Mosafejo-Idudo- Imeke Road in Badagry LGA Phase III (2020) | 95% work to be done |  | 94% work done | 95% | 94% | 78984281.62 |  | 98.95% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Reconstruction of Old Ojo Road (Phase 1) from Irede to Oluti in Amuwo Odofin LGA (2022) | 97% work to be done |  | 55% work done | 97% | 55% | 228734949.85 |  | 56.7% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Babafemi Dada with bridge - Yinka Folarin - Jamiu Lawal - Shalom Academy Road Network, Alimisho LGA (2021) | 92% work to be done |  | 77% work done | 92% | 77% | 100037894.16 |  | 83.7% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Completion of Agric-Isawo-Konu-Arepo (Phase 1B), Upgrade of Ogolonto and Aruna Junctions and Sectional Rehabilitation of Ikorodu Road in Local Government Area (2023) | 97% work to be done |  | 0% work done | 97% | 0% | 160349616.66 |  | 0% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Akesan Igando Road (Dual Carriage way). (2022) | 92% work to be done |  | 22% work done | 92% | 22% | 62107509.59 |  | 23.91% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Replacement of Contract Award for the Construction of Ijegun- Ijeododo Road with Construction of Ijegun-Ijagemo Road in Alimosho L.G.A. (2022) | 95% work to be done |  | 20% work done | 95% | 20% | 140749554.76 |  | 21.05% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Arowojobe Link Bridge and Approach Road at Mende Maryland in Kosofe LGA (2018) | 100% work to be done |  | 77% work done | 100% | 77% | 22257648.9 |  | 77% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Lekki Regional Roads, VGC to Freedom Way, Eti- osa LGA (2020) | 95% work to be done |  | 31% work done | 95% | 31% | 3525462972 |  | 32.63% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation/Upgrade of Igbogbo-Bola Ahmed Tinubu-Igbe Road, Ikorodu LGA (2017) | 99% work to be done |  | 40% work done | 99% | 40% | 1158881996 |  | 40.4% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Reconstruction/Rehabilitation of Agric Isawo- Konu-Arepo Road (Phase I), Ikorodu LGA (2017) | 99% work to be done |  | 70% work done | 99% | 70% | 1957192845 |  | 70.71% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Reconstruction/Upgrading of Oshodi-Muritala Muhammed International Airport (MMIA) Road (2017) | 100% work to be done |  | 83% work done | 100% | 83% | 274783429 |  | 83% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Reconstruction/Upgrading of Oshodi-Muritala Muhammed International Airport (MMIA) Road (Additional Works) (2019) | 100% work to be done |  | 78% work done | 100% | 78% |  |  | 78% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Re-Construction & Dualisation of Irede Road in Amuwo Odofin LGA (2017) | 100% work to be done |  | 86% work done | 100% | 86% |  |  | 86% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Aka/Kemberi road in Ojo LGA (2022) | 98% work to be done |  | 68% work done | 98% | 68% | 53433568.19 |  | 69.39% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Oshinlemo Street, Adaloko in Ojo Local Governement Area (2022) | 93% work to be done |  | 36% work done | 93% | 36% | 27594632.19 |  | 38.71% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Fadaini- Obale road in Apapa | 100% work to be done |  | 50% work done | 100% | 50% | 44131690.16 |  | 50% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Oko Afo-Ilogbo Eremi-Pota Road in Badagry Local Government Area (2022) | 81% work to be done |  | 5% work done | 81% | 5% | 353403427.7 |  | 6.173% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Prosposed Rehabilitation/Upgrading of Ademoye/Alake Lakonko in Alimosho LGA (2021) | 100% work to be done |  | 90% work done | 100% | 90% | 8381255.14 |  | 90% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Constituency Roads (14Roads) within the State (Phase IV) and Olu of Agege's Palace in Agege LGA (2021) | 100% work to be done |  | 81% work done | 100% | 81% | 25000000000 |  | 81% |  | SIIF | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Constituency Roads (Phase VI) located in Agege, Ajeromi-Ifelodun, Alimosho, Ifako-Ijaiye, Ikeja, Kosofe, Lagos Mainland, Mushin, Oshodi-Isolo and Surulere Local Government Area | 60% work to be done |  | #VALUE! | 60% |  |  |  | 0% |  | SIIF | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Constituency Roads (Phase V) within the State in Ifelodun LGA (1 Road).Badagry LGA (1 Road),Ikeja LGA (1 Road),Kosofe LGA (2 Roads),Mushin LGA (1 Road),Ojo LGA (1 Road)and Surulere LGA (1 Road)( Lot 2) (2022) | 90% work to be done |  | 26% work done | 90% | 26% | 20000000000 | 16482052228.39 | 28.89% | 82.41% | SIIF | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Constituency Roads (Phase V) within the State in Epe LGA (4 Roads) and Eti- Osa LGA (5 Roads)(Lot 3) (2022) | 96% work to be done |  | 19% work done | 96% | 19% |  |  | 19.79% |  | SIIF | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Ile-Eja, Ola-Iya/Ajibola Hassan- Alh Mustapha- Olu Adeyanju with Bridge-Rabiatu Ogedengbe Road Network in Alimosho LGA (2022) | 97% work to be done |  | 29% work done | 97% | 29% | 133371463.46 |  | 29.9% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Agric Access Road (Bamidele kasali/Dosu Ekunrin Road) Egan Road Section (Phase IIa) and Ayobo Road Section (Phase IIB) (2018) | 100% work to be done |  | 67% work done | 100% | 67% | 9121986.92 |  | 67% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Proposed Church Access Road Off 3rd Relief/Resettlement Camp Access Road in Ibeju-Lekki L.G.A (2021) | 100% work to be done |  | 44% work done | 100% | 44% | 1917296.35 |  | 44% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Isiba Oluwo (Phase II) in Alimosho L.G.A (2020) | 100% work to be done |  | 51% work done | 100% | 51% | 4481081.42 |  | 51% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation/Upgrading of Happy Home-Alahun Ozumba Link Road (2018) | 100% work to be done |  | 95% work done | 100% | 95% | 223282296 |  | 95% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation/Upgrading of Ifebajo Streets (2017) | 100% work to be done |  | 90% work done | 100% | 90% |  |  | 90% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation/Upgrading of Mobolaji Johnson(First Avenue /Bank Road Ikoyi) (2018) | 100% work to be done |  | 95% work done | 100% | 95% | 4308658.28 |  | 95% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Platinum road, off Lekki Expressway, Igbekosu. (2020) | 100% work to be done |  | 85% work done | 100% | 85% | 4404572.34 |  | 85% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Abeje Street in Ajeromi Ifelodun LGA (2021) | 93% work to be done |  | 71% work done | 93% | 71% | 3803939.53 |  | 76.34% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Remi Oyefiade Street in Eti-Osa L.G.A (2018) | 100% work to be done |  | 52% work done | 100% | 52% | 9302620.87 |  | 52% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Adeyemi Thomas Street Agbowa- Ikosi L.C.D.A (2018) | 100% work to be done |  | 98% work done | 100% | 98% | 905328.58 |  | 98% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Navy Town(Section 1) Road in Amuwo Odofin LGA (2021) | 100% work to be done |  | 62% work done | 100% | 62% | 10890132.89 |  | 62% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Samuel Ekundayo/Toga road in Badagry L.G.A (2018) | 92% work to be done |  | 84% work done | 92% | 84% | 71417812.71 |  | 91.3% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Reconstruction of Hospital Road, Badagry (Phase 1) (2021) | 81% work to be done |  | 65% work done | 81% | 65% |  |  | 80.25% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Completion of Samuel Ekundayo Road in Badagry LGA (Phase III) (2022) | 89% work to be done |  | 44% work done | 89% | 44% | 88729295.79 |  | 49.44% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Lagos bus reform project: development of depot at Oshodi Anthony and Yaba (2017) | 100% work to be done |  | 94% work done | 100% | 94% | 7561948.91 |  | 94% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Lagos bus reform project: development of depot at Anthony (2017) | 100% work to be done |  | 63% work done | 100% | 63% | 8197871.2 |  | 63% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Jamiu Eletu Road and Eletu Road Outfall in Ibeju-Lekki L.G.A (2014) | 94% work to be done |  | 64% work done | 94% | 64% | 19295199.3 |  | 68.09% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Identified Strategic Roads across the State in Alimosho L.G.A. (2 Roads), Ikeja L.G.A. (3 Roads), Ifako-Ijaiye L.G.A. (6 Roads) and Kosofe L.G.A. (4 Roads) (Lot 3) (2023) | 99% work to be done |  | 4% work done | 99% | 4% | 386444331.54 |  | 4.04% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Adamo-Akanun- Agunfoye Lugbusi Roads in Ikorodu LGA. (2022) | 92% work to be done |  | 66% work done | 92% | 66% | 54603126.67 |  | 71.74% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Saka Orotan/Ilufe/Olufemi Adenigba/Alhaji Okin Road in Ojo Local Government Area (2022) | 100% work to be done |  | 2% work done | 100% | 2% | 104178414.36 |  | 2% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Rilwan Onifade/Osidele street Ikotun in Alimosho LGA. (2022) | 100% work to be done |  | 95% work done | 100% | 95% | 5350698.05 |  | 95% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Constituency Roads (Phase V) within the State in Agege LGA (17 Roads).Alimosho LGA (1 Road),and ifako Ijaiye LGA (1 Road) Lot 1 (2022) | 91% work to be done |  | 49% work done | 91% | 49% | 499382242.49 |  | 53.85% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Identified Strategic Roads across the State in Agege L.G.A. (6 Roads), Ajeromi- Ifelodun L.G.A. (1 Roads), Ojo L. G.A. (2 Roads) and Badagry L.G.A. (1 Roads) (Lot 2) (2023) | 94% work to be done |  | 3% work done | 94% | 3% | 355767335.79 |  | 3.191% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Completion of Surveyor Yakubu /Balogun Ola Str eets network of roads in Epe LGA. (2022) | 90% work to be done |  | 41% work done | 90% | 41% | 34018070.38 |  | 45.56% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Identified Strategic Roads across the State in Agege L.G.A. (19 Roads) (Lot 1) (2023) | 96% work to be done |  | 8% work done | 96% | 8% | 499382242.49 |  | 8.333% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Ogombo Sangotedo Road in Eti- Osa LGA. ( Review of Contract Price) (2022) | 98% work to be done |  | 59% work done | 98% | 59% | 25178832.82 |  | 60.2% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitattion of Moshalashi Street in Somolu LGA (2021) | 99% work to be done |  | 45% work done | 99% | 45% | 8975878.94 |  | 45.45% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Sand Zero Road, Oyingbo in Lagos Mainland LGA (2022) | 80% work to be done |  | 65% work done | 80% | 65% | 4698090.82 |  | 81.25% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation of Amoo/Adalemo Street, in Agege LGA (2022) | 85% work to be done |  | 45% work done | 85% | 45% | 20788956.36 |  | 52.94% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Johnson Umejei Close, Ajao Estate. (2014) | 100% work to be done |  | 92% work done | 100% | 92% | 4625529.06 |  | 92% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Reinforced Concrete Foot Bridge at Okunudun/Erekun Communities in Ojo LGA (2016) | 100% work to be done |  | 93% work done | 100% | 93% | 770382.32 |  | 93% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Reinforced Concrete Foot Bridge at Irewe/Itogbesa Communities in Ojo LGA (2016) | 100% work to be done |  | 67% work done | 100% | 67% | 900949.81 |  | 67% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Adewunmi/Imafidon Crescent, Oko-Oba, G.R.A Scheme (2017) | 98% work to be done |  | 65% work done | 98% | 65% | 4187670.18 |  | 66.33% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Magbon-Alade Township roads, Ibeju-Lekki (2021) | 100% work to be done |  | 52% work done | 100% | 52% | 16752986.09 |  | 52% |  | HANDED OVER TO PWC | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Abiola Onijemo Link Road with Bridge in Ifako Ijaiye LGA (2022) | 93% work to be done |  | 60% work done | 93% | 60% | 121507796.43 |  | 64.52% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Rehabilitation / Upgrading of Ilabere, Ilu and Inupa Roads in Ikoyi, Eti-Osa Local Government Area | 65% work to be done |  | 5% work done | 65% | 5% | 43349350.69 |  | 7.692% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Reconstruction and Upgrading of Oke Popo/Tapa street in Lagos Island LGA | 100% work to be done |  | 55% work done | 100% | 55% | 53329141.15 | 1398988299.43 | 55% | 100% |  | 0% |  | Economic Affairs | Office of Infrastructure
Economic Affairs | Office of Infrastructure | Modern Infrastructure | Reduced travel time,enhanced property values and socio-economic activities and improve road connectivity. | Construction of Lagos Badagry Expressway SEGMENT 2 | 98% work to be done |  | 91% work done | 98% | 91% | 3914070862 |  | 92.86% |  |  | 0% |  | Economic Affairs | Office of Infrastructure
Housing and Community Amenities | Lands Bureau | Thriving Economy | Reduced bureaucracy of C of O process | Digilization Process (Automation of Process) | 60% of e-Processing of Certificate of Occupancy to be Digitized (100 C of O Proposed per year) | 0 | 35% of e-Processing of Certificate of Occupancy Digitized (100 C of O Proposed per year) | 60% | 35% | 550455809 | 75000000 | 58.33% | 13.63% | On going | 0% |  | Housing and Community Amenities | Lands Bureau
Housing and Community Amenities | Lands Bureau | Thriving Economy | Reduced bureaucracy of C of O process | Digilization Process (Automation of Process) | 50% Transaction to be Digitalized | 0 | 40% Transaction Digitalized | 50% | 40% | 0 | 0 | 80% |  |  | 0% |  | Housing and Community Amenities | Lands Bureau
Housing and Community Amenities | Lands Bureau | Thriving Economy | Efficient and Effective Land Transaction | Perimeter Fencing and Giant Sign Post | 100% Work to be done on Perimeter Fencing | 0 | 65% Work done on Perimeter Fencing | 100% | 65% | 179573728.46 | 71829491.38 | 65% | 40% | On going | 0% |  | Housing and Community Amenities | Lands Bureau
Housing and Community Amenities | Lands Bureau | Thriving Economy | Efficient and Effective Land Transaction | Erection of Giant Sign Post | 100% Erection work to be done on Giant Sign Post | 0 | 70% Erection work done on Giant Sign Post | 100% | 70% | 30000000 | 21000000 | 70% | 70% |  | 0% |  | Housing and Community Amenities | Lands Bureau
Housing and Community Amenities | Lands Bureau | Thriving Economy | Improved availability of Lands for Public Purposes | Compesation for Acquired Land | 40% Compesation to be paid on Acquired Lands | 0 | 20% Compesation paid on Acquired Lands | 40% | 20% | 3835249137 | 600000000 | 50% | 15.64% |  | 0% |  | Housing and Community Amenities | Lands Bureau
Housing and Community Amenities | Lands Bureau | Thriving Economy | Improved availability of Lands for Public Purposes | Compesation for Lekki Foreshore and Refund on other Scheme | 80% Compesation to be paid for Lekki Foreshore and other Schemes | 0 | 0% Compesation paid for Lekki Foreshore and other Schemes | 80% | 0% | 5689025 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Lands Bureau
Housing and Community Amenities | Lands Bureau | Thriving Economy | Improved availability of Lands for Public Purposes | Acquisition of Lands (Around Train Station) | 100 Lands around Trains Stations to be Acquired | 0 | 0 no of Lands around Trains Stations Acquired | 100 | 0 | 1936967333 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Lands Bureau
General Public Services | Public Service Office | Human-Centric City | Improved Staff Welfare | Pens Down Ceremony for Permanent Secretaries | 11 Retired Permanent Secretaries to receive Cash Gift | 0 | 0 No of Retired Permanent Secretaries receive Cash Gift | 11 | 0 | 100000000 | 0 | 0% | 0% | Yet to Commence(Most of the Programmes are end of the Year Events) | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Improved Staff Welfare | Long Service Awaard Celebration | 1500 Retired Officers scheduled for PMB (Exit) | 0 | 0 No of Retired Officers scheduled for PMB (Exit) | 1500 | 0 | 30000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Improved Staff Welfare | Retirees Matters | 750 Retiress Officers in Public Service to receive Gift | 0 | 0 no of Retiress Officers in Public Service receive Gift | 750 | 0 | 35000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Improved Staff Welfare | Last Day in Office Ceremony(State Wide) | 100 Branded Centre Rugs to be presented to Retiress Officers | 0 | 0 no of Branded Centre Rugs presented to Retiress Officers | 100 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Well Equiped and Informed Management Staff | Retreat for Administarators & Directors (A&HR) Statewide | 189 Admistrators and Directors (A&HR) Statewide to be in attendance for Administrator & Directors Retreat | 0 | 0 no of Admistrators and Directors (A&HR) Statewide in attendance for Administrator & Directors Retreat | 189 | 0 | 50000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Well Equiped and Informed Management Staff | Retreat for Management Staff | 80 Management Staff to be in attendance at the Management Retreat | 0 | 0 no of Management Staff in attendance at the Management Retreat | 80 | 0 | 25000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Improved Effective Service Delivery | ALARHOSPS | 1 no of Annual meeting to be held for Association of Retired Lagos State Heads of Service and Permanent Secretaries | 0 | 0 no of Annual meeting held for Association of Retired Lagos State Heads of Service and Permanent Secretaries | 1 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Improved Skills of I.T & SIWESS Students | Research & Development | 1 no of Day Sensitization and Orientation Programmes to be done for IT and SIWESS Students | 0 | 0 no of Day Sensitization and Orientation Programmes done for IT and SIWESS Students | 1 | 0 | 3000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Encouraged spirit of Sportmanship and Camaraderie amongst Staff | Federation of Public Service Games | 94 MDAs and Parastaltals to participate in Federation of Public Service Games (HoS Games) | 0 | 0 no of MDAs and Parastaltals participate in Federation of Public Service Games (HoS Games) | 94 | 0 | 40000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Well Informed Staff | Publication & Documentation | 10000 Hands Books to be Published on Retired Hos & Permanent Secretaries | 0 | 0 no of Hands Books Published on Retired Hos & Permanent Secretaries | 10000 | 0 | 4000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Reduced Financial Embarrasment of Staff | Car Refurbishment Loan | 85% of Staff to be benefitted from Car Refurbishment Loan | 0 | 0% of Staff benefitted from Car Refurbishment Loan | 85% | 0% | 1000000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Improved Living Condition of Staff | Rehabilitation of Staff Quarters | 55 no of Flats in Staff Quarter to be renovated | 0 | 0 no of Flats renovated , Upgraded | 55 | 0 | 130000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Improved Staff Welfare | Re-Construction of New Staff Canteen, Office | 100% completion of Staff Canteen, Office to be done | 0 | 0% completion of Staff Canteen, Office done | 100% | 0% | 1000000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Improved conducive working Environment | Renovation/ Upgrading and supply of Equipment for Adeyemi Bero Auditorium | 100% Completion of Upgrading/ Renovation and supply of Equipment to Adeyemi Bero Auditorium to be done | 0 | 0% Completion of Upgrading/ Renovation and supply of Equipment to Adeyemi Bero Auditorium to be done | 100% | 0% | 100000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Improved Staff Welfare | Refurbishment/ Repair of Plant, Vehicles and Machines | 100% of Refurbishment /repair of Heavy Plant/Vehicle and Machine to procured | 0 | 20% of Refurbishment /repair of Heavy Plant/Vehicle and Machine to procured | 100% | 20% | 60000000 | 10000000 | 20% | 16.67% |  | 0% |  | General Public Services | Public Service Office
General Public Services | Public Service Office | Human-Centric City | Reduction in financial embarrassment of staff | Rehabilitation of facilities & other special equipment (staff housing loan) | 100% Rehabilitation of facilities & other special equipment (staff housing loan) to be achieved |  | 0% Rehabilitation of facilities & other special equipment (staff housing loan) | 100% | 0% | 1000000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Service Office
Housing and Community Amenities | Office of the State Surveyor General | Modern Infrastructure | Improved Productivity and Effective Service Delivery | Infrastructural Upgrade of Zonal Offices | 10 Zonal Offices to be provided with Operational working tools | 0 | 0 no of Zonal Offices provided with Operational working tools | 10 | 0 | 62000000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Office of the State Surveyor General
Housing and Community Amenities | Office of the State Surveyor General | Modern Infrastructure | Enhanced the creation of pool Asset for Valuation purpose | Public Institution Survey | 36 Public Institution to be Surveyed | 0 | 0 no of Public Institution Surveyed | 36 | 0 | 93000000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Office of the State Surveyor General
Housing and Community Amenities | Office of the State Surveyor General | Modern Infrastructure | Improved Productivity and Effective Service Delivery | Survey and other Specialized Operational Equipment | 10 specialized Operational Equipment to be procured | 0 | 0 no of specialized Operational Equipment procured | 10 | 0 | 30000000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Office of the State Surveyor General
Housing and Community Amenities | Office of the State Surveyor General | Modern Infrastructure | Enhanced Geospatial Information Project Management | Geospatial Information Management Project | 50 survey Map to be produced | 0 | 0 no of survey Map produced | 50 | 0 | 49000000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Office of the State Surveyor General
Housing and Community Amenities | Office of the State Surveyor General | Modern Infrastructure | Improved Productivity and Effective Service Delivery | Purchase of Computer Hardware | 4 System Hardware to be purchased | 0 | 0 no of System Hardware purchased | 4 | 0 | 0 | 0 | 0% |  |  | 0% |  | Housing and Community Amenities | Office of the State Surveyor General
Housing and Community Amenities | Office of the State Surveyor General | Modern Infrastructure | Improved Effective Service Delivery | Purchase of Office Equipment and Furniture | 6 offices to be supplied with Office Equipment | 0 | 0 no of offices supplied with Office Equipment | 6 | 0 | 14755086 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Office of the State Surveyor General
Housing and Community Amenities | Office of the State Surveyor General | Modern Infrastructure | Improved Effective Service Delivery | Purchase of Office Equipment and Furniture | 3 Offices to be Furnished |  | 0 no of Offices Furnished | 3 | 0 | 15605000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Office of the State Surveyor General
Economic Affairs | Public Works Corporation | Modern Infrastructure | Improved free flow of Traffic anf Travel Time | Drainage Maintenance | 80 drainages to be maintained | 0 | 27 no of drainages maintained | 80 | 27 | 2005610651 | 143758254.62 | 33.75% | 7.168% |  | 0% |  | Economic Affairs | Public Works Corporation
Economic Affairs | Public Works Corporation | Modern Infrastructure | Improved free flow of Traffic anf Travel Time | Maintenance/ Servicing of Equipment | 220 Maintenance / Servicing of of Equipment to be done | 0 | 68 no of Maintenance / Servicing of Equipment done | 220 | 68 | 266867698 | 58240912.5 | 30.91% | 21.82% |  | 0% |  | Economic Affairs | Public Works Corporation
Economic Affairs | Public Works Corporation | Modern Infrastructure | Improved free flow of Traffic anf Travel Time | Procurement and Refurbishing of Plant and Heavy Equipment | 280 Plant and heavy Equipment to be Purchased | 0 | 82 no of Plant and heavy Equipment Purchased | 280 | 82 | 939534375 | 267095558 | 29.29% | 28.43% |  | 0% |  | Economic Affairs | Public Works Corporation
Economic Affairs | Public Works Corporation | Modern Infrastructure | Improved free flow of Traffic anf Travel Time | Construction/ Rehabilitation of Drainages | 80 Drainages to be Constructed, Rehabilitated | 0 | 0 no of Drainages Constructed, Rehabilitated | 80 | 0 | 857463750 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Public Works Corporation
Economic Affairs | Public Works Corporation | Modern Infrastructure | Improved free flow of Traffic anf Travel Time | Rehabilitation of Roads | 550 Roads to be Rehabilitated | 0 | 145 Roads to be Rehabilitated | 550 | 145 | 14690271619 | 1913616366.6 | 26.36% | 13.03% |  | 0% |  | Economic Affairs | Public Works Corporation
Social Protection | Office of Civic Engagement | Human-Centric City | Improved Good Governance (Improved harmonious relationship between Executive & Legislative) | Executive, Legislative & Political Submit | 2 no of Executive, Legislative & Political Submit to be Organised | 0 | 1 no of Executive, Legislative & Political Submit Organised | 2 | 1 | 335000000 | 254400000 | 50% | 75.94% |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Improved Good Governance(Improved harmonious relationship between Executive & Legislative) | Executive, Legislative & Political Submit | 8 no of Executive Bills expected to be passed | 0 | 1 no of Executive Bills passed | 8 | 1 | 0 | 254400000 | 12.5% |  |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Improved Good Governance (Improved harmonious relationship between Executive & Legislative) | Executive, Legislative & Political Submit | 15 no of Resolution to be reached | 0 | 13 no of Resolution reached | 15 | 13 | 0 | 254400000 | 86.67% |  |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Improved Good Governance (Improved harmonious relationship between Executive & Legislative) | Executive, Legislative & Political Submit | 15 no of Resolution to be implemented | 0 | Nil | 15 |  | 0 |  | 0% |  |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Reduced Maternal Maternity rate | Womb to School | 1140 no of Beneficiaries expected | 0 | 0 no of Beneficiaries reached | 1140 | 0 | 200000000 | 1750000 | 0% | 0.875% |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Enhanced violent- free political environment/society | Political Engagement | 40 no of Political engagements expected to be organised | 0 | 0 no of Political engagements organised | 40 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Equipped citizens on government activities | Constituency Outreach Programme (Town Hall Meetings) | 10 no of outreaches(Town Hall meetings) to be held | 0 | 5 no of outreaches(Town Hall meetings) held | 10 | 5 | 40000000 | 9998500 | 50% | 25% |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Improved peaceful co-existence among citizens | Hosting of dispute management and resolution meetings | 40 no of dispute and resolution meetings to be hosted | 0 | 2 no of dispute and resolution meetings hosted | 40 | 2 | 6000000 | 9998500 | 5% | 100% |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Improved standard of living | Financial Assistance:(Financial supports for indigent/vulnerable Lagosians) | 4,000 no of application to be received for financial assistance | 0 | 756 no of application received for financial assistance | 4,000 | 756 | 700000000 | 21450000 | 18.9% | 3.064% |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Improved citizens’ consciousness on Legislative matters | Printing of translated and simplified version of the state Laws; | 2 no of state Laws expected to be simplified and translated | 0 | 0 no of state Laws simplified and translated | 2 | 0 | 8000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Improved citizens’ consciousness on Legislative matters | Printing of translated and simplified version of the state Laws; | 100,000 copies of state laws simplified and translated expected to be printed | 0 | 0 no of copies of state laws simplified and translated printed | 100,000 | 0 | 8000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Increased level of well-informed/compliant citizens on the State Laws; | Sensitization and advocacy awareness of passed Laws and Quarterly Observation Legislative process and procedures. | 4 no of Legislative procedures and process expected to be observed | 0 | 0 no of Legislative procedures and process observed | 4 | 0 | 45000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City |  | Sensitization and advocacy awareness of passed Laws and Quarterly Observation Legislative process and procedures. | 5 no of Passed law to be sensitized | 0 | 1 no of Passed law sensitized | 5 | 1 | 0 |  | 20% |  |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Improved Inclusive governance and service delivery | Citizensgate App. Operations | 3000 no of citizens complaints/Request to be received through the App. Operations | 0 | 124 no of citizens complaints/Reques received through the App. Operations | 3000 | 124 | 150000000 | 7700000 | 4.133% | 5.133% | (The citizens complaints/ Request resolved does not involve money as it was through existing app)Awaiting for the release of fund from STO | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Improved Inclusive governance and service delivery | Citizensgate App. Operations | 3000 no of citizens complaints/Request to be resolved through the App. Operations | 0 | 12 no of citizens complaints/Request resolved through the App. Operations | 3000 | 12 | 0 |  | 0.4% |  |  | 0% |  | General Public Services | Office of Civic Engagement
Social Protection | Office of Civic Engagement | Human-Centric City | Improved standard of living of the vulnerables | Civic Week | 1 Civic Week to be organized |  | 0 no of Civic week organized | 1 | 0 | 50000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Office of Civic Engagement
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City |  | Lagos State Cash Transfer Unit (LSCTU) | (cash token) to be paid Bi-Monthly. | 0 | 0 Beneficiaries (cash token) to be paid Bi-Monthly |  | 0 | 137499280 | 0 |  | 0% |  |  |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | Equipment Support for Upskilled Artisans. | Emloyability skill Development for Youth | 1200 Artisans / Tradesmen tobe trained / upskilled | 0 | 0 Artisans / Tradesmen tobe trained / upskilled | 1200 | 0 | 67700000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City |  | Number of Artisans supported with professional equipment. | 1200 Artisans/ Tradesmen to be equipped | 0 | 0 Artisans/ Tradesmen to be equipped | 1200 | 0 | 180000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | Reduced unemployment | Graduate Internship Placement Programme | 2000 Post- NYSC gradutes for placements as interns with different organisations. | 0 | 0 NYSC gradutes as interns with different organisations. | 2000 | 0 | 1100000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | A functional Online marketplace for secured transaction and improved Artisans service delivery. | Virtual Market/ Database Portal | 1 functional database portal | 0 | 0 functional database portal | 1 | 0 | 89344121 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | i. Reduced unemployment | Organisation of Job Fair | 100% Numbers of job seekers connected to intending/ would be employers. | 0 | 0 Numbers of job seekers connected to intending/ would be employers. | 100% | 0 | 34250400 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | Encouraged collaborations for entrepreneurial and employability projects for the benefit of the citizens | Corporate Lagos Expenses | 95% of the participants and number of Partners/ Organizations engaged for collaborations. | 0 | 0% of the participants and number of Partners/ Organizations engaged for collaborations. | 95% | 0% | 20000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | More than 50% of beneficiary would be able to secure sustainable paid jobs | Employability Skill Development for Youths | 2000 graduates to be trained on Employability skills | 0 | 0 graduates trained on Employability skills | 2000 | 0 | 564137600 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | More than 50% of beneficiary would be able to secure sustainable paid jobs. | Empowerment of 200 Youths for Specialized ICT training with equipments/laptops | 200 Youths to be equipped with laptops | 0 | 0 Youths equipped with laptops | 200 | 0 | 105000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | Successful Creation of enabling environment of existing and prospective business owners to partner with State with a view of depleting the unemployment ratio. | Stakeholders Summit | 500 existing and new partners | 0 | 0 existing and new partners | 500 | 0 | 40000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | Support growth of entrepreneurs | Creation of Industrial / Incubation Hub (Building & Equipping) | 1 completed, equipped and insured Leather Hub | 0 | 0 completed, equipped and insured Leather Hub | 1 | 0 | 1935359787 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | Reduction of unemployment & creation of wealth for Artisans. | Entrepreneurship Empowerment Programme: ( Startup assistance for 500 People living with disabilities) | 500 Trained & support for people with disabilities. | 0 | 0 Trained & support for people with disabilities. | 500 | 0 | 70000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | Creating a platform for generating lawful wealth among youths of Lagos State. | Solar Farm / Renewable energy Empowerment Training. | 250 Youths to be trained and empowered. | 0 | 0 Youths trained and empowered. | 250 | 0 | 91915000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | Discovery of innate talents in Youths and convertion of same to wealth. | 21st Century Talent Discovery Empowerment backed up with digital Entrepreneurship skills/mentorship for 570 youths in the 57LGA/LCDA | 570 Youths to be helped to discover their talents and equipped. | 0 | 0 Youths helped to discover their talents and equipped. | 570 | 0 | 107900000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | Increased number of registered Artisans/ Tradesmen | Production of ID Card & Certificates for Artisans/ Tradesmen | 10,000 ID Cards to be produced. | 0 | 0 ID Cards produced. | 10,000 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | A standard Job Centre that ensures efficient servive delivery. | A standard Job Centre that ensures efficient servive delivery. | 5 Job centres to be rebranded and upgraded. | 0 | 0 Job centres rebranded and upgraded. | 5 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | A conducive and comfortable work environment. | Brise Soleil for the 2nd and 3rd floor of the office building | Completion of Brise Soleil Coverage of 2nd and 3rd floor | 0 | 0 Hosting and recognise Registered Tradesmen & Artisans in the State. | Completion | 0 | 10000000 | 0 |  | 0% |  |  |  | Economic Affairs | Ministry of Wealth Creation and Employment
Economic Affairs | Ministry of Wealth Creation and Employment | Human-Centric City | Supports ease of doing business | Celebration of Artisans Week | Host and recognise Registered Tradesmen & Artisans in the State. | 0 | 0 Host and recorgnised Registered Tradesmen & Artisans in the State | Host | 0 | 20000000 | 0 |  | 0% |  |  |  | Economic Affairs | Ministry of Wealth Creation and Employment
General Public Services | Office of Chief of Staff | Thriving Economy | Improved Security for citizens in criminally affected communities | Construction of Ise Police Station,Ibeju Lekki | 5% retention work to be done |  | 0% work done | 5% | 0% | 4606022.06 | 0 | 0% | 0% | FUND HAS BEEN APPROVED BUT YET TO BE RELEASED BY STO | 0% |  | General Public Services | Office of Chief of Staff
General Public Services | Office of Chief of Staff | Thriving Economy | Improved Security for citizens in criminally affected communities | Construction of State Security Service (SSS) Office, Alimosho Local Government Area | 5% retention work to be done |  | 0% work done | 5% | 0% | 7791706.68 | 0 | 0% | 0% | YET TO BE APPROVED BY MR. GOVERNOR | 0% |  | General Public Services | Office of Chief of Staff
General Public Services | Office of Chief of Staff | Thriving Economy | Improved Conducive Residential Area for Security Officers in Governor's Office | Renovation of LASTMA/Police Officers Buildings (A&B) at the State House, Alausa-Ikeja | 20% retention work to be done |  | 0% Renovation of LASTMA/Police Officers Buildings (A&B) at the State House, Alausa-Ikeja | 20% | 0% | 27870731.23 | 0 | 0% | 0% | YET TO BE APPROVED BY MR. GOVERNOR | 0% |  | General Public Services | Office of Chief of Staff
General Public Services | Office of Chief of Staff | Thriving Economy | Improved Security for citizens in criminally affected communities | Construction of Lekki Police Station, Lekki LCDA, Ibeju Lekki | 30% work to be done |  | 0% Construction of Lekki Police Station Lekki LCDA, Ibeju Lekki | 30% | 0% | 77614693.87 | 0 | 0% | 0% | YET TO BE APPROVED BY MR. GOVERNOR | 0% |  | General Public Services | Office of Chief of Staff
General Public Services | Office of Chief of Staff | Thriving Economy | Improved Security for citizens in criminally affected communities | Construction of Elepe Police Station, Igbogbo-Baiyeku LCDA, Ikorodu | 100% work to be done | 0 | 0% Construction of Elepe Police Station, Igbogbo-Baiyeku LCDA, IKorodu | 100% | 0% | 374547369.5 | 0 | 0% | 0% | YET TO BE APPROVED BY MR. GOVERNOR | 0% |  | General Public Services | Office of Chief of Staff
General Public Services | Office of Chief of Staff | Thriving Economy | Improved Security for citizens in criminally affected communities | Renovation works at L-wing Office Block, Alausa Ikeja and the Speech Writers Building | 100% work to be done | 0 | 0% Renovation works at L-wing Office Block, Alausa Ikeja and the Speech Writer Office | 100% | 0% | 762730645.71 | 0 | 0% | 0% | YET TO BE APPROVED BY MR. GOVERNOR | 0% |  | General Public Services | Office of Chief of Staff
Economic Affairs | Office of Works | Thriving Economy | Increase Office spaces | ILE-PAKO (RECONSTRUCTION OF ILE-PAKO, WOODEN BLOCK BY THE MAIN ENTRANCE) | 70% reconstruction of Ile-Pako | 0 | 0% reconstruction of Ile-Pako | 70% | 0% | 578258271.13 | 35657927 | 0% | 6.166% |  | 0% |  | Economic Affairs | Office of Works
Economic Affairs | Office of Works | Thriving Economy | Lightening up the Alausa Secretariat | UPGRADING OF ELECTRICAL EQUIPMENTS | 65 Nos. of Security light to be installed | 0 | 0 Nos. of Security light installed | 65 | 0 | 35657927 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Office of Works
Economic Affairs | Office of Works | Modern Infrastructure | Much-needed modern amenities, enhance the condition and dignity of police officers and community | RENOVATION OF ALAUSA POLICE BARRACKS AND CONSTRUCTION OF PCRC HALL | 100% Completion of PCRC Hall and Renovation of Alausa Police Barracks | 0 | 0% Completion of PCRC Hall and Alausa Police Barracks renovation | 100% | 0% | 219412748.86 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Office of Works
Economic Affairs | Office of Works | Modern Infrastructure | Additional Parking and Office space | COMPLETION OF MULTI-AGENCY OFFICE COMPLEX | 100% Completion of Multi-Agency office | 0 | 48% Completion of Multi-Agency Office | 100% | 48% | 12000000000 |  | 48% |  |  | 0% |  | Economic Affairs | Office of Works
Economic Affairs | Office of Works | Modern Infrastructure | Condusive atmosphere to boost staff welfare and productuvity | RESCUSITATION OF LIFTS WITHIN THE SECRETARIAT COMPLEX | 11 Nos. maintained lifts in the secretariat | 0 | 11 Nos. maintained lifts in the secretariat | 11 | 11 | 200000000 |  | 100% |  |  | 0% |  | Economic Affairs | Office of Works
Economic Affairs | Office of Works | Modern Infrastructure | Efficient mechanical system and Safety management of mechanical tools and accessories | RETROFITING OF EXTRA LOW VOLTAGE | 10 Nos. Fire Alarm panel to be installed | 0 | 0 Nos. Fire Alarm panel installed | 10 | 0 | 71050500 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Office of Works
Economic Affairs | Office of Works | Modern Infrastructure | Efficient mechanical system and Safety management of mechanical tools and accessories | RETROFITING OF EXTRA LOW VOLTAGE | 5 Nos. CCTV to be installed. | 0 | 0 Nos. CCTV installed. | 5 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Office of Works
Environmental Protection | Office of Drainage Services | Human-Centric City | Reducing Flooding and Erosion to Ensure Safety of Lives and Properties, Improved well being of the Citizen | Maintenance/Rehabilitation of collapsed Drainage Channel | 39 number of Primary Dredging Channels to be maintained | 0 | 0 number of Primary Dredging Channels maintained | 39 | 0 | 4575000000 | 2745000000 | 0% | 60% |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Maintennace/Rehabilitation of collapsed Drainage Channel | 280 number of Secondary Collector Channel to be maintained | 0 | 0 number of Secondary Collector Channel maintained | 280 | 0 | 700460089 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Development of EFAG YARDS | 38 Number of Drainage Channel to be Rehabilitated | 0 | 0 Number of Drainage Channel Rehabilitated | 38 | 0 | 0 | 0 | 0% |  |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Construction of Drainage Channel in the State | 1 Numbers of EFAG YARDS to be constructed | 0 | 0 Numbers of EFAG YARDS constructed | 1 | 0 | 200000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Deflooding of School | 54 Numbers of Drainage Channel to be constructed | 0 | 0 Numbers of Drainage Channel constructed | 54 | 0 | 35452428243 | 2500000000 | 0% | 7.052% |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Enlightenment & Campaign/ Stakeholders Forum | 18 Number of School to be Deflooded | 0 | 0 Number of School Deflooded | 18 | 0 | 0 | 0 | 0% |  |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Enlightenment & Campaign/ Stakeholders Forum | 100% Percentage of community Awareness | 0 | 59% Percentage of community Awareness | 100% | 59% | 145000000 | 86400000 | 59% | 59.59% |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Restoration and Protection of R.O.W of Ikotun Channel, Alimosho | 3 Number of Areas contravening structure to be removed along various aligment | 0 | 0 Number of Areas contravening structure removed along various aligment | 3 | 0 | 2000000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Establishment of Flood forecasting system with Automatic Weather Stations | 1 Number weather station to be constructed | 0 | 0 Number weather station constructed | 1 | 0 | 128000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Drilling And Installation Of Investigative Boreholes | 3 Number of Investigate boreholes to be Installed | 0 | 0 Number of Investigate boreholes to be Installed | 3 | 0 | 78000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Establishment of flood monitoring and alert system in Lagos State Phase II | 5 Number of Flood monitoring and alert system installed | 0 | 0 Number of Flood monitoring and alert system installed | 5 | 0 | 100000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Year 2023 annual Celebration (a) March 22-World Water Day. (b) October 15-Global Handwash Day, © November 19-World Toilet Day | 2 No of annual celebration to be carried out | 0 | 0 No of annual celebration carried out | 2 | 0 | 50000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Drainage Services
Environmental Protection | Office of Drainage Services | Human-Centric City | Reduce Encroachment within Drainage Rigth-of-way | Flood Vulnerability study/Hydrological Geological logging Mapping in Lagos State | 1 Flood Vulnerability study/ Hydrological Mapping in Lagos State | 0 | 0 Flood Vulnerability study/ Hydrological Mapping in Lagos State | 1 | 0 | 44000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Drainage Services
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Improved local content production | Development of Imota Light Industrial Park | 100% work to be done | 0 | 20% work done | 100% | 20% | 131250000 | 0 | 20% | 0% |  | 0% |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Developed Technical Skills in Fashion production line | Development of Gberigbe Enterprise Zone | 10% work to be done | 0 | 0% work done | 10% | 0% | 600000000 | 0 | 0% | 0% | Most of the Project are yet to Commence | 0% |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Reduced cost of starting/ growing business | Development of Ibeju-Agbe Enterprise Zone | 100% work to be done | 0 | 0% work done | 100% | 0% | 322350000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Enabling Environment for Light-Industrial Activities of Trucks | Establishment of EKO MSME Fashion Hub 2 | 100% work to be done | 0 | 0% work done | 100% | 0% | 150000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Enabling Environment for Light-Industrial Activities of Trucks | Organisation of Annual MSME Fair | 100% work to be done | 0 | 0% work done | 100% | 0% | 65000000 | 17450000 | 0% | 26.85% |  | 0% |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Policy & Complaints Resolution | Organisation of Corporate Assembly Meeting | 300 no of participants to be in attendance | 0 | 0 no of participant in attendance | 300 | 0 | 20000000 | 19925000 | 0% | 99.62% |  | 0% |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Boost local content production | Staging of Africa Industrialisation Day | 250 no of participants to be in attendance | 0 | 0 no of participants in attendance | 250 | 0 | 15000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Awareness for industrialisation growth | International Cooperative Day Celebration | 20 no of Industrialists to participate and showcase innovative projects at African Industrialization day celebration | 0 | 0 no of Industrialists participate and showcase innovative projects at African Industrialization day celebration | 20 | 0 | 4600000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Awareness for industrialisation growth | Construction of LASCOCO Academic Building | 30 no of Schools innovative ideas to be showcased at African Industrialization day celebration | 0 | 0 no of Schools innovative ideas showcased at African Industrialization day celebration | 30 | 0 | 55000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Awareness for industrialisation growth | Consumer Education Programme | 150 no of Industrialists to be awarded at African Industrialization day celebration | 0 | 0 no of Industrialists awarded at African Industrialization day celebration | 150 | 0 | 18266000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | nformed & educated consumers on good business practice | World Consumer Rights Day | 220 no of Consumers education and awareness campaigns to be carried out | 0 | 21 no of Consumers education and awareness campaigns carried out | 220 | 21 | 3000000 | 0 | 9.545% | 0% |  | 0% |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Speedy redress of complaints through negotiation, mediation & concilliation | World Anti-Counterfeit Day | 8,000 no of Complaint and mediation to be resolved |  | 402 | 8,000 |  | 2000000 | 0 | 0% | 0% |  |  |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | Thriving Economy | Compliance, safety, satisfaction of basic needs and value for money for consumers | Continous Enlightment on the aftermath of display of Plastic bottle drinks exposed to sunlight | 550 no of Supermarket and Grocery Stores to be Visited |  | 130 | 550 |  | 5780230 | 0 | 0% | 0% |  |  |  | Economic Affairs | Ministry of Commerce, Industry and Cooperatives
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 15% of Ikorodu Master Plan to be completed | 0 | 0% of Ikorodu Master Plan completed | 15% | 0% | 157500000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 15% Completion of Kosofe Model City Plan to be done | 0 | 0% Completion of Kosofe Model City Plan done | 15% | 0% | 118000000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 35% Completion of Badagry Master Plan(2013-2033) to be done | 0 | 0% Completion of Badagry Master Plan(2013-2033) done | 35% | 0% | 68250000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 35% Completion of Ibeju – Lekki Model City Plan | 0 | 0% Completion of Ibeju- Lekki Model City Plan | 35% | 0% | 34855194.13 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 15% of Completion of Ikoga-Town Action Area Plan to be done | 0 | 0% of Completion of Ikoga-Town Action Area Plan to be done | 15% | 0% | 4275000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 60% Completion of Iju-Town Action Area Plan to be done | 0 | 0% Completion of Iju- Town Action Area done | 60% | 0% | 17100000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 30% Completion of Development Guide Plans for Excised Villages in Lagos-Ketu/Ijanikin-Ojo to be done | 0 | 0% Completion of Development Guide Plans for Excised Villages in Lagos-Ketu/Ijanikin-Ojo to be done | 30% | 0% | 6267780 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 30% Completion of Development Guide Plans for Excised Villages in Lagos-Sangotedo-Eti-Osa to be done | 0 | 0% Completion of Development Guide Plans for Excised Villages in Lagos-Sangotedo-Eti-Osa | 30% | 0% | 7464255 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 30% Completion of Development Guide Plans for Excised Villages in Lagos-Awoyaya-Ibeju to be done | 0 | 0% Completion of Development Guide Plans for Excised Villages in Lagos-Awoyaya-Ibeju to be done | 30% | 0% | 7167720 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 30% Completion of Development Guide Plans for Excised Villages in Lagos-Eleputu-Ibeju | 0 | 0% Completion of Development Guide Plans for Excised Villages in Lagos-Eleputu-Ibeju done | 30% | 0% | 3021000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 30% Completion of Development Guide Plans for Excised Villages in Lagos-Suberu-Oje, Alimosho to be done | 0 | 0% Completion of Development Guide Plans for Excised Villages in Lagos-Suberu-Oje, Alimosho to be done | 30% | 0% | 4790352 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 30% Completion of Development Guide Plans for Excised Villages in Lagos-Apa-Badagry LGA to be done | 0 | 0% Completion of Development Guide Plans for Excised Villages in Lagos-Suberu-Oje, Alimosho done | 30% | 0% | 4615558.58 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | Human-Centric City | Natural and built environment of the mega city protected and enhanced through the organized and coordinated physical development of the State. | Regional Planning | 25% Completion of Development Guide Plans for Excised Villages in Lagos-Orimedu Ibeju-Lekki to be done | 0 | 0% Completion of Development Guide Plans for Excised Villages in Lagos-Orimedu Ibeju-Lekki to be done | 25% | 0% | 6837000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Physical Planning and Urban Development
General Public Services | Public Procurement Agency | Effective Governance | Government procurement activities are carried out via the e-procurement Platform thereby culminating into efficient procurement and value-for-money | Integration, Configuration and Setup of Environment for 19 MDAs | 19 no of MDAs Hospitals to be on-boarded onto the e-procurement system (19 Government Entities) | 0 | 0 no of MDAs Hospitals on-boarded onto the e-procurement system (19 Government Entities) | 19 | 0 | 271700000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
General Public Services | Public Procurement Agency | Effective Governance | enhanced the job effectiveness/service delivery of the user Community in PPA | Procurement of Office and ICT Hardware Equipment for the Agency Y2024 | 40 no of ICT Equipment to be procured for the Agency | 0 | 0 no of ICT Equipment procured for the Agency | 40 | 0 | 19389103 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
General Public Services | Public Procurement Agency | Effective Governance | Uninterrupted/Continuity of ease of doing business (procurement process) | Licenses, Renewals & Maintenance of Deployed Solutions | 168 No of Licenses, Renewals & Maintenance of Deployed Solutions to be done | 0 | 0 No of Licenses, Renewals & Maintenance of Deployed Solutions done | 168 | 0 | 280000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
General Public Services | Public Procurement Agency | Effective Governance | MDAs Compliance with the procurement process and timely completion of State's Projects. | Procurement Post Review: Monitoring, Enforcement & Compliance Expenses (Y2024 Procurement Process Records for MDAs reviewed) | 100 no of Inspection/Project Monitoring of on-going/completed State Capital Projects Statewide to be done | 0 | 0 no of Inspection/Project Monitoring of on-going/completed State Capital Projects Statewide done | 100 | 0 | 6500000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
General Public Services | Public Procurement Agency | Effective Governance | Enhanced the efficient and effective discharge of procurement process | Engagement of Stakeholders on Procurement Process | 500 no of Stakeholders to be engaged on Procurement Process | 0 | 0 no of Stakeholders engaged on Procurement Process | 500 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
General Public Services | Public Procurement Agency | Effective Governance | Effective showcase to the general public & relevant stakeholders on the general activities of the Government and the Agency | Advocacy on Procurement Process | 40 no of Field trip & Content update, Servicing of the Screens, Updating the Software of the Screen, Updating and editing of Content on Procurement Activities and various State Government Projects to be done | 0 | 0 no of Field trip & Content update, Servicing of the Screens, Updating the Software of the Screen, Updating and editing of Content on Procurement Activities and various State Government Projects done | 40 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
General Public Services | Public Procurement Agency | Effective Governance | Compliance with Change Management on e-Procurement and Open Contracting Data Standard | Change Management on e-Procurement | 200 no of Accounting Officers,Procurement officers to be trained on new change about e-procurement process | 0 | 0 no of Accounting Officers,Procurement officers trained on new change about e-procurement process | 200 | 0 | 37500000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
General Public Services | Public Procurement Agency | Effective Governance | Compliance with procurement process by Officers in MDAs Statewide | Annual Procurement Plan Clinic | 480 no of Procurement plan review of Y2024 MDAs Annual Procurement Plan Clinic to be done | 0 | 0 no of Procurement plan review of Y2024 MDAs Annual Procurement Plan Clinic done | 480 | 0 | 9000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
General Public Services | Public Procurement Agency | Effective Governance | Compliance with procurement process with all procuring entity by the PPA | Technical Committee & Parastatal Tender Board Meeting Expenses | 4 No of Technical meetings carried out by the Technical Committee & Evaluation to be done | 0 | 0 no of Technical meetings carried out by the Technical Committee & Evaluation done | 4 | 0 | 4000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
General Public Services | Public Procurement Agency | Effective Governance | Further enhancement of the Procurement officers skills on the e-procurement platform vis-à-vis the new update and changes on the portal | Annual State Procurement Summit | 450 no of Procurement officers (Statewide) to attend Annual State Procurement Summit | 0 | 0 no of Procurement officers (Statewide) attend Annual State Procurement Summit | 450 | 0 | 17000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
General Public Services | Public Procurement Agency | Effective Governance | Further enhancement of the Procurement officers skills on the e-procurement platform vis-à-vis the new update and changes on the portal | Capacity Building for Procurement Cadre (Statewide) | 75 no of Procurement officer to be trained and equipped (Statewide) on e-procurement module and Procurement process | 0 | 0 no of Procurement officer trained and equipped (Statewide) on e-procurement module and Procurement process | 75 | 0 | 17000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
General Public Services | Public Procurement Agency | Effective Governance | Support the growth of Local Ecoonomy (Ease of doing business and sign on to the open Government Initiatives) | Board Expenses | 4 no of compliance of the Agency to the improved strategies & Laws formulted by the governing to be met | 0 | 0 no of compliance of the Agency to the improved strategies & Laws formulted by the governing met | 4 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Public Procurement Agency
Education Sector | Ministry of Education | Human-Centric City | improved teaching enviroment | 100% complete construction of 1 no 18 classrooms block | 20% work to be done in the construction of 1 no 18 classrooms block | 0 | 0% completion construction 1 no 18 classrooms block | 20% | 0% | 1600000000 | 1276136080 | 0% | 79.76% | 100% Completed | 0% |  | Education Sector | Ministry of Education
Education Sector | Ministry of Education | Human-Centric City | Increased enrolment | Registration of SS3 candidates for May/June 2024 WASSCE data capturing | 61,918 candidates to be captured for May/June 2024 WASSCE | 61420 | 61,420 candidates were captured for May / June 2024 WASSCE | 61,918 | 61,420 | 27620090 | 27620090 | 99.2% | 100% | 100% Completed | 99.2% |  | Education Sector | Ministry of Education
Education Sector | Ministry of Education | Human-Centric City | improved conducive environment for learning | Construction of wall fence on RAFT/PILE/PAD Foundation in some selected public secondary schools in all the six education districts. | 100% completion construction of wall fences in 10 selected public secondary schools | 0 | 0% work done in the Construction of wall fences in 10 selected public Schools | 100% | 0% | 948966412.58 | 0 | 0% | 0% |  | 0% |  | Education Sector | Ministry of Education
Education Sector | Ministry of Education | Human-Centric City | Improved performance | Y2024 payment of WASSCE | 61,918 WASSCE candidates payment to be paid | 61420 | 61,420 WASSCE Y2024 candidates were paid | 61,918 | 61,420 | 1863709000 | 1863709000 | 99.2% | 100% |  | 99.2% |  | Education Sector | Ministry of Education
Education Sector | Ministry of Education | Human-Centric City | Improved performance | unified exam | 61,918 candidates to partake in writing the unified exam | 61420 | 61,420 Candidates partook in writing the Unified Exam | 61,918 | 61,420 | 500000000 | 500000000 | 99.2% | 100% |  | 99.2% |  | Education Sector | Ministry of Education
Education Sector | Ministry of Education | Human-Centric City | Improved performance | Redesigned and construction of Lagos state examboard office complex | 100% completion redisigned and construction of Lagos State Exam Board Office Complex | 0 | 0% Redesigned and Construction of Lagos State Examboard Office Complex | 100% | 0% | 3500000000 | 0 | 0% | 0% |  | 0% |  | Education Sector | Ministry of Education
Education Sector | Ministry of Education | Human-Centric City | Improved performance | Child guidance and special school project | 61,918 candidates to be carried along for the child guidance and special school project | 61420 | 61,420 Candidates were carried along for the Child Guidance and Special School Project | 61,918 | 61,420 | 540805367 | 0 | 99.2% | 0% |  | 99.2% |  | Education Sector | Ministry of Education
Education Sector | Ministry of Education | Human-Centric City | Improved performance | Renovation/Rehabilitation Multilingual centre | 100% work to be done in the completion of the renovation and rehabilitation of multilingual centre | 0 | 0% completion of the renovation and rehabilitation of multilingual centre | 100% | 0% | 34665895.61 | 0 | 0% | 0% |  | 0% |  | Education Sector | Ministry of Education
Education Sector | Ministry of Education | Human-Centric City | improved teaching environment | Construction of LMDGP classsroooms Block | 60% completion of the LMDGP classrooms block | 0 | 0% completion of the LMDGP classrooms block | 60% | 0% | 1139148092.78 | 455659236 | 0% | 40% |  | 0% |  | Education Sector | Ministry of Education
Education Sector | Ministry of Education | Human-Centric City | improved performance | Procurement of science materials for 2024 WAX | 100% of science materials to be procure for 2024 WAX | 1 | 100% science materials procured for 2024 WAX | 100% | 100% | 120782980 | 120782980 | 100% | 100% |  | 100% |  | Education Sector | Ministry of Education
General Public Services | Ministry of Establishments and Training | Effective Governance | Increased pool of highly skilled Proffesionals | Cadre Specific Training | 30 Specific Training to be Organised | 0 | 0 cadred specific trainings organized | 30 | 0 | 84000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Establishments and Training
General Public Services | Ministry of Establishments and Training | Effective Governance | Increased pool of highly skilled Proffesionals | Generic training (Virtual & In person) | 70 Virtual Generic Training to be Organised | 0 | 0 Virtual & In Person generic training organized | 70 | 0 | 196000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Establishments and Training
General Public Services | Ministry of Establishments and Training | Effective Governance | Increased pool of highly skilled Proffesionals | Local Conference seminar & Workshop | 470 Local Conferencies Seminar & Workshop to be Ornainsed | 0 | 0 staff participants attended Local conference and seminar | 470 | 0 | 599515000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Establishments and Training
General Public Services | Ministry of Establishments and Training | Effective Governance | Increased pool of highly skilled Proffesionals | International Conference seminar & Workshop | 100 Staff to Attend International Conference and Seminar | 0 | 0 staff participants attended Onternational conference and seminar | 100 | 0 | 400000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Establishments and Training
General Public Services | Ministry of Establishments and Training | Effective Governance | Increased pool of highly skilled Proffesionals | Long term training sponsored | 3 Long term Training to be Sponsored | 0 | 0 Long term training sponsored | 3 | 0 | 105655000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Establishments and Training
General Public Services | Ministry of Establishments and Training | Effective Governance | Increased pool of highly skilled Proffesionals | Learning Management System (LMS) Training | 100% On-boarding of Employees from Grade 07-17 | 0 | 0% Employees on GL 07 - 17 onboarded | 100% | 0% | 0 | 0 | 0% |  |  | 0% |  | General Public Services | Ministry of Establishments and Training
General Public Services | Ministry of Establishments and Training | Effective Governance | Increased pool of highly skilled Proffesionals | Public - Private Exchange Programmme | 100 Employees to be deployed to relevant private companies for on-the-job training | 0 | 0 Public servants deployed to relevant private companies for on the job learning experience | 100 | 0 | 150000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Establishments and Training
General Public Services | Ministry of Establishments and Training | Effective Governance | Improved work experience of the work force | Others- Retreat, Departmental Training etc | 1 Retreat to be organised | 0 | 0 retreat organised | 1 | 0 | 151571108 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Establishments and Training
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Enhanced south west regional development for conducive economic environment. | DAWN Programmes | 10 no of Meeting to be mobilized for DAWN programme |  | 0 no of Meeting mobilized for DAWN programme | 10 | 0 | 7413021.21 | 0 | 0% | 0% |  |  |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Acurate and reliable head count | Sensitization / Advocazy Programmes in support of the forth coming 2024 National Population and Houding Census | 5 no of Division of the State to be sensitized on the forthcoming National Population and Housing Census. | 0 | 0 no of Division of the State sensitized on the forthcoming National Population and Housing Census. | 5 | 0 | 8000000 | 0 | 0% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Secured environment in the State | Sensitization of Lagos indigeneous Youth on the need to join the Nigerian Armed Forces & Other Para-Military Agencies | 6000 no of indegeneous youth to be sensitized to join Nigeria Armed Forces | 0 | 0 no of indegeneous youth sensitized to join Nigeria Armed Forces | 6000 | 0 | 2500000 | 0 | 0% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Reduce negative health impact in the state. | Youth Sensitization on Drug Abuse, its effects on youth and the society at large | 5000 no of youths to be sensitized through out lagos State | 0 | 0 no of youths sensitized on drug abuse | 5000 | 0 | 3500000 | 0 | 0% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Quick response to any form of emergency/disaster | Rescue Emergency Operation | 2,000 no of Emergency Rescue Operation to be carried out in order to save more lives & Properties | 0 | 445 no of Emergency Rescue Operation carried out | 2,000 | 445 | 150400000 | 0 | 22.25% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Reduced fatalties | Compliance & enforcement of safety standards across socio-economic sector i.e construction, event & hospitality, schools, manufacturing e.t.c. | 60% increase in compliance level in the selected sectors of the economy to be met | 0 | 15% increase in compliance level met | 60% | 15% | 40000000 | 0 | 25% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Prompt response to Fire & Rescue Incidence around the environment | Safety sensitization and awareness campaign for the formal sector (school) | 1,800 no of schools to be sensitized | 0 | 0 no of schools sensitized | 1,800 | 0 | 30000000 | 0 | 0% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Prompt response to Fire & Rescue Incidence around the environment | Construction of Mechanical workshop | 50% work to be done on construction of mechanical workshop | 0 | 12% work done on construction of mechanical workshop | 50% | 12% | 90798587 | 0 | 24% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Prompt response to Fire & Rescue Incidence around the environment | Construction of Kosofe Fire Station | 30% of work to be done on construction of kosofe fire station | 0 | 0% work done on construction of kosofe fire station | 30% | 0% | 100026001.05 | 0 | 0% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Prompt response to Fire & Rescue Incidence around the environment | Construction of Ijede Fire Station and variation | 25% of work to be done on construction of ijede fire station | 0 | 0% work done on construction of ijede fire station | 25% | 0% | 72932300.48 | 0 | 0% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Proactive Safety Training and Enlightment | Construction of Ijegun-Egba Fire Station/Rapid Intervention Vehicles | 15% of work to be done on construction of ijegun-egba fire station/rapid intervention vehicles | 0 | 15% of work done on construction of ijegun-egba fire station/rapid intervention vehicles | 15% | 15% | 219000000 | 0 | 100% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Housing and Community Amenities | Ministry of Housing | Human-Centric City | Increased Housing Stock/Unit in the State | LAGOSHOMS, SANGOTEDO 11 (BUILDING) 528 Units | 57% of Work to be Done | 0 | 5% Work Done | 57% | 5% | 3408880973.41 | 0 | 8.772% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Housing and Community Amenities | Ministry of Housing | Human-Centric City | Improved Livable Communities and Patronage of Housing Estate in the state | LAGOSHOMS, SANGOTEDO II (INFRASTRUCTURE) | 55% of Work to be Done | 0 | 5% Work Done | 55% | 5% | 1000000000 | 0 | 9.091% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Housing and Community Amenities | Ministry of Housing | Human-Centric City | Increased Housing Stock/Unit in the State | LAGOSHOMS, AJARA BADAGRY (BUILDING) 420 Units | 48% of Work to be Done | 0 | 0% Work Done | 48% | 0% | 3400000000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Housing and Community Amenities | Ministry of Housing | Human-Centric City | Improved Livable Communities and Patronage of Housing Estate in the state | LAGOSHOMS, AJARA BADAGRY (INFRASTRUCTURE ) | 20% of Work to be Done | 0 | 0% Work Done | 20% | 0% | 400000000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Housing and Community Amenities | Ministry of Housing | Human-Centric City | ncreased Housing Stock/Unit in the State | EPE HOUSING SCHEME, (BUILDING) 112 Units | 25% of Work to be Done | 0 | 1% Work Done | 25% | 1% | 1000000000 | 0 | 4% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Housing and Community Amenities | Ministry of Housing | Human-Centric City | Improved Livable Communities and Patronage of Housing Estate in the state | EPE HOUSING SCHEME (INFRASTRUCTURE) | 45% of Work to be Done | 0 | 5% Work Done | 45% | 5% | 500000000 | 0 | 11.11% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Housing and Community Amenities | Ministry of Housing | Human-Centric City | Increased Housing Stock/Unit in the State | LAGOSHOMS, IBESHE Phase II (BUILDING) 192 Units | 74% of Work to be Done | 0 | 4% Work Done | 74% | 4% | 2000000000 | 0 | 5.405% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Housing and Community Amenities | Ministry of Housing | Human-Centric City | Improved Livable Communities and Patronage of Housing Estate in the state | LAGOSHOMS, IBESHE Phase II (INFRASTRUCTURE) | 65% of Work to be Done | 0 | 5% Work Done | 65% | 5% | 570000000 | 0 | 7.692% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Housing and Community Amenities | Ministry of Housing | Human-Centric City | Increased Housing Stock/Unit in the State | EGAN - IGANDO MIXED HOUSING SCHEME CLUSTER I EXTENTION I (BUILDING) 30 Units | 100% of Work to be Done | 0 | 60% Work Done | 100% | 60% | 150000000 | 0 | 60% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Housing and Community Amenities | Ministry of Housing | Human-Centric City | Improved Livable Communities and Patronage of Housing Estate in the state | EGAN - IGANDO MIXED HOUSIG SCHEME CLUSTER I EXTENTION I (INFRASTRUCTURE) | 100% of Work to be Done | 0 | 0% Work Done | 100% | 0% | 300000000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Reduced in ATC & C in communities | Implementation of the Lagos State Electricity policy- Creation of Institutions /Agencies (Set up cost) | 1 no of Agency to be created | 0 | 0 no of Agency Created | 1 | 0 | 100000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Improved Legacy Electricity Distribution Infrastructure within the secretariat | Electricity infrastucture improvement within Alausa Secretariat & LASG Agencies | 80% of Commision to be done. | 0 | 0% of Commision to done. | 80% | 0% | 454463271.13 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Improved Electricity Distribution Infrastructure for LASG off campus Agencies | Electricity infrastucture improvement outside Alausa Secretariat & LASG Agencies | 80% of commission to be done |  | 0% of Commision to done. | 80% | 0% | 129006457.21 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Improved electricity distribution Infrastructure to low-income communities (underserved & unserved). | Community Electrification Intervention | 3 no of Business units to be covered | 0 | 0 no of Business unit covered | 3 | 0 | 256649000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Improved Electricity infrastructure in LASG General Hospitals | Hospitals Electrification intervention (Electricity Infrastructure improvement of LASG General Hospitals phase (1&2) | 100% Improvement of LASG Hospitals of power infrastructure | 0 | % Improvement of LASG Hospitals of power infrastructure | 100% | % | 222419348.35 | 0 |  | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Reduced response time to fault rectification. | Procurement/Purchase of Power equipment | 40% of Fault detector and data logger equipment to be acquired | 0 | 0% of Fault detector and data logger equipment acquired | 40% | 0% | 38910000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Improved Electricity supply to Lagos State Residence | Creation and set up of Energy Hub | 1 no of Hub to be created | 0 | 0 no of Hub Created | 1 | 0 | 100000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Enhanced quality of Food production from Agricultural Zones | Geological Services & Solid Mineral Development: Lagos State Agricultural Zone (GIZ) Mapping Lagos East | 100% of credible Lagos East Agricultural soil geochemical map to be produced | 0 | 0% of credible Lagos East Agricultural Soil Geochemical Map produced | 100% | 0% | 45000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Sources of income diversified | LAGOS GEOLOGICAL & MINING COMPANY : Set up for Lagos State owned enterprise (fully or partially) | 100% of Aeromagnetic data to be purchased | 0 | 0% of Aeromagnetic data purchased | 100% | 0% | 82500000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Gas Infrastructure Master Plan Document | Development of Geological & Mining Sector: Mining operation and machineries | 2 no of machineries to be purchased | 0 | 0 no of machineries purchased | 2 | 0 | 140250000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Improved safety of LPG Retailers operations | Development of Gas Infrastructure MasterPlan (Phase 1,2 &3) | 20% completion of Gas Infrastructure Master Plan to be done | 0 | 0% completion of Gas Infrastructure Master Plan done | 20% | 0% | 86202500 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Ease the transition to Natural Gas usage in Lagos State | Migration of LPG Retailers to safer operations across the 5 divisions of Lagos state | 2 no of divisions to be trained on Standard LPG Retail operations | 0 | 0 no of divisions trained on Standard LPG Retail operations | 2 | 0 | 40160000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Reduced soil & ground water pollution in the State (Heavy Metals) | Establishment Of Intervention Funds To Enable Switch To The Use Of Natural Gas | 20% increase on Natural Gas usage to be achieved | 0 | 0% increase on Natural Gas usage achieved | 20% | 0% | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure |  | Study On Abandoned Oil & Gas Facilities in Lagos State | 30% Reduction in soil & ground water pollution in the State to be met | 0 | 0% Reduction in soil & ground water pollution in the State met | 30% | 0% | 24750000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased use of CNG, LPG for transportation | Decarbonization Of Lagos State Transport Sector; Promoting The Use Of CNG, LPG For Transportation And Power Generation | 5% consumption of the use of CNG & LPG for transportation in the State to be achived | 0 | 0% consumption of the use of CNG & LPG for transportation in the State achived | 5% | 0% | 183087500 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased Economic Activities, Safety of Citizens and Security of Lives and Properties | Operation and Maintenance of Streetlights | 36,000 no of street lights poles to be maintained | 0 | 0 no of street lights poles maintained | 36,000 | 0 | 9848862262.75 | 434567544.48 | 0% | 4.412% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased Economic Activities, Safety of Citizens and Security of Lives and Properties | Installation of New Streetlights | 3 no of new streetlight to be installed | 0 | 0 no of new streetlight installed | 3 | 0 | 321966194 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased Economic Activities, Safety of Citizens and Security of Lives and Properties | Repayment of Retrofitting of public lighting from HPS to LED and operational | 1300 Kilometre of street lightening to be Retrofitted from HPS to LED | 0 | 0 Kilometre of street lightening Retrofitted from HPS to LED | 1300 | 0 | 9326963101.85 | 2331740775.46 | 0% | 25% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased Economic Activities, Safety of Citizens and Security of Lives and Properties | Procurement & Installation of Transformers for the Electrification intervention within the State | 8 nos of Transformers to be procured & Installed | 0 | 0 no of Transformers procured & Installed | 8 | 0 | 317348967 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased Economic Activities, Safety of Citizens and Security of Lives and Properties | Connection of Government facilities to IPP | 7 no. of Government facilities to be connected to IPP | 0 | 0 no. of Government facilities connected to IPP | 7 | 0 | 634697934 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased Economic Activities, Safety of Citizens and Security of Lives and Properties | Maintenance of existing Solar powered street lights & installation of more Solar Powered Streetlights to Primary health care centres(PHCs)and public schools | 213 no of Solar panel installed are to be maintained in PHC | 0 | 0 no of Solar panel installed maintained in PHC | 213 | 0 | 286126733.76 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased Economic Activities, Safety of Citizens and Security of Lives and Properties | Maintenance of 3 nos IPP | 3 Nos of IPP to be maintained | 0 | 0 Nos of IPP maintained | 3 | 0 | 9023509640.3 | 1244886604.03 | 0% | 13.8% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased Economic Activities, Safety of Citizens and Security of Lives and Properties | Energy Audit on under-served communities in Epe and Badagry Division, selected Market and various Government facilities | 1 Energy Audit on under-served communities in Epe and Badagry Division, selected Market and various Government facilities are to be done | 0 | 0 no of Energy Audit on under-served communities in Epe and Badagry Division, selected Market and various Government facilities done | 1 | 0 | 214310856.21 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Retail Filling Stations | 1 no of additional Mega Retail Filling Stations to be Constructed and Leased | 0 | 0 no of additional Mega Retail Filling Stations Constructed and Leased | 1 | 0 | 1308000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Containerised Retail Filling Stations | 1 no of additional containerized retail filling station to be Constructed and Leased | 0 | 0 no of additional containerized retail filling station Constructed and Leased | 1 | 0 | 350000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Petroleum Products Bulk Storage Facility | 1 no of petroleum product bulk storage facility to be Constructed and Leased. | 0 | 0 no of petroleum product bulk storage facility Constructed and Leased. | 1 | 0 | 250000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Importation of petroleum product/Bulk Offtake of Petroleum Products from NNPC and other Federal Government approved importers | 1 Bulk offtake /trading of Petroleum product to be increased by 36,000,000 litres annually | 0 | 0 Bulk offtake /trading of Petroleum product increased by 0 litres annually | 1 | 0 | 423548576 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Liquified Petroleum Gas Refill Plants | 1 no of additional Liquified Petroleum Gas Filling Station to be Constructed and Leased. | 0 | 0 no of additional Liquified Petroleum Gas Filling Station Constructed and Leased. | 1 | 0 | 694500000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Purchase of Compressed Natural Gas Trucks | 1 no of Compressed Natural Gas (CNG)Truck to be purchased. | 0 | 0 no of Compressed Natural Gas (CNG)Truck purchased. | 1 | 0 | 275000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Purchase of 15MT LPG Trucks | 1 no of 15MT Liquified Petroleum Gas (LPG)Truck to be purchased. | 0 | 0 no of 15MT Liquified Petroleum Gas (LPG)Truck purchased. | 1 | 0 | 157500000 | 0 |  | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Bulk Offtake/Trading of LPG & CNG) from NLNG and other Federal Government approved importers) | 1 Bulk offtake/trading of LPG and CNG supplies to be increased by 5,195.37 MT annually | 0 | 0 Bulk offtake/trading of LPG and CNG supplies increased by 0 MT annually | 1 | 0 | 400000000 | 0 |  | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Gas Reticulation. | 1 Gas reticulation systems to be increased by 10. | 0 | 0 Gas reticulation systems increased by 0. | 1 | 0 | 50000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Purchase of Gas Cylinders – Gas Awareness Campaign | 1,500 no of additional Cylinders to be purchased | 0 | 0 no of additional Cylinders purchased | 1,500 | 0 | 50000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Purchase of CNG Conversion Kits | 600 Nos of conversion kits to be purchased | 0 | 0 Nos of conversion kits purchased | 600 | 0 | 1092000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Construction of Compressed Natural Gas (CNG)Daughter stations | 1 Construction of 1No.fully functional and operational Compressed Natural Gas Daughter Stations to be done | 0 | 0 no of fully functional and operational Compressed Natural Gas Daughter Stations Constructed | 1 | 0 | 3228000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Economic Affairs | Ministry of Energy and Mineral Resources | Modern Infrastructure | Increased the use of LPG for domestic use by an additional 25% Cost savings | Construction of Compressed Natural Gas (CNG) containerized solutions. | 1 Construction of 3Nos.fully functional and operational Compressed Natural Gas containerized solutions to be done | 0 | 0 no of fully functional and operational Compressed Natural Gas containerized solution Constructed | 1 | 0 | 2746500000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Energy and Mineral Resources
Education Sector | Ministry of Tertiary Education | Human-Centric City | Encourage reading culture amongst young students in Lagos State Public Secondary Schools | Library Development : Rehabilitation/Upgrade of 50nos Public Secondary Schools in Lagos | 50 units of public secondary schools to be rehabilitated. | 0 | 0% units of public secondary schools were rehabilitated | 50 | 0% | 525000000 |  | 0% |  | Awaiting Mr. Governor's Approval. | 0% |  | Education Sector | Ministry of Tertiary Education
Education Sector | Ministry of Tertiary Education | Human-Centric City | Enhance employability of penultimate and final year students of State owned Tertiary Institutions in Lagos State. | Job Initiative Lagos (JIL) 2024. | 1,000 penultimate and final year students in State owned Tertiary Institutions to be trained | 0 | 0% penultimate and final year studends in Stste owned Tertiary Institutions were trained | 1,000 | 0% | 185000000 |  | 0% |  | Awaiting Mr. Governor's Approval. | 0% |  | Education Sector | Ministry of Tertiary Education
Education Sector | Ministry of Tertiary Education | Human-Centric City | Training youths in Lagos state on digital skill acquisition | Eko Digital Skills Initiative Lagos 2024. (EDSIL) | 10,000 Youths in Lagos State to be trained for Eko Digital Skills Initiatives Lagos 2024.(EDSIL) | 0 | 0% Youths in Lagos State were trained for Eko Digital Skills Initiatives Lagos 2024. (EDSIL) | 10,000 | 0% | 142500000 |  | 0% |  | Awaiting Mr. Governor's Approval. | 0% |  | Education Sector | Ministry of Tertiary Education
Social Protection | Ministry of Youth and Social Development | Human-Centric City | To promote Youth engagement, development and resilence | Renovation, refurbishment, equiping/ furnishing & maintenance of Youth Centres | 13 no of Youths centres to be renovated | 0 | 6 no of Youths centres renovated | 13 | 6 | 1252265534.74 | 3523962.88 | 46.15% | 0.2814% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | ensured habitable environment for the senior Citizens | Construction of Epe Model Elderly Care Centre | 100% Completion of Construction of Epe Model Elderly Care Centre to be done | 0 | 0% Completion of Construction of Epe Model Elderly Care Centre done | 100% | 0% | 616995152 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | improved Youth participation on peace and conflict resolution | Youths dialogue on peace and conflict resolution in five divisions of Lagos State | 100% Completion of Youths dialogue on peace and conflict resolution in five divisions of Lagos State to be done | 0 | 0% Completion of Youths dialogue on peace and conflict resolution in five divisions of Lagos State done | 100% | 0% | 40000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | Improved Leadership Training in Youths | Ibile Youth Academy | 500 Youths to be in attendance at the Youth Academy | 0 | 0 Youths in attendance at the Youth Academy | 500 | 0 | 40000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | Improved Leadership Training in Youths | Youths Transformational Leadership training | 400 Youths to be in attendance at the Transformational leadership Training | 0 | 0 Youths in attendance at the Transformational leadership Training | 400 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | To improve the awareness of youth for preventive programmes for drug abuse and crime rate among adolescents | Youth Training on Prevention of Crime,Mental HealthProblem,Depression,Drug Abuse and suicide. | 500 Youths to be in attendance in Prevention of Crime,Mental HealthProblem,Depression,Drug Abuse and suicide. | 0 | 0 no of Youths in attendance in Prevention of Crime,Mental HealthProblem,Depression,Drug Abuse and suicide. | 500 | 0 | 60000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | increased the HIV preventive measures and awareness among adolescents and youth | Youth training on HIV,preventive and sexual Reproductive programme. | 650 Youth to be trained in HIV,preventive and sexual Reproductive programme. | 0 | 0 no of Youths trained in HIV,preventive and sexual Reproductive programme. | 650 | 0 | 5000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | increased skilled youths for empolyment | Youth training on Vocational Skill Acquisition | 600 Youths to be in attendance at the Vocational skill Acqusition Training | 0 | 0 no of Youths in attendance at the Vocational skill Acqusition Training | 600 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | provided parental care for the Vulnerable Children | Development Programme on parenting for adoption of Orphans/ Vulnerable Children | 250 no of Vulnerable children to be adopted through the Development Programme on parenting for adoption of Orphans/ Vulnerable Children | 0 | 0 no of Vulnerable children adopted through the Development Programme on parenting for adoption of Orphans/ Vulnerable Children | 250 | 0 | 169800000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | ensured the Child educational carrer is not hampered | Rescue, Rehabilitation of mentally challenged, Beggars and Destitute for Social Inclusion | 1200 no of Mentally challenged, Beggars and Destitute to be rescued and rehabilitated | 0 | 0 no of Mentally challenged, Beggars and Destitute rescued and rehabilitated | 1200 | 0 | 30000000 | 4748000 | 0% | 15.83% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | provided Parental care for the vulnerables children | Renovation, Equipping, furniture and refurbishment of Social Welfare Offices, Home & Institutions | 5 no of Welfare Offices to be renovated | 0 | 0 no of Welfare Offices to renovated | 5 | 0 | 465178932.57 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | increased number of Children protected | Children Preventive and Protective Programmme | 400 no of Children to be protected through the Children Preventive and Protective Programmme | 0 | 0 no of Children protected through the Children Preventive and Protective Programmme | 400 | 0 | 60000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | increased number of Children protected | Children Celebration and Ceremonies | 5 no of Celebrations and Ceremonies to be Organised | 0 | 1 no of Celebration and Ceremonie Organised | 5 | 1 | 20000000 | 19945000 | 20% | 99.72% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | increased number of Children protected | Household Economy Strenghten for the Parents of the Vulnerables. | 200 no of Vulnerables Household Parents to be Strenghtened. | 0 | 0 no of Vulnerables Household Parents Strenghtened. | 200 | 0 | 70000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | increased number of Children protected | Food and Nutrition | 500 no of children to be provided with good dietary habits | 0 | 0 no of children provided with good dietary habits | 500 | 0 | 25000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Ministry of Youth and Social Development | Human-Centric City | increased number of Children protected | Rescue and Emergecy Operation for Destitutes | 250 no of children are to be rescued in one form of abused or the other. | 0 | 0 no of children rescued in one form of abused or the other. | 250 | 0 | 25000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Youth and Social Development
Social Protection | Lagos State Sports Commission | Human-Centric City | Early scouted talents are being developed from amateur to professional level, while promoting life skills, ethical values and skills acquisition among Student of School age | SchoolSport | 500 Athletes expected to participate in school sports | 0 | 0 Athletes participated | 500 | 0 | 150000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Lagos State Sports Commission
Social Protection | Lagos State Sports Commission | Human-Centric City | Diplomatic image of the State is being strengthened by inviting top flight international athletes to part in the competition | Sport Classics | 280 Athletes expected to participate in sports classic | 0 | 0 Athletes participated | 280 | 0 | 36000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Lagos State Sports Commission
Social Protection | Lagos State Sports Commission | Human-Centric City | Lagosians are empowered physically, Mentally, Socially and emotionally, while building community ties towards engendering peace | Grassroot Sports Competition | 800 Athletes expected to participate in grassroots sports competition | 0 | 0 Athletes participated | 800 | 0 | 100000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Lagos State Sports Commission
Social Protection | Lagos State Sports Commission | Human-Centric City | National Competitive platform for the Progress of discovered young talents to populate and refresh the pool of existing athletes towards good representation at National Africa and World Competitions | State Physically Challenged Sports | 250 Athletes expected to participate in state physically challenged sports | 0 | 0 Athlets participated | 250 | 0 | 50000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Lagos State Sports Commission
Social Protection | Lagos State Sports Commission | Human-Centric City | Mass participation of Lagosians towards psycho - social development and peaceful co - existence from the grassrootsusing conventional and unconventional Sports | National Youth Game | 280 Athletes expected to participate in national youth game | 0 | 0 Athlets participated | 280 | 0 | 150000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Lagos State Sports Commission
Social Protection | Lagos State Sports Commission | Human-Centric City | Capacity Development of Sports Personnel, Curb social vices and build community cohesion. Gainful involvement and engagement of people across different age grade which eradicate sedentry lifestyle towards increasing lifespan | Community Development Sport | 550 State population expected to Participate in community development sports | 0 | 0 Athlets participated | 550 | 0 | 1500000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Lagos State Sports Commission
Social Protection | Lagos State Sports Commission | Human-Centric City | Standard stadium | Upgrading of Teslim Balogun | 100% work to be done on upgrading of teslim balogun stadium, Surulere | 0 | 0% Work done on Teslim Balogun Stadium | 100% | 0% | 3343097580 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Lagos State Sports Commission
Social Protection | Lagos State Sports Commission | Human-Centric City | Promotion of runners performance socialization Networking and harnesing tourism potentials cum economic development of Low medium and large scale business in Lagos State | Marathon and other Race | 60,000 runners to participate in marathon and other race |  | 75318 runners participated in Access Bank Lagos City Marathon | 60,000 | 75318 | 690000000 | 0 | 100% |  |  | 0% |  | Recreation Culture and Religion | Lagos State Sports Commission
Social Protection | Lagos State Sports Commission | Human-Centric City | Capacity Development of Sports Personnel, Curb social vices and build community cohesion. Gainful involvement and engagement of people across different age grade which eradicate sedentry lifestyle towards increasing lifespan | Construction Of Seven (7) Stadia | 100% work to be done on construction of 4 Stadia | 0 | 0% work done on the construction of 4 stadia | 100% | 0% | 0 | 0 | 0% |  |  | 0% |  | Recreation Culture and Religion | Lagos State Sports Commission
General Public Services | Ministry of Science and Technology | Effective Governance | Safe and Secure Vehicles | Vehicle Tracking System | 500 New Vehicles to be Installed with Trackers | 0 | 0 New Vehicles installed with Trackers | 500 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Science and Technology
General Public Services | Ministry of Science and Technology | Effective Governance | Safe and Secure Vehicles | Vehicle Tracking System | 2100 Existing Vehicles to be Tracked | 0 | 0 Existing Vehicles Tracked | 2100 | 0 | 33000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Science and Technology
General Public Services | Ministry of Science and Technology | Effective Governance | Knowledge Driven Smart Economy | KITE Yaba Hub Project | 100% of MasterPlan Design to be Completed | 0 | 0% Completion of Masterplan Design | 100% | 0% | 147348692 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Science and Technology
General Public Services | Ministry of Science and Technology | Modern Infrastructure | Safe, Secure and Connected Lagos | Lagos Smart City | 3300km of Fibre Connection to be Laid for the Smart City Project | 0 | 0km of Fibre Connection Laid for the Smart City Project | 3300km | 0km | 4887468104 | 0 |  | 0% |  |  |  | General Public Services | Ministry of Science and Technology
General Public Services | Ministry of Science and Technology | Thriving Economy | Lagos Smart City | Lagos Smart City | 550 Surveillance Cameras to be Installed for the Smart City Project | 0 | 0 Surveillance Cameras Installed | 550 | 0 | 0 | 0 | 0% |  |  | 0% |  | General Public Services | Ministry of Science and Technology
General Public Services | Ministry of Science and Technology | Thriving Economy | Standardize Data Storage System | Construction of New Data Centre | 100% work to be done on construction Of New Data Centre | 0 | 0% Completion of Construction of New Data Centre | 100% | 0% | 653797713 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Science and Technology
General Public Services | Ministry of Science and Technology | Thriving Economy | Creative and Innovative Ideas for Funding | Organisation of Art of Technology Programme | 3000 Innovators to attend | 0 | 0 Innovators Attended | 3000 | 0 | 120000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Science and Technology
General Public Services | Ministry of Science and Technology | Thriving Economy | Creative and Innovative Ideas for Funding | Organisation of Art of Technology Programme | 100 inventions to be funded | 0 | 0 invention funded | 100 | 0 | 0 | 0 | 0% |  |  | 0% |  | General Public Services | Ministry of Science and Technology
General Public Services | Ministry of Science and Technology | Thriving Economy | Investors Connected to Innovators | Eko Vention | 10 Tech problems to be solved | 0 | 0 Tech Problems Solved | 10 | 0 | 15000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Science and Technology
General Public Services | Ministry of Science and Technology | Thriving Economy | Standardize Platform for Start-up Ecosystem | Start-up Lagos | 100% Update of Portal 2.0 | 0 | 0% update of Portal 2.0 | 100% | 0% | 20000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Science and Technology
General Public Services | Ministry of Science and Technology | Thriving Economy | Standardize Portal for Technological Development Networking | Open Source | 100% Completion of Portal | 0 | 0% Portal Completed | 100% | 0% | 15000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Science and Technology
General Public Services | Ministry of Science and Technology | Thriving Economy | Standardize Portal for Technological Development Networking | Open Source | 10 Tech Problems to be Solved | 0 | 0 Tech Problems Solved | 10 | 0 | 0 | 0 | 0% |  |  | 0% |  | General Public Services | Ministry of Science and Technology
Economic Affairs | Ministry of Science and Technology | Thriving Economy | To increase and improve RELIABILITY | Campus Infrastructure Upgrade | 100% completion of the Campus Infrastructure Upgrade | 0 | 0% of Campus infrastructure upgrade completed | 100% | 0% | 209156759.31 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Science and Technology
Economic Affairs | Ministry of Science and Technology | Thriving Economy | Enhanced efficiency in the State financial & technical process | Enterprise Resource Planning | 100% Optimisation of the oracle modules | 0 | 64% of the Oracle module Optimised | 100% | 64% | 401000000 | 0 | 64% | 0% |  | 0% |  | General Public Services | Ministry of Science and Technology
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | RENOVATION OF 6 CLASSROOM at OORE-OFE NURSERY AND PRIMARY SCHOOL | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 56366576.04 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | RENOVATION OF INCLUSIVE BLOCK at OORE-OFE NURSERY AND PRIMARY SCHOOL | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 11713639.54 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | FENCE WORK at OORE-OFE NURSERY AND PRIMARY SCHOOL | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 9630102.63 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Other external works at OORE-OFE NURSERY AND PRIMARY SCHOOL | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 14075355.31 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | RENOVATION OF 6 CLASSROOM at state Nursery &Primary School | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 57500977.85 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | RENOVATION OF 3 CLASSROOM at state Nursery &Primary School | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 19648969.41 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Other external works at state Nursery &Primary School | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 9267723.75 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | RENOVATION OF 6 CLASSROOM at Ibukunolu Nursery and Primary School | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 69684835.92 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | RENOVATION OF 6 CLASSROOM with office block at Ibukunolu Nursery and Primary School | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 67489646.47 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | RENOVATION OF 3 CLASSROOM with Toilet block at Ibukunolu Nursery and Primary School | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 5739263.75 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Construction of fence work at Ibukunolu Nursery and Primary School | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 6323241.38 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Construction of other external works at Ibukunolu Nursery and Primary School | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 768625 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Ikorodu LGEA office block Renovation of office with toilet block | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 84259711.53 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Renovation of 7 classroom with toilet block at Express Nursery &primary school II ikosi ketu | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 92125499.32 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Drainage work at Express Nursery &primary school II ikosi ketu | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 33466050.75 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Raising of exsiting fence at Express Nursery &primary school II ikosi ketu | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 58032843 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Ansardeen primary school Renovation of 6 classroom block with toilets | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 56626306.55 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Olomu Primary School renovation of 6 classroom | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 41968036.55 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Zumuratul Primary school 1 Block | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 48684680.89 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Renovation of 7 Clasroom Block at Abaranje Primary School Okerube Alimosho | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 50389458.63 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | RCM Primary School Awoyaya renovation of 2no. 3 classroom block | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 34048229.5 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Ikota Primary School isolated toilet | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 17658348.77 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Umoru Memorial Nursery and Primary School, Coker Renovation of 18 classroom with office | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 159696766.22 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Fazil Omar Primary School, Iwaya Renovation of 6 classroom block with toilets | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 80769914.03 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | ANGLICAN NURSERY / PRIMARY SCHOOL ILADO, BADAGRY renovation of 6 classroom | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 66966458.54 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | ANGLICAN NURSERY / PRIMARY SCHOOL 1, IGBOROSUN renovation of 2no. Of 6 classroom block | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 93470361.06 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Renovation of 7 classrooms block at MUSLIM MISSION COMMUNITY PRIMARY SCHOOL, IWORO AJIDO | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 60848807.11 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | RENOVATION OF ISOLATED TOILET (14 CUBICLE) at MUSLIM MISSION COMMUNITY PRIMARY SCHOOL, IWORO AJIDO | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 26387570.27 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | ST. PETER ANGLICAN PRIMARY SCHOOL, IKEJA Renovation of 17+1 Block | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 176148921.33 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Renovation of 6 classroom Block, admin &external works at All Saint Primary school Mushin | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 30214089.82 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Tolu Price Flunctuation | 100% Advance for Fluctuation and inflation in Price of Materials in Tolu |  | 0% supply of Student and Staff Furniture supplied to identified Schools | 100% | 0% | 4025143962.3 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Construction of Wowbill Modular classroom | 20% 2no. school foundation had been completed out of 3no schools |  | 0% 2no. school foundation had been completed out of 3no schools | 20% | 0% | 1825442815 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Construction of Tolu complex Regenaration | 20% of Tolu Complex regenaration to be Completed |  | 4% of Tolu Complex regenaration to be Completed | 20% | 4% | 3929488469 | 226361906.32 | 20% | 5.761% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Human-Centric City | Improved conducive environment for learning | Construction of Roads within Schemes / Projects | 50% Completion of the Building | 50 | 50% of Builder's work ; General block setting at advance stage of completion and roof construction completed, Electrical: All pipe work, wiring and switch are in place and Mechanical: Water supply and waste drainage plumping installation are on-going | 50% |  | 0 |  | 0% |  |  | 100% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 240 Advocacy meetings with House of Assembly Members, Clerics, Women Groups in Lagos, Political Leaders, Traditional Leaders (Obas and Chief) , CDA'S CDC'S, Captain of Industries, Investors, Public Private Partners, Stakeholders, Special Committees, Executive Council Members, Courtesy Visits, Community Leaders, Petitions/Complaints & Resolved meetings, , Letters received & Treated from Private individuals and Corporate Organizations, Palliatives meetings etc. towards the Implementation/achievement of the THEMES+ Agenda. | 0 | 84 Advocacy meetings with House of Assembly Members, Clerics, Women Groups in Lagos, Political Leaders, Traditional Leaders (Obas and Chief) , CDA'S CDC'S, Captain of Industries, Investors, Public Private Partners, Stakeholders, Special Committees, Executive Council Members, Courtesy Visits, Community Leaders, Petitions/Complaints & Resolved meetings, , Letters received & Treated from Private individuals and Corporate Organizations, Palliatives meetings etc. towards the Implementation/achievement of the THEMES+ Agenda. | 240 | 84 | 133200000 | 35400000 | 35% | 26.58% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 24 Local & International Travels for Investor towards achieving of THEMES+ Agenda | 0 | 7 Local & International Travels for Investor towards achieving of THEMES+ Agenda | 24 | 7 | 360000000 | 90000000 | 29.17% | 25% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 60 Representational Duties (Unprecedented/unforeseen assignments delegated by Mr. Governor) towards the Implementation/achievement of the THEMES+ Agenda | 0 | 18 Representational Duties (Unprecedented/unforeseen assignments delegated by Mr. Governor) towards the Implementation/achievement of the THEMES+ Agenda | 60 | 18 | 90000000 | 22500000 | 30% | 25% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 1,500 Welfare allowance for the DG, PS, Security/Enforcement Personnel, convoy, SSA's, Aides, Members of Staff | 0 | 354 Welfare allowance for the DG, PS, Security/Enforsment Personnel, convoy, SSA's, Aides, Members of Staff | 1,500 | 354 | 290236000 | 72559000 | 23.6% | 25% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 12 Publicity & Advocacy Expenses to document the activities of Mr. Deputy Governor. | 0 | 5 Publicity & Advocacy Expenses to document the activities of Mr. Deputy Governor. | 12 | 5 | 6000000 | 4885000 | 41.67% | 81.42% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 127440 number of meals for Welfare (Breakfast, Lunch & Dinner) for MDG’s Security/Enforcement Staff | 0 | 31860 number of meals for Welfare (Breakfast, Lunch & Dinner) for MDG’s Security/Enforcement Staff | 127440 | 31860 | 194316000 | 48321000 | 25% | 24.87% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 1200 Welfare package Items for 4 Festive Celebrations in the Year (Easter, Eid-il-Fitr, Eid-il-Kabir, and Christmas) to be distributed to less privileged, Non-Governmental Organization, Clerics/Religious Leaders, and Community Leaders etc. | 0 | 315 Welfare package Items for 4 Festive Celebrations in the Year (Easter, Eid-il-Fitr, Eid-il-Kabir, Christmas) to be distributed to less priviledge, Non-Governmental Organisation, Clerics/Religious Leaders, Community Leaders etc. | 1200 | 315 | 200000000 | 36945000 | 26.25% | 18.47% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 3500 Production of Branded Carrier Bags & Gift Wrappers for the Welfare packaging of items | 0 | 875 Production of Branded Carrier Bags & Gift Wrappers for the Welfare packaging of items | 3500 | 875 | 11520000 | 2880000 | 25% | 25% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 80 Grants (Donations & Pledges, Financial Assistance etc.) Organisation seeking Governmental input/support, Less priviledges homes, Orphanages, Individuals with special needs of assistance etc. | 0 | 16 Grants (Donations & Pledges, Financial Assistance etc.) Organisation seeking Governmental input/support, Less priviledges homes, Orphanages, Individuals with special needs of assistance etc. | 80 | 16 | 40000000 | 2000000 | 20% | 5% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 240 Corporate Gifts for Official Guests of the State. | 0 | 40 Corporate Gifts for Official Guests of the State. | 240 | 40 | 21600000 | 7200000 | 16.67% | 33.33% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 12 DG monthly Empowerment programme to be expected | 0 | 3 DG monthly Empowerment programme | 12 | 3 | 48000000 | 12000000 | 25% | 25% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 12 Entertainment Events of Dignitaries/Visitors to be expected | 0 | 3 Entertainment Events of Dignitaries/Visitors | 12 | 3 | 90000000 | 22500000 | 25% | 25% |  | 0% |  | General Public Services | Office of the Deputy Governor
General Public Services | Office of the Deputy Governor | Effective Governance | Increased Citizen/ Government relationship | WELAFARE AND ADVOCACY | 4172 Contigency/Special duties assaigned by the Mr. Governor/ Received & Treated request files for Approvals from MDA's/DG's approvals/ Mails received and Treated from Organisations, Individual etc t in other reduced the Administrative bottle necks. | 0 | 1,944 Contigency/Special duties assaigned by the Mr. Governor/ Received & Treated request files for Approvals from MDA's/DG's approvals/ Mails received and Treated from Organisations, Individual etc t in other reduced the Administrative bottle necks. | 4172 | 1,944 | 90000000 | 22500000 | 46.6% | 25% |  | 0% |  | General Public Services | Office of the Deputy Governor
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Agricultural Production | Agricultural Value Chain Enterprise activation programme | 2,000 Youths and Women to be empowered | 0 | 0 youths and women empowered | 2,000 | 0 | 750000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Agricultural Production | Agricultural Value Chain Enterprise activation programme | 50 Co-operatives and Existing Agribusiness to be activated | 0 | 0 Co-operatives and 50 Existing Agribusiness activated | 50 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Agricultural Production | Agricultural Value Chain Enterprise activation programme | 5% increase in food production to be expected | 0 | 0% increase in food production | 5% | 0% | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Rice Production | Development of Rice Value Chain towards the operationalization of the 32MTPH, Lagos Rice Mill | 2,400,000 bags of 50kg Rice to be produced | 0 | 0 bags of 50kg Rice produced | 2,400,000 | 0 | 1560000000 | 781250000 | 0% | 50.08% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Rice Production | Development of Rice Value Chain towards the operationalization of the 32MTPH, Lagos Rice Mill | 1,000,000 bags of 25kg Rice to be produced | 0 | 0 bags of 25kg Rice produced | 1,000,000 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Rice Production | Development of Rice Value Chain towards the operationalization of the 32MTPH, Lagos Rice Mill | 100% Completion of the Line B Part of the Rice-Mill to be expected | 0 | 0% completion of the line B Part of the Rice-Mill | 100% | 0% | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Agricultural Production | Lagos Agricultural Scholars Programme | 6 projects to be established in schools | 0 | 0 projects established in schools | 6 | 0 | 150000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Agricultural Production | Lagos State Summer School Programme | 87 students to be engaged in the Lagos State Summer School Programme | 0 | 0 students engaged | 87 | 0 | 25000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Agricultural Production | Lagos State Summer School Programme | 6 Educational Districts to be engaged in the Lagos State Summer School Programme | 0 | 0 Educational Districts engaged | 6 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Preservation of forest life and eco system | Afforestration and Conservation activities | 10 Hectares of forest life to be preserved | 0 | 0 Hectares of forest life preserved | 10 | 0 | 40000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Availability of hygenic and wholesome meat and meat products in the State | Veterinary Public Health | 100,000 Tonnes of Meat to be certified | 0 | 0 Tonnes of Meat certified | 100,000 | 0 | 100000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Availability of hygenic and wholesome meat and meat products in the State | Veterinary Public Health | 10 additional Abattoirs to be Established | 0 | 0 additional Abattoirs Established | 10 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased food production | cattle feedlot | 100% completion on infrastructure to be expected | 0 | 0% completion on infrastructure | 100% | 0% | 3025469863 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production | Lagos Food Production Centre, Badagry | 150000 Crates of eggs to be produced | 0 | 36200 crates produced | 150000 | 36200 | 200000000 | 0 | 24.13% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production | Lagos Food Production Centre, Badagry | 10 tonnes of fish to be produced | 0 | 6.7 tonnes of fish produced | 10 | 6.7 | 0 | 0 | 67% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production | Lagos Food Production Centre, Badagry | 8000 Old Layers to be reared | 0 | 0 Old Layers reared | 8000 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production and reduction in youth unemployment | Lagos Agripreneuship Programme, Araga, Epe | 2000 Youths to be trained in Agricultural Training Institute, Epe | 0 | 0 Youths trained in Agricultural Training Institute, Epe | 2000 | 0 | 500000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production and reduction in youth unemployment | Lagos Agripreneuship Programme, Araga, Epe | 261,000 crates of eggs to be produced | 0 | 0 crates of eggs produced | 261,000 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production and reduction in youth unemployment | Lagos Agripreneuship Programme, Araga, Epe | 9000 Broiler to be reared | 0 | 0 Broiler reared | 9000 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production and reduction in youth unemployment | Lagos Agripreneuship Programme, Araga, Epe | 10 tonnes of leafy vegetables to be produced | 0 | 0 tonnes of leafy vegetables produced | 10 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production and reduction in youth unemployment | Lagos Agripreneuship Programme, Araga, Epe | 8000 old layers to be produced | 0 | 0 old layers produced |  |  | 0 | 0 | [5 empty] | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production and reduction in youth unemployment | Lagos Agripreneuship Programme, Araga, Epe | 120 tonnes of sweet corn to be produced | 0 | 0 tonnes of sweet corn produced | 120 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production and reduction in youth unemployment | Lagos Agripreneuship Programme, Araga, Epe | 2 tonnes of catfish to be reared. | 0 | 0 tonnes of catfish reared. | 2 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production in the state | Establishment of Lagos Wholesale Produce and Processing Hub, Ketu Ereyun, Epe | 100% Completion of Food Security and Logistics Hub to be expected | 0 | 0% Completion of Food Security and Logistics Hub | 100% | 0% | 27403655136 | 962586400 | 0% | 3.513% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased local food production in the state | Establishment of Agric Training Institute, Ikorodu | 100% Completion of the Institute to be expected | 0 | 0% Completion of the Institute | 100% | 0% | 654750000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased food Production and popularization of Coconu crop | Establishment of Coconut Processing Centre | 100% Completion of the Coconut Processing Centre to be expected | 0 | 0% Completion of the Coconut Processing Centre | 100% | 0% | 250000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Agricultural Production | Sustainable Land Management | 200 Hectares of land to be allocated to agricultural investors for Sustainable Land | 0 | 0 Hectares of land allocated | 200 | 0 | 287500000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Agricultural Production | Sustainable Land Management | 2,000 Hectares of land to be cultivated for cropping for sustainable Land | 0 | 0 Hectares of land cultivated | 2,000 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Agricultural Production | Sustainable Land Management | 300,000 farm families to be reached with Sustainable Integrated Extension Services | 0 | 0 farm families reached with Sustainable Integrated Extension Services | 300,000 | 0 | 136500000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Increased Agricultural Production | Sustainable Land Management | 5 new technology to be introduced to farmers | 0 | 0 new technology introduced to farmers | 5 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Agriculture | Human-Centric City | Improved water transportation in line with the multi-modal transport policy across the state | Input Supply | 97,500,000 Naira trade in Agricultural inputs to be expected | 0 | 0 Naira trade in Agricultural inputs | 97,500,000 | 0 | 97500000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Agriculture
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Channelization of Ebute Ikorodu-Ilaje Falomo waterways ferry route | 100 % channellization work to be done | 0 | 75 % channellization work done | 100 | 75 | 154463750 | 0 | 75% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Channelization of Bariga-whitesand Route | 100 % channellization work to be done | 0 | 75 % channellization work done | 100 | 75 | 74013021.71 | 0 | 75% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Channelisation waterways routes and provision of Navigation Buoys from Ilado- Ilashe-Odofin Channel at project | 100 % channellization work to be done | 0 | 0 % channellization work done | 100 | 0 | 1771223000.29 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Channelisation waterways routes and provision of Navigation Buoys from Five Cowries- Lekki-Lagoon-Parkview/Banana Channel at project | 100 % channellization work to be done | 0 | 0 % channellization work done | 100 | 0 | 4000300228 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Channelization of Ferry Route from Epe-Ebute Lekki | 100 % channellization work to be done | 0 | 90 % channellization work done | 100 | 90 | 508787185.06 | 0 | 90% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Jetties at Epe and Ebute Lekki (LFTZ) | 100 % completion of construction work to be done | 0 | 0 % completion of construction work done | 100 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Completion of Concrete Jetty with waiting Shelter and Shoreline Protection at VIP Challet, Badagry. | 100 % completion of construction work to be done | 0 | 100% completion of construction work done | 100 | 100% | 43599030 | 0 | 1% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Jetty with waiting Shelter and Shoreline Protection at Isalu Ajido, Badagry. | 100 % completion of construction work to be done | 0 | 75 % completion of construction work done | 100 | 75 | 14209109.3 | 0 | 75% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Completion of Concrete Jetty with waiting Shelter and Shoreline Protection at Apa Badagry. | 100 % completion of construction work to be done | 0 | 52 % completion of construction work to be done | 100 | 52 | 53067300 | 0 | 52% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Concrete Jetty with waiting Shelter and Shoreline Protection at Takwa Bay Island | 100 % completion of construction work to be done | 0 | 93 % completion of construction work to be done | 100 | 93 | 151185567.87 | 0 | 93% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of reinforced Jetty with waiting Shelter and Shoreline Protection at Ijede | 100 % completion of construction work to be done | 0 | 48 % completion of construction work to be done | 100 | 48 | 119020485.5 | 0 | 48% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Concrete Jetty with waiting Shelter and Shoreline Protection at Offin waterfront Ikorodu | 100 % completion of construction work to be done | 0 | 75 % completion of construction work done | 100 | 75 | 52581087.45 | 0 | 75% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Floating Jetty,shoreline protection,waiting shelter and Hydraulic sandfilling @Alaiyabiagba Ajeromi Ifelodun. | 100 % completion of construction work to be done | 0 | 0 % completion of construction work done | 100 | 0 | 516824294 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Floating Jetty,shoreline protection,waiting shelter and Hydraulic sandfilling @Oworoshoki | 100 % completion of construction work to be done | 0 | 0 % completion of construction work done | 100 | 0 | 570300984 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Floating Jetties/Terminal for Surveillance purpose at Parkview/Banana. | 100 % completion of construction work to be done | 0 | 0 % completion of construction work done | 100 | 0 | 590656336 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Jetty with waiting shelter and shoreline protection @Ebute-Ero Lagos | 100 % completion of construction work to be done | 0 | 54 % completion of construction work done | 100 | 54 | 123317446.24 | 0 | 54% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Jetty with waiting shelter and shoreline protection @Oke -Ira nla Lagos | 100 % completion of construction work to be done | 0 | 46 % completion of construction work done | 100 | 46 | 102784084.74 | 0 | 46% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Concrete Jetty at Agboyi-Ketu, Kosofe | 100 % completion of construction work to be done | 0 | 95 % completion of construction work done | 100 | 95 | 271765085 | 0 | 95% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Concrete Jetty at Perwinkle,ilashe | 100 % completion of construction work to be done | 0 | 55 % completion of construction work done | 100 | 55 | 437208481.71 | 0 | 55% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Floating Jetty,shoreline protection,waiting shelter and Hydraulic sandfilling @Bogije. | 100 % completion of construction work to be done | 0 | 0 % completion of construction work done | 100 | 0 | 402017000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Jetty Terminal at (Whitesand) Oyingbo | 100 % completion of construction work to be done | 0 | 85 % completion of construction work done | 100 | 85 | 124888696.04 | 0 | 85% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Economic Affairs | Ministry of Waterfront Infrastructure Development | Modern Infrastructure | Improved water transportation in line with the multi-modal transport policy across the state | Construction of Reinforced Jetty with waiting Shelter and Shoreline Protection at Muwo, Ojo. | 100 % completion of construction work to be done | 0 | 48 % completion of construction work done | 100 | 48 | 440124728.94 | 0 | 48% | 0% |  | 0% |  | Economic Affairs | Ministry of Waterfront Infrastructure Development
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | Y2024 Annual Thanksgiving Service | 2500 attendees to be invited | 0 | 6,000 attended | 2500 | 6,000 | 40000000 | 146500000 | 100% | 100% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | To Improve National Cohesion | 2024 Armed Forces Remembrance Day Celebration | 800 both service and ex-service men and women to attend | 0 | 1,100 both service and ex-service men and women attended | 800 | 1,100 | 33550000 | 50000000 | 100% | 100% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | Y2024 Annual Ramadan Tafsir | 300 muslims targeted to attend daily tafsir for 30 days | 0 | 350 muslims attended daily tafsir for 30 days | 300 | 350 | 225000000 | 224620000 | 100% | 99.83% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | Y2024 Annual lenten fast breaking food for Civil Servants | 19,500 Civil servants christians targeted | 0 | 18,000 Civil servants Christians achieved | 19,500 | 18,000 | 135712000 | 100000000 | 92.31% | 73.69% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | Y2024 Annual Ramadan fast breaking food for Civil Servants | 28,000 civil servant muslims targeted | 0 | 26,000 civil servant muslims achieved | 28,000 | 26,000 | 175510000 | 150000000 | 92.86% | 85.47% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | Eid-il- Fitri Celebration | 2,000 attendees expected |  | 0 attended | 2,000 | 0 | 48150000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | Eil - il - Kabir Celebration | 750 attendees expected |  | 0 attended | 750 | 0 | 45150000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | YEAR 2024 RAMADAN FASTING | 10,500 attendees expected |  | 0 attended | 10,500 | 0 | 225000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | YEAR 2024 BREAKING OF FAST DURING LENT PERIOD FOR PUBLIC SERVANTS CHRISTIAN FAITHFULS | 43,750 Food packs targeted for distribution |  | 0 Food packs distributed | 43,750 | 0 | 130712500 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | YEAR 2024 UMURAH (LESSER HAJJ) | 120 attendees expected |  | 0 attended | 120 | 0 | 1000300000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | YEAR 2024 HAJJ OPERATIONS | 400 attendees expected |  | 0 attended | 400 | 0 | 1499700000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Economic Affairs | Lagos Metropolitan Area Transport Authority | Modern Infrastructure | Convenience and Safety of Commuters, Reduced travel time, and Revenue optimization | Lagos Rail Mass Transit (LRMT) Blue line project Section 2 | 30% Completion of Sectionn 2 of Lagos Rail Mass Transit (LRMT) Blue line project | 0 | 0% Completion of Sectionn 2 of Lagos Rail Mass Transit (LRMT) Blue line project | 30% | 0% | 45277193478 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Lagos Metropolitan Area Transport Authority
Economic Affairs | Lagos Metropolitan Area Transport Authority | Modern Infrastructure | Convenience and Safety of Commuters, Reduced travel time, and Revenue optimization | Lagos Rail Mass Transit (LRMT) Red line project Phase 2 | 5% Completion expected of Phase 2 of Lagos Rail Mass Transit (LRMT) Red line project | 0 | 0% Completion of Phase 2 of Lagos Rail Mass Transit (LRMT) Red line project | 5% | 0% | 51895581228 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Lagos Metropolitan Area Transport Authority
Economic Affairs | Lagos Metropolitan Area Transport Authority | Modern Infrastructure | Convenience and Safety of Commuters, Reduced travel time, and Revenue optimization | Passenger Operations Services for LRMT Blue line rail services | 150,000 passengers to be carried on daily basis on Blue line rail | 0 | 0 passengers to be carried on daily basis on Blue line rail | 150,000 | 0 | 8000000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Lagos Metropolitan Area Transport Authority
Economic Affairs | Lagos Metropolitan Area Transport Authority | Modern Infrastructure | Convenience and Safety of Commuters, Reduced travel time, and Revenue optimization | Passenger Operations Services for LRMT Red line rail services | 500,000 passengers to be carried on daily basis on Red line rail | 0 | 0 passengers to be carried on daily basis on Red line rail | 500,000 | 0 | 0 | 0 | 0% |  |  | 0% |  | Economic Affairs | Lagos Metropolitan Area Transport Authority
Economic Affairs | Lagos Metropolitan Area Transport Authority | Modern Infrastructure | Convenience and Safety of Commuters, Reduced travel time, and Revenue optimization | Construction of BRT terminal at Abule Egba | 100% Completion of Construction of BRT terminal at Abule Egba | 0 | 0% Completion of Construction of BRT terminal at Abule Egba | 100% | 0% | 400000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Lagos Metropolitan Area Transport Authority
Economic Affairs | Lagos Metropolitan Area Transport Authority | Modern Infrastructure | Convenience and Safety of Commuters, Reduced travel time, and Revenue optimization | Construction of BRT terminal at Iyana Ipaja for the operation of BRT service | 100% Completion of Construction of BRT terminal at Iyana Ipaja for the operation of BRT service | 0 | 0% Completion of Construction of BRT terminal at Iyana Ipaja for the operation of BRT service | 100% | 0% | 1000000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Lagos Metropolitan Area Transport Authority
Economic Affairs | Lagos Metropolitan Area Transport Authority | Modern Infrastructure | Convenience and Safety of Commuters, Reduced travel time, and Revenue optimization | Construction of BRT terminal at Ajah for the operation of BRT service | 100% Completion of Construction of BRT terminal at Ajah for the operation of BRT service | 0 | 0% Completion of Construction of BRT terminal at Ajah for the operation of BRT service | 100% | 0% | 500000000 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Lagos Metropolitan Area Transport Authority
Economic Affairs | Lagos Metropolitan Area Transport Authority | Modern Infrastructure | Convenience and Safety of Commuters, Reduced travel time, and Revenue optimization | Construction of BRT Infrastructure along LBE from Doyin Orile to Mile 2 (LOT 2, Part 1 & 2) | 100% Completion of BRT Infrastructure along LBE from Doyin Orile to Mile 2 (LOT 2, Part 1 & 2) | 0 | 0% Completion of BRT Infrastructure along LBE from Doyin Orile to Mile 2 (LOT 2, Part 1 & 2) | 100% | 0% | 1457000000 | 586715273.89 | 0% | 40.27% |  | 0% |  | Economic Affairs | Lagos Metropolitan Area Transport Authority
Economic Affairs | Lagos Metropolitan Area Transport Authority | Modern Infrastructure | Convenience and Safety of Commuters, Reduced travel time, and Revenue optimization | The Construction of Quality Bus Corridor Package 1: Ketu-Alapere, Yaba-Lawanson-Cele; Package 2: Iju Ishaga-Abule Egba; and Package 3: Iyana-Iba-Igando. Contruction of Marina & Mile 2 Interchanges | 25% Completion of Construction of Quality Bus Corridor Package 1, Package 2 and Package 3 and construction of Marina & Mile 2 Interchanges | 0 | 0% Completion of Construction of Quality Bus Corridor Package 1, Package 2 and Package 3 and construction of Marina & Mile 2 Interchanges | 25% | 0% | 11327736175 | 0 | 0% | 0% |  | 0% |  | Economic Affairs | Lagos Metropolitan Area Transport Authority
Environmental Protection | Lagos State Parks and Garden Agency | Human-Centric City | Improved air quality for healthy living of citizenry through aggressive tree planting and maintenance | Continuous Tree Planting State Wide | 10,000 trees to be planted and maintained | 0 | 33 trees planted and maintained | 10,000 | 33 | 25000000 | 0 | 0.33% | 0% |  | 0% |  | Environmental Protection | Lagos State Parks and Garden Agency
Environmental Protection | Lagos State Parks and Garden Agency | Human-Centric City | Improved air quality for healthy living of citizenry through aggressive tree planting and maintenance | Tree Felling or Blowover | 12,000 trees expected to be fell or blown over. | 0 | 373 trees fell / blown over. | 12,000 | 373 | 10000000 | 0 | 3.108% | 0% |  | 0% |  | Environmental Protection | Lagos State Parks and Garden Agency
Environmental Protection | Lagos State Parks and Garden Agency | Human-Centric City | Improved air quality for healthy living of citizenry through aggressive tree planting and maintenance | Upgrade Horticultural Research Centre | 154,900 seedlings are expected to be propagated. | 0 | 0 seedlings propagated. | 154,900 | 0 | 2500000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Lagos State Parks and Garden Agency
Environmental Protection | Lagos State Parks and Garden Agency | Human-Centric City | Improved healthy living of citizenry through functional recreational Parks and Gardens & Aesthetic beauty of the Environment | Regular Recreational and Event activities in Established in Parks and Gardens State Wide | 800,000 people expected to visit recreational and event centres established in Parks State Wide. | 0 | 0 people visited recreational and event centres established in Parks State Wide. | 800,000 | 0 | 114865000 | 114865000 | 0% | 100% |  | 0% |  | Environmental Protection | Lagos State Parks and Garden Agency
Environmental Protection | Lagos State Parks and Garden Agency | Human-Centric City | Improved healthy living of citizenry through functional recreational Parks and Gardens & Aesthetic beauty of the Environment | Maintenance of Parks and Gardens | 125 Gardens to be maintained. | 0 | 0 Gardens maintained | 125 | 0 | 168960000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Lagos State Parks and Garden Agency
Environmental Protection | Lagos State Parks and Garden Agency | Human-Centric City | Improved healthy living of citizenry through functional recreational Parks and Gardens & Aesthetic beauty of the Environment | Maintenance of Parks and Gardens | 10 Parks to be maintained | 0 | 0 Parks Maintained | 10 | 0 | 0 | 0 | 0% |  |  | 0% |  | Environmental Protection | Lagos State Parks and Garden Agency
Environmental Protection | Lagos State Parks and Garden Agency | Human-Centric City | Improved healthy living of citizenry through functional recreational Parks and Gardens & Aesthetic beauty of the Environment | Rehabilitation of Parks, Beautification and Landscaping in Schools | 3 Parks to be rehabilitated. | 0 | 0 Parks rehabilitated | 3 |  | 588659500 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Lagos State Parks and Garden Agency
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Improved Tourist Traffic | Redevelopment of J. Randle Center for Yoruba Culture and History | 5% work to be done | 0 | 0% work done | 5% | 0% | 186721241.64 | 0 | 0% | 0% | The Project is completed (retention payment outstanding) | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Enhanced preservation of values & monuments | Redevelopment of J. Randle Center for Yoruba Culture and History | 5% work to be done on Phase II | 0 | 0% work done | 5% | 0% | 140000000 | 0 | 0% | 0% | The Project is completed (retention payment outstanding) | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City |  | Renovation of Agia Tree | 15% work to be done | 0 | 0% work done | 15% | 0% | 59738545.79 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Enhanced preservation of values & monuments | Erection of Late Jakande Statue | 25% work to be done | 0 | 0% work done | 25% | 0% | 32500000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Improved Tourist Traffic | Greater Lagos Y2024 | 2,000,000 Tourists to be attracted at Greater Lagos Y2022 (5 different locations) | 0 | 0 no of tourists attracted | 2,000,000 | 0 | 1500000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Improved Tourist Traffic | World Tourism Day | 1,000 participants to be in attendance | 0 | 0 no of participants in attendance | 1,000 | 0 | 8500000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Enhanced preservation of values & monuments | Branding,Awareness and Sensitization | 5,000 attendees to br at the Community Tourism Awareness | 0 | 0 no of attendees | 5,000 | 0 | 250000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Enhanced preservation of values & monuments | Monitoring of Monument Sites | 106 no of Monuments to be monitored | 0 | 0 no of Monuments monitored | 106 | 0 | 4500000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Improved Tourist Traffic | Monitoring of Hospitality Tourism Establishments | 3 no of Hospitality Tourism Establishments to be monitored | 0 | 0 no of Hospitality Tourism Establishments monitored | 3 | 0 | 15000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Improved Tourist Traffic | Alimosho Cultural Heritage Centre (Fencing), Alimosho, Lagos. | 75% work to be done | 0 | 0% work done | 75% | 0% | 43837716.86 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Improved Tourist Traffic | Ejirin Film City Project (Fencing), Ejinrin, Epe | 75% work to be done | 0 | 0% work done | 75% | 0% | 315533930.33 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Improved Tourist Traffic | Construction of Tourism Theatre/Cinema | 50% work to be done | 0 |  | 50% |  | 2500000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Promoted culture | Lagos Boat Regatta | 5,000 participants to be in attendance | 0 | 0 no of Participant in attendance | 5,000 | 0 | 1100000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Promoted culture | World Theatre Day | 500 participants to be in attendance | 0 | 500 no of Participant in attendance | 500 | 500 | 60000000 | 60000000 | 100% | 100% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Promoted culture | World Culture Day | 1,000 participants to be in attendance | 0 | 1000 no of Participant in attendance | 1,000 | 1000 | 5000000 | 5000000 | 100% | 100% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Enhanced preservation of values & monuments | Rehabilitation of Princess Erelu Kuti Tomb | 60% work to be done | 0 | 40% work done | 60% | 40% | 15254250 | 9152550 | 66.67% | 60% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Improved Tourist Traffic | Eyo Festival | 5,000 participants to be in attendance | 0 | 0 no of Participant in attendance | 5,000 | 0 | 2000000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City |  | Symphony of Light | 2,000,000 Tourists to be attracted | 0 | 0 no of Tourist attracted | 2,000,000 | 0 | 600000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Improved Tourist Traffic | Upgrading of Badagry Heritage Museum | 5,000,000 Tourists to be attracted | 0 | 0 no of Tourist in attendance | 5,000,000 | 0 | 60000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | Human-Centric City | Enhanced preservation of values & monuments | Creation and Beautification of Recreation Centre in Lagos | 3,000,000 Tourists to be attracted | 0 | 0 no of Tourist attracted | 3,000,000 | 0 | 120000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Tourism, Arts and Culture
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Enhanced well being of Community dwellers | Community based intervention and self help project | 23 no of interventions in self- help projects across communities to be done | 0 | 0 no of interventions in self- help projects across communities done | 23 | 0 | 265000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Community participation in Government Programmes / Projects | Stakeholders Meeting | 699 no of Community and Engagement Meetings | 0 | 175 no of Community and Engagement Meetings | 699 | 175 | 23000000 | 3500000 | 25.04% | 15.22% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Improved Welfare of Traditional Rullers | Ugrade and Rehabilitation of Oba Palaces | 5 no of Oba Palaces to be upgraded and renovated | 0 | 1 no of oba Palaces upgraded and renovated | 5 | 1 | 1996407914 | 155000000 | 20% | 7.764% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Improved Inter-Government Synergy between Government and Traditional Rulers | Special Allowance for Obas | 84 no of Traditional Rulers to be given special allowance | 0 | 84 no of Traditional Rulers given special allowance | 84 | 84 | 1059681403 | 101500000 | 100% | 9.578% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Improved Well being of peasant farmers | Community Agriculture | 6 no of community agriculture Interventionsto be carried out | 0 | 0 no of community agriculture Intervention carried out | 6 | 0 | 25000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Enabling Environment for Market Patronage | Local Government Administration | 70 % compliance with State Policy Directives to be achived | 0 | 0 % compliance with State Policy Directives achived | 70 | 0 | 102000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Enhanced peaceful co-existence among Border Communities | Market Development | 14 no of market infrastructures facilities to be provided | 0 | 7 no of market infrastructures facilities to be provided | 14 | 7 | 100000000 | 28714869.67 | 50% | 28.71% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Enhanced peaceful co-existence among Border Communities | SignPosts of Boundary re-alignment | 16 no of boundary sign post to be rehabilitated in LGs/ LCDAs | 0 | 0 no of boundary sign post to be rehabilitated in LGs/ LCDAs | 16 | 0 | 12000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Enhanced peaceful co-existence among Border Communities | Boundary Matters | 5 no of intervention in boundary disputes to be done |  | 0 no of intervention in boundary disputes done | 5 | 0 | 6000000 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Improved well being of rural dwellers in innovations and development | Water Equipment | 47 no of Potable Water Projects to be done | 0 | 0 no of Potable Water Projects to be done | 47 | 0 | 522072902.93 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Improved well being of rural dwellers in innovations and development | Rural Road Intervention | 5 no of Rural Road Projects to be done | 0 | 0 no of Rural Road Projects done | 5 | 0 | 712235537.07 | 0 | 0% | 0% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
General Public Services | Ministry of Local Government and Community Affairs | Human-Centric City | Improved well being of rural dwellers in innovations and development | Rural Electrification Intervention | 37 no of Rural Electrification Projects to be done | 0 | 10 no of Rural Electrification Projects done | 37 | 10 | 600000000 | 139195000 | 27.03% | 23.2% |  | 0% |  | General Public Services | Ministry of Local Government and Community Affairs
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of adequate working environment | Construction of 3 Storye NTDA HQ Building | 100% Completion Construction of 3 Storye NTDA HQ Building |  | 0% Completion Construction of 3 Storye NTDA HQ Building | 100% | 0% | 169408951 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of access road within Lekki Scheme II | Construction of 2km length of road IDERA, Lekki II | 100% Completion Construction of 2km length of road IDERA, Lekki II |  | 0% Completion Construction of 2km length of road IDERA, Lekki II | 100% | 0% | 468252194.3 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of Infrastructure within Lekki Scheme II | Construction of 1 Storye NTDA Lekki Phase II Zonal Office (For zonal officers and monitoring team accomodation) | 100% Completion Construction of 1 Storye NTDA Lekki Phase II Zonal Office (For zonal officers and monitoring team accomodation) |  | 80% Completion Construction of 1 Storye NTDA Lekki Phase II Zonal Office (For zonal officers and monitoring team accomodation) | 100% | 80% | 239762147.01 |  | 80% |  |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of access road within Other Estate ( Allottee capital contributions) | Construction of gateway Cresent Magodo Scheme I | 100% Completion Construction of gateway Cresent Magodo Scheme I |  | 70% Completion Construction of gateway Cresent Magodo Scheme I | 100% | 70% | 170837100.41 | 128774045.56 | 70% | 75.38% |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of access road within Other Estate ( Allottee capital contribution | Construction of Jaiye Oyedotun street, Magodo scheme II | 100% Completion Construction of Jaiye Oyedotun street, Magodo scheme II |  | 100% Completion Construction of Jaiye Oyedotun street, Magodo scheme II | 100% | 100% | 8350611.17 | 8296861.17 | 100% | 99.36% |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of access road within Lekki Scheme I | Rehabilitation of Onikepo Akande Street. Lekki Scheme I | 100% Completion Rehabilitation of Onikepo Akande Street. Lekki Scheme I |  | 60% Completion Rehabilitation of Onikepo Akande Street. Lekki Scheme I | 100% | 60% | 125885255.14 | 83961908.77 | 60% | 66.7% |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of street light within scheme | Street lighting of Kayode Otitoloju Lot III | 100% installation of Streetlights at Kayode Otitoloju Lot III to be Completed |  | 100% Completion of installation of Streetlights at Kayode Otitoloju Lot III | 100% | 100% | 35793454.6 |  | 100% |  |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of street light within scheme | Street lightning of Bashorun Okunsanya Lot II street Lekki Scheme I | 100% Installation of Street lightning of Bashorun Okunsanya Lot II street Lekki Scheme I to be Completed |  | 100% Completion Installation of Street lightning of Bashorun Okunsanya Lot II street Lekki Scheme I | 100% | 100% | 41922612.25 | 34930529.46 | 100% | 83.32% |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of street light within scheme | Street lightning of Sakiru Anjorin /Sarumon Lot I Lekki Scheme I | 100% Installation of Street lightning of Sakiru Anjorin /Sarumon Lot I Lekki Scheme I to be Completed |  | 100% Completion Installation of Street lightning of Sakiru Anjorin /Sarumon Lot I Lekki Scheme I | 100% | 100% | 48595663.8 |  | 100% |  |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of access road within Lekki Scheme I | Construction of Cannanland at Lekki I | 100% Completion Construction of Cannanland at Lekki I |  | 100% Completion Construction of Cannanland at Lekki I | 100% | 100% | 41940921.2 |  | 100% |  |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of access road within Lekki Scheme I | Rehabilitaion of Abayomi Shonuga Lekki I | 100% Completion Rehabilitaion of Abayomi Shonuga Lekki I |  | 100% Completion Rehabilitaion of Abayomi Shonuga Lekki I | 100% | 100% | 6648821.03 |  | 100% |  |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Housing and Community Amenities | New Town Development Authority | Modern Infrastructure | Provision of access road within Lekki Scheme I | Rehabilitation Ayinde Akinmade LekikI I | 100% Completion Rehabilitation Ayinde Akinmade LekikI I |  | 100% Completion Rehabilitation Ayinde Akinmade LekikI I | 100% | 100% | 12604987.31 | 12604987.31 | 100% | 100% |  | 0% |  | Housing and Community Amenities | New Town Development Authority
Economic Affairs | Office of Sustainable Development Goals | Thriving Economy | Increased engagement of citizen in Governance | Engagement of Volunteers corps for programmes and projects | 2500 volunteers corps to be engage for programmes and projects |  | 80 volunteers corps engaged for programmes and projects | 2500 | 80 | 87500000 | 0 | 3.2% | 0% |  | 0% |  | Economic Affairs | Office of Sustainable Development Goals
Economic Affairs | Office of Sustainable Development Goals | Thriving Economy | SDGs project implemented | SDG Intervention Projects | 18 SDGs Intervention Programmes to be organised |  | 3 SDGs Intervention Programmes organised | 18 | 3 | 141500000 | 30000000 | 16.67% | 21.2% |  | 0% |  | Economic Affairs | Office of Sustainable Development Goals
Economic Affairs | Office of Sustainable Development Goals | Thriving Economy | Achieved SDGs Goals | Mainstreaming of SDGs in the State | 35% increase in awareness to be achieved |  | 3% increase in awareness achieved | 35% | 3% | 335000000 | 18380000 | 8.571% | 5.487% |  | 0% |  | Economic Affairs | Office of Sustainable Development Goals
Economic Affairs | Office of Sustainable Development Goals | Thriving Economy | Achieved collaborations in Social and Economic growth among member states, Partners and stakeholders | collaborations/Partnership | 14 nos Collaborations/Partnership (Domestic and Foreign) |  | 5 nos Collaborations/Partnership (Domestic and Foreign) | 14 | 5 | 75000000 | 2500000 | 35.71% | 3.333% |  | 0% |  | Economic Affairs | Office of Sustainable Development Goals
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Confident, self-reliant and protected women | Sponsorship of 100 women for COWLSO programme | 100 women to be sponsored |  | 0 women sponsored | 100 | 0 | 35000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Confident, self-reliant and protected women | Marking of International Depression Day (Celebration of World Mental Health Day) | 5,000 Vulnerable women to be empowered |  | 0 Vulnerable women empowered | 5,000 | 0 | 7500000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Confident, self-reliant and protected women | Special Sponsor NCWS-ICWS . | 20 Vulnerable women to be sponsored |  | 9 Vulnerable women sponsored | 20 | 9 | 9000000 | 4824450 | 45% | 53.61% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Confident, self-reliant and protected women | Sensitization and Distribution of Micronutrient rich foods for vulnerable women in each of the IBILE areas | 600 Vulnerable women to be empowered |  | 360 Vulnerable women empowered | 600 | 360 | 60000000 | 50000000 | 60% | 83.33% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Confident, self-reliant and protected women | Women Assembly | 5,000 Vulnerable women to be empowered |  | 5000 Vulnerable women empowered | 5,000 | 5000 | 114000000 | 100000000 | 100% | 87.72% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Confident, self-reliant and protected women | WAPA Connect | 5,000 Vulnerable women to be empowered |  | 0 Vulnerable women empowered | 5,000 | 0 | 70000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Confident, self-reliant and protected women | Financial Inclusion | 2,000 Vulnerable women to be empowered |  | 1,500 vulnerable women empowered | 2,000 | 1,500 | 5000000 | 4990000 | 75% | 99.8% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Confident, self-reliant and protected women | Mobilization to hold OBPS- | 30 Vulnerable women to be empowered |  | 0 Vulnerable women empowered | 30 | 0 | 129179194 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Confident, self-reliant and protected women | Mobilization to CSW (Commission of Status of Women) | 12 attended International conference |  | 12 attended International conference | 12 | 12 | 244000000 | 263201293.6 | 100% | 100% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Confident, self-reliant and protected women | International training on Small Medium Entrepreneur (SMEs) | 40 Vulnerable women to be empowered |  | 0 Vulnerable women empowered | 40 | 0 | 71750000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Empowered and self-reliant citizens that support the growth of local economy and develop vulnerable to drive productivity | Maintenance of Avia farm: Short term courses- | 1,500 vulnerable people to be empowered |  | 0 Vulnerable women empowered | 1,500 | 0 | 39000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Empowered and self-reliant citizens that support the growth of local economy and develop vulnerable to drive productivity | Poverty Alleviation Programme: (I) International day of eradicating poverty- (ii) Mega Empowerment - | 5,000 vulnerable people to be empowered |  | 0 Vulnerable women empowered | 5,000 | 0 | 962500000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Enlightened Vulnerables protected from all forms of economic crisis, Entrepreneurship challenges, medical challenges and from all forms of violence | Celebration of International Women’s Day | 20,000 vulnerable people to be empowered |  | 10,000 vulnerable people empowered | 20,000 | 10,000 | 90000000 | 89850000 | 50% | 99.83% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Enlightened Vulnerables protected from all forms of economic crisis, Entrepreneurship challenges, medical challenges and from all forms of violence | Celebration of International Rural Women- | 3,000 vulnerable people to be empowered |  | 0 Vulnerable people empowered | 3,000 | 0 | 25000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Enlightened Vulnerables protected from all forms of economic crisis, Entrepreneurship challenges, medical challenges and from all forms of violence | Celebration of Widow’s Day- | 800 vulnerable people to be empowered |  | 0 vulnerable people empowered | 800 | 0 | 50700000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Enlightened Vulnerables protected from all forms of economic crisis, Entrepreneurship challenges, medical challenges and from all forms of violence | Celebration of Humanitarian Day | 400 vulnerable people to be empowered |  | 250 vulnerable people empowered | 400 | 250 | 10000000 | 4495000 | 62.5% | 44.95% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Enlightened Vulnerables protected from all forms of economic crisis, Entrepreneurship challenges, medical challenges and from all forms of violence | Celebration of Menstrual Hygiene Day | 10,000 vulnerable people to be empowered |  | 0 vulnerable people empowered | 10,000 | 0 | 30000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Enlightened Vulnerables protected from all forms of economic crisis, Entrepreneurship challenges, medical challenges and from all forms of violence | Celebration of 16th Day Activism- | 1,000 vulnerable people to be empowered |  | 0 vulnerable people empowered | 1,000 | 0 | 5000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Protected women from any forms of damage from any forms of violation | Hospital Expenses | 50 women to be provided with medical support |  | 0 women protected | 50 | 0 | 9000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Empowered and self-reliant citizens that supports the growth of local economy and develop vulnerable to drive productivity | Program for People Living with HIV | 5000 vulnerable people to be empowered |  | 0 vulnerable people empowered | 5000 | 0 | 2000000 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Empowered and self-reliant citizens that supports the growth of local economy and develop vulnerable to drive productivity | Women Development Program:- Regular Short term training | 2875 vulnerable people to be empowered |  | 0 vulnerable people empowered | 2875 | 0 | 480200000 | 479800000 | 0% | 99.92% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Empowered and self-reliant citizens that supports the growth of local economy and develop vulnerable to drive productivity | Upkeep and Maintenance of Skill Acquisition Centers | 5200 vulnerable people to be empowered |  | 5512 vulnerable people empowered | 5200 | 5512 | 707014013 | 707014013 | 100% | 100% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Increased Numbers of trained indigent citizen and skilled vulnerable women to foster self-reliance | Ketu Vocational Centre Phase II | 100% work to be done on Ketu Vocational Centre Phase II |  | 98% work done | 100% | 98% | 32390245.17 | 10796748.39 | 98% | 33.33% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Local economy growth through development of the vulnerable to drive productivity and enhance revenue generation | Construction Of Garri Processing, Cold Room, Market Stall And Community Hall Ibeshe Town, Amuwo-Odofin Local Government Area, Lagos State | 100% work to be done |  | 90% work done | 100% | 90% | 13634031.07 | 8434031.08 | 90% | 61.86% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Conducive environment for a learning | Equipping and furniture of Ketu Centres | 100% work to be done |  | 0 work done | 100% | 0 | 0 | 0 | 0% |  |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Conducive environment for a learning | Procurement of furniture/Demonstration /Training Equipment to 18 Skill centres, Provision of tables, chairs, boards, sewing | 100% work to be done |  | 0 work done | 100% | 0 | 391443260 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Empowerment, Revenue generated, growth support of the Local economy and increased productivity through the development of vulnerable people | Construction of WAPA multi- purpose centre, Agidingbi, Ikeja | 100% work to be done |  | 0% work done | 100% | 0% | 86477313.48 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Empowerment, Revenue generated, growth support of the Local economy and increased productivity through the development of vulnerable people | Construction of Care Givers Institute Agidingbi Ikeja | 100% work to be done |  | 0% work done | 100% | 0% | 19953884.87 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Empowerment, Revenue generated, growth support of the Local economy and increased productivity through the development of vulnerable people | Renovation and upgrading of 29 public toilets | 100% work to be done |  | 10% work done | 100% | 10% | 64697257 | 5724969.22 | 10% | 8.849% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Empowerment, Revenue generated, growth support of the Local economy and increased productivity through the development of vulnerable people | Renovation and upgrading of 9 public car wash | 100% work to be done |  | 0% work done | 100% | 0% | 14906761 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Social Protection | Ministry of Women Affairs and Poverty Alleviation | Human-Centric City | Empowerment, Revenue generated, growth support of the Local economy and increased productivity through the development of vulnerable people | Renovation of shelter home Agidingbi | 100% work to be done |  | 0% work done | 100% | 0% | 22062487 | 0 | 0% | 0% |  | 0% |  | Social Protection | Ministry of Women Affairs and Poverty Alleviation
Economic Affairs | Ministry of Housing | Human-Centric City | Increased Housing Stock/Unit in the State | EGAN MIXED HOUSING SCHEMES CLUSTER II (BUILDING) 150 Units | 100% of Work to be Done | 0 | 0% work done | 100% | 0% | 250000000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Economic Affairs | Ministry of Housing | Human-Centric City | Improved Livable Communities and Patronage of Housing Estate in the state | EGAN MIXED HOUSING SCHEMES CLUSTER II (INFRASTRUCTURE) | 100% of Work to be Done | 0 | 0% work done | 100% | 0% | 455000000 | 0 | 0% | 0% |  | 0% |  | Housing and Community Amenities | Ministry of Housing
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 57 LGAs/LCDAs in the state To be covered all |  | 0 LGAs/LCDAs in the state covered | 57 | 0 | 247709000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 6 no of recyclabin Banks to be Erected |  | 0 no of recyclabin Banks Erected | 6 | 0 | 236188694 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 1 no of study to be carried out |  | 0 no of study to carried out | 1 | 0 | 61342765 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 4 no of facilities to be monitored |  | 0 no of facilities to monitored | 4 | 0 | 24920000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 20 no of Public Toilets and Bathroom to be constructed |  | 0 no of Public Toilets and Bathroom to be constructed | 20 | 0 | 24920000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 240 Markets and Public places to be monitored |  | 0 Markets and Public places to monitored | 240 | 0 | 25000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 100 Operatives to be paide stipend for 12 months |  | 0 Operatives to paid stipend for 12 months | 100 | 0 | 78000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 4 nos of meeting to be held in a year |  | 0 nos of meeting to held in a year | 4 | 0 | 4000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 5 Operators to be trained |  | 0 Operators to trained | 5 | 0 | 4000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 10 programs to be held |  | 0 programs to held | 10 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 1 program to be held |  | 0 program to held | 1 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 57 LGA/LCDA in the state to participate |  | 0 LGA/LCDA in the state to participate | 57 | 0 | 117780000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 12 Sanitation Competitions among MDAs in secretariat complex and quarterly awards |  | 0 Sanitation Competitions among MDAs in secretariat complex and quarterly awards | 12 | 0 | 50000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 4 meeting to be held |  | 0 meeting to held | 4 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 6 times to fumigate NYSC camp |  | 0 times to fumigate NYSC camp | 6 | 0 | 6000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 150 to attend |  | 0 attended | 150 | 0 | 4000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 2,300 premises and blackspots to be monitored |  | 0 premises and blackspots monitored | 2,300 | 0 | 2000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 23 vector control chemicals to be procured |  | 0 vector control chemicals procured | 23 | 0 | 2000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 12 participants to travel to Germany |  | 0 participants to travel to Germany | 12 | 0 | 20060000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 10 series of cartoons to be produced |  | 0 series of cartoons produced | 10 | 0 | 4990000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 180 Handlers to participate |  | 0 Handlers participated | 180 | 0 | 4990000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 5,000 Students to participate |  | 0 Students participated | 5,000 | 0 | 4990000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 3,000 Students to participate |  | 0 Students participated | 3,000 | 0 | 9990000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 5 communities to be sensitized |  | 0 communities sensitized | 5 | 0 | 2490000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 1000 participants to be engaged |  | 0 participants engaged | 1000 | 0 | 2490000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 10 Stakeholders Engagement workshop on EIA to be held in 10 LGAs |  | 0 Stakeholders Engagement workshop on EIA held in 10 LGAs | 10 | 0 | 25000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 4 No of Technical Panel Review Meeting to be held |  | 0 No of Technical Panel Review Meeting to held | 4 | 0 | 25000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 10 LGAs/25LCDAs to be reached |  | 0 LGAs/25LCDAs reached | 10 | 0 | 50000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 3 major divisions to be Coveraged |  | 0 major divisions Coveraged | 3 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 2000 trees to be evaluated |  | 0 trees evaluated | 2000 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 2,500 women to be trained |  | 0 women to trained | 2,500 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 1000 people to be trained |  | 0 people to trained | 1000 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 1000 Stakeholders to be engaged |  | 0 Stakeholders to engaged | 1000 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 2,500 hundre people to be trained |  | 0 hundre people to trained | 2,500 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 1000 number of active NGOs to collaborate with the Ministry |  | 0 trained | 1000 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 100 number of Stakeholder to participate |  | 0 Network Projects Implemented | 100 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 500 participants to participate |  | 0 Stakeholders engaged | 500 | 0 | 250000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 20 No of Pilot Projects to be Implemented |  | 0 No of Pilot Projects Implemented | 20 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 100 Number of Stakeholders to participated |  | 0 Number of Stakeholders participated | 100 | 0 | 5000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 5 Project to be funded |  | 0 Project funded | 5 | 0 | 5000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 9 Nos of ground water sampling points identified across five Divisions of the State |  | 0 Nos of ground water sampling points identified across five Divisions of the State | 9 | 0 | 120732000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 10 LGAs/LCDAsStakeholder's to be engaged in the State |  | 0 LGAs/LCDAsStakeholder's engaged in the State | 10 | 0 | 25000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 10 Technical panel meeting on Ten developmental project reports |  | 0 Technical panel meeting on Ten developmental project reports | 10 | 0 | 25000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 7 sampling locations across the State |  | 0 sampling locations across the State | 7 | 0 | 80000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 2 no of RF assessment activities to be carried out |  | 0 no of RF assessment activities to be carried out | 2 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 4 no of development projects to be monitored across the State |  | 0 no of development projects to monitored across the State | 4 | 0 | 8910000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 8 development projects in Lagos State to be Examined and Scoping to be done on |  | 0 development projects in Lagos State to Examined and Scoping on | 8 | 0 | 12000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 2 no of Stakeholders Engagement on EIA for financial institutions and professional bodies |  | 0 no of Stakeholders Engagement on EIA for financial institutions and professional bodies | 2 | 0 | 5500000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 800 trees to be tagged |  | 0 trees tagged | 800 | 0 | 20000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 5 stakeholders meetings to be held |  | 0 stakeholders meetings held | 5 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 50 nos warning signposts to be erected |  | 0 nos warning signposts erected | 50 | 0 | 5000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 5 nos erossion proned areas to be identified and assessed |  | 0 nos erossion proned areas identified and assessed | 5 | 0 | 10000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 1 no of garden to be studied for intensive mowing. |  | 0 no of garden studied for intensive mowing. | 1 | 0 | 2500000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 2 nos NGOs and Co-operate Organisation on conservation matter to be collaborated with |  | 0 nos NGOs and Co-operate Organisation on conservation matter to be collaborated with | 2 | 0 | 2500000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 2 nos of oil impacted areas |  | 0 nos of oil impacted areas | 2 | 0 | 2500000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 2 nos degraded areas within the State to be restored |  | 0 nos degraded areas within the State restored | 2 | 0 | 5000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 2 nos monitoring vehicles to be adequately fuelled |  | 0 nos monitoring vehicles adequately fuelled | 2 | 0 | 5000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 3 nos awareness campaigns to be carried out in the Three senatorial district |  | 0 nos awareness campaigns carried out in the Three senatorial district | 3 | 0 | 5000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 5 nos of Ecological Degraded areas within the State to be rehabilitated |  | 0 nos of Ecological Degraded areas within the State rehabilitated | 5 | 0 | 5000000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Environmental Protection | Office of Environmental Services | Human-Centric City | Improved Cleaniness, Health and safety of the environment | Environmental Protection | 3 nos seminars to be organized for the Sand Miners Association |  | 0 nos seminars organized for the Sand Miners Association | 3 | 0 | 7500000 | 0 | 0% | 0% |  | 0% |  | Environmental Protection | Office of Environmental Services
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 6 classroom Block at Local Government Primary school Otta-Ikosi | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 29859011.08 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of classroom block &8cubicle isolated toilet at Local Authorty Primary school Ajido Badagry | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 30125990.81 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Proposed renovation of 6 classroom block, newly isolated toilet at Temidira Primary school | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 43135956.33 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Proposed renovation of 30 cubicle toilet,5 classroom block, & offices plus walkway lobby at ona-Yade community primary school part B fadeyi | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 61077746.48 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Remedial roofing of 2no. 12classroom block at Onifolo community Junior &senior secondary high school | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 50255194.14 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 18 classroom block with toilet at Cheriubun&Seraphin Nursary&Primary school Ikorodu | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 7667046.2 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 6 classroom block at Ado Primary school Ajah | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 188169950.27 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 8 classroom block at LGA primary school Akodo, Epe | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 41874299.78 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 18 Classroom with 16 Cubicle Tiolets Block at Etunrenren Primary School,Ikorodu | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 36076716.69 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 2NR Blocks of 6 Classroom Block Anglican Nursery & Primary Schools,Igborosun,Lagos | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 130019465.07 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 6 Classroom Block at Methodist Primary School,Mafoluku Oshodi,Lagos | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 93390784.19 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of existing fence at Sheperd Hill Primary School Obanikoro | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 47780150.19 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 6 classrooms blocks with cubicle toilets at Ogo Oluwa Nursery and Primary School, Bariga, Gbagada | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 38961660.38 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Emergency renovation of classroom block at Local Authority Nursery and Primary School, Hospital Road, Badagry | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 71770139.44 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Construction of 8 cubicle isolated toilet block at Anuoluwapo Primary School | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 8101750.82 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 4Classroom block with toilet at Kusoru Primary School Ilasamaja | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 16379967.72 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Fabrication &supply of 678 units of furnitures District V&VI | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 54468738.05 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Reroofing of 6 classoom Block office &toilet at Herbert macauly Nur&Pry school makoko, Reactivation of faulty Borehole at Oroku Pry school Ebutte metta | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 53325865.2 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 5 classroom block at Local Govt pry school Noforija Epe | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 8320342.01 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 7+1 classroom block at Community pry school Egan | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 8331865 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 6classroom at Dele Ajomale Primary School | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% |  | 0 | 0% |  |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Supply & fabrication of 2,378 units of single composite furniture for Primary school | 100% supply of Student and Staff Furniture to be supplied to identified Schools |  | 0% completion of Renovation of classroom | 100% | 0% | 186957758.7 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Public Order and Safety | Ministry of Justice | Effective Governance | Increase in number of cases dispensed | Renovation of Magistrate Courts | 5 High/Magistrate Court to be renovated | 0 | 0 Books to be purchased for 63 Hon. Judges, 159 Magistrates, Legal Registrars, Lawyers and Staff. | 5 | 0 | 372354295 | 7285100 | 0% | 1.956% |  | 0% |  | Public Order and Safety | Ministry of Justice
Public Order and Safety | Ministry of Justice | Effective Governance | Safety & Security | Construction of Prisons | 15 Cell block to be completed | 0 | 0 to participate in the organisation of retreats | 15 | 0 | 161704217 | 56741650 | 0% | 35.09% | On-Going | 0% |  | Public Order and Safety | Ministry of Justice
Public Order and Safety | Ministry of Justice | Effective Governance | Safety & Security | Construction of Police Area Command | 2 Police Area Command to be completed | 0 | 0 to participate in legal year ceremony | 2 | 0 | 77035427 | 0 | 0% | 0% | Legal Year program takes effect in 3rd Quarter | 0% |  | Public Order and Safety | Ministry of Justice
Public Order and Safety | Ministry of Justice | Effective Governance | Improved Access to Justice | Renovation and Conversion of the DNA Center | 100% Completion of DNA Center | 0 | 0 to participate in conference and seminar | 100% | 0 | 455591783.25 | 42857684 | 0% | 9.407% | Participation in Conference and Seminar on-going | 0% |  | Public Order and Safety | Ministry of Justice
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 6 classroom block at African church primary school 2 Meiran | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 62818915.97 | 0 | 0% | 0% | Participation in Training and Workshop on-going | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Renovation of 7 classroom block at Local Governmet primary school Noforija Epe | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 46678951 | 0 | 0% | 0% | Decongestion Program scheduled for 2nd and 3rd Quarter | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | Christian Pilgrimage | 500 Christains to go on Pilgrimage | 0 | 0 Christains went on Pilgrimage | 500 | 0 | 1300200000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | National Indepedence Day Celebration | 2500 citizens to attend indepence day celebration |  | 0 citizens to attend independence day celebration | 2500 | 0 | 90000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | International Tolerance Day Celebration | 800 Guest to Attend Event | 0 | 0 Guest to Attended Event | 800 | 0 | 30000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | Annual Christmas Carol | 1200 guest to attend event | 0 | 0 Guest Attended Event | 1200 | 0 | 81165000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | Foster harmonious relationship between the two major religion groups | Inter-Faith Parley | 120 Guest to Attend Event | 0 | 0 Guest Attended Event | 120 | 0 | 200000000 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | To have a Befitting Worship Centre | Renovation of Mosques | 1 Mosque to be Renovated | 0 | 0 Mosque Renovated | 1 | 0 | 48386718.75 | 0 | 0% | 0% |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Recreation Culture and Religion | Ministry of Home Affairs | Human-Centric City | To have a Befitting Worship Centre | Renovation of churches | 1 church to be Renovated | 0 | 0 church Renovated | 1 | 0 | 358932135.57 |  | 0% |  |  | 0% |  | Recreation Culture and Religion | Ministry of Home Affairs
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Quick response to any form of fire disaster / emergency | Procurement of fire equipment /truck (psp) | 1 set of Payment for fire equipment , Taxes and others | 0 | 0 set of Payment for fire equipment , Taxes and others | 1 | 0 | 2044295853 | 0 | 0% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Quick response to any form of emergency/disaster | Procurement of plant & heavy duty equipment | 1 set of payment for the procurement of rescue equipment for LASEMA,Fire & Rescue Service to be made | 0 | 0 set of payment for the procurement of rescue equipment for LASEMA,Fire & Rescue Service made | 1 | 0 | 234666422 | 0 | 0% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Maintenance of Command & Control Centre for effective management and intervention of Emergency/Disaster | Quarterly payments for Provision of fleet Management and Pre-Hospital Management Services of LASEMA | 4 Quarterly payment for Provision of fleet Management and Pre-Hospital Management Services of LASEMA to be made | 0 | 0 Quarterly payment for Provision of fleet Management and Pre-Hospital Management Services of LASEMA made | 4 | 0 | 960000000 | 0 | 0% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | Human-Centric City | Maintenance of Command & Control Centre for effective management and intervention of Emergency/Disaster | Maintenance of Command & Control Centre (Facility Management of the Command & Control Centre) | 4 Quarterly payment for facility management of the Command & Control Centre,Operation of the Call Centre and the Mobile CCTV system | 0 | 0 Quarterly payment for facility management of the Command & Control Centre,Operation of the Call Centre and the Mobile CCTV system made | 4 | 0 | 1200000000 | 0 | 0% | 0% |  | 0% |  | Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Emergency roof repair of12 classroom block at Ogba Junior Grammar school | 100% completion of Renovation of classroom |  | 0% Complete Renovation of Classrooms | 100% | 0% | 8304321.25 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Final Payment on Fabrication and Supply at identified schs at Edu District IV & V | 100% supply of Student and Staff Furniture to be supplied to identified Schools |  | 0% supply of Student and Staff Furniture supplied to identified Schools | 100% | 0% | 53288230.56 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Final Payment on Fabrication and Supply at identified schs in Mushin, Oshodi & Ikeja LGA | 100% supply of Student and Staff Furniture to be supplied to identified Schools |  | 0% supply of Student and Staff Furniture supplied to identified Schools | 100% | 0% | 162174217.6 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | 70% Advance Payment on Fabrication & supply of 632 units Dual single composite furniture's for Identified Public Pry Schools in Edu district VI | 100% supply of Student and Staff Furniture to be supplied to identified Schools |  | 0% supply of Student and Staff Furniture supplied to identified Schools | 100% | 0% | 66133251.26 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | 70% Advance Fabrication & supply of 2,480 units Dual single composite furniture's for Identified Public Pry Schools in Edu district I & II | 100% supply of Student and Staff Furniture to be supplied to identified Schools |  | 0% supply of Student and Staff Furniture supplied to identified Schools | 100% | 0% | 258802239.93 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Fabrication & supply of 2,480 units Dual single composite furniture's for Identified Public Pry Schools in Edu district II,III & IV | 100% supply of Student and Staff Furniture to be supplied to identified Schools |  | 0% supply of Student and Staff Furniture supplied to identified Schools | 100% | 0% | 258772061.58 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Fabrication & supply of 1,343 units Dual single composite furniture's for Identified Public Pry Schools in Edu district V | 100% supply of Student and Staff Furniture to be supplied to identified Schools |  | 0% supply of Student and Staff Furniture supplied to identified Schools | 100% | 0% | 140807529.85 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Fabrication & supply of 1,356 units Dual single composite furniture's for Identified Public Pry Schools in Edu district IV & V | 100% supply of Student and Staff Furniture to be supplied to identified Schools |  | 0% supply of Student and Staff Furniture supplied to identified Schools | 100% | 0% | 141629609.58 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Fabrication & supply of 1,356 units Dual single composite furniture's for Identified Public Pry Schools in Edu district IV & V | 100% supply of Student and Staff Furniture to be supplied to identified Schools |  | 0% supply of Student and Staff Furniture supplied to identified Schools | 100% | 0% | 53325865.09 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Fabrication & supply of 1,280 units Dual single composite furniture's for Identified Public Pry Schools in Edu district IV | 100% supply of Student and Staff Furniture to be supplied to identified Schools |  | 0% supply of Student and Staff Furniture supplied to identified Schools | 100% | 0% | 133284443.34 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Construction of 2no school and renovation of selected schools in Ikorodu | 40% Construction 70% Renovation completion |  | 0% Construction 40% Renovation Completion | 40% | 0% | 893936604.87 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Price Flunctuation for 12n0. construction of 18 classrooms block around the 6 district | 100% Advance for Fluctuation and inflation in Price of Materials in Tolu |  | 0% Advance for Fluctuation and inflation in Price of Materials in Tolu | 100% | 0% | 1393198761.09 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | Modern Infrastructure | Standard and conducive environment for delivery of quality education | Defualted Bond Projects | 100% completion of Renovation of classroom |  | 0% completion of Renovation of classroom | 100% | 0% | 4046046781.86 | 0 | 0% | 0% |  | 0% |  | Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS)
Education Sector | [16 empty] | #N/A
Education Sector | [16 empty] | #N/A
Education Sector | [16 empty] | #N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## COFOG
LAGOS STATE PERFORMANCE MANAGEMENT REPORT |  | Y2024
COFOG | TOTAL NUMBER OF MDAs | COUNTUNIQUE of Programme / Project | TOTAL NUMBER OF KPIs | Y2024 Approved Budget | Cummulative Budget Released as at Q1 | AVERAGE BUDGET PERFORMANCE | AVERAGE OUTPUT PERFORMANCE
Economic Affairs | 12 | 214 | 239 | 339333691076.66 | 26729411144.4 | 7.877% | 14.15%
Education Sector | 3 | 83 | 84 | 31373496278.57 | 4470269292.32 | 14.25% | 16.65%
Environmental Protection | 4 | 26 | 87 | 70263540589 | 9530732125 | 13.56% | 2.411%
General Public Services | 12 | 104 | 211 | 546912737405.22 | 61550019027.94 | 11.25% | 17.15%
Health Sector | 1 | 140 | 141 | 28547543016.2 | 0 | 0% | 58.3%
Housing and Community Amenities | 5 | 37 | 51 | 22046322670.8 | 1036397823.65 | 4.701% | 26.17%
Public Order and Safety | 3 | 44 | 62 | 20860559739.94 | 315819876 | 1.514% | 13.57%
Recreation Culture and Religion | 3 | 46 | 47 | 20703151618.94 | 745272550 | 3.6% | 17.13%
Social Protection | 2 | 47 | 47 | 6710648065.9 | 1757347468.17 | 26.19% | 14.82%
Grand Total | 45 | 741 | 969 | 1.0868e+12 | 106135269307.48 | 9.766% | 20.04%

## SUMMARY
LAGOS STATE PERFORMANCE MANAGEMENT REPORT Y2024
COFOG | MDA REVISED | AVERAGE of Q1 Output Performance | No of Programme / Project | No of KPIs | SUM of Y2024 Approved Budget | SUM of Cummulative Budget Released as at Q1 | AVERAGE BUDGET PERFORMANCE
Economic Affairs | Lagos Metropolitan Area Transport Authority | 0% | 9 | 9 | 119857510881 | 586715273.89 | 0.4895%
Economic Affairs | Lagos State Infrastructure Asset Management Agency | 0% | 2 | 4 | 5000000000 | 0 | 0%
Economic Affairs | Ministry of Agriculture | 3.038% | 14 | 31 | 35180374999 | 1743836400 | 4.957%
Economic Affairs | Ministry of Commerce, Industry and Cooperatives | 2.273% | 13 | 13 | 1392246230 | 37375000 | 2.685%
Economic Affairs | Ministry of Energy and Mineral Resources | 0% | 36 | 36 | 42902232342.56 | 4011194923.97 | 9.35%
Economic Affairs | Ministry of Transportation | 0% | 3 | 8 | 3463375296 | 0 | 0%
Economic Affairs | Ministry of Waterfront Infrastructure Development | 43.95% | 22 | 22 | 10522336901.85 | 0 | 0%
Economic Affairs | Ministry of Wealth Creation and Employment | 0% | 18 | 18 | 4603106188 | 0 | 0%
Economic Affairs | Office of Infrastructure | 59.26% | 82 | 82 | 83909380698.26 | 17881040527.82 | 21.31%
Economic Affairs | Office of Sustainable Development Goals | 16.04% | 4 | 4 | 639000000 | 50880000 | 7.962%
Economic Affairs | Office of Works | 21.14% | 6 | 7 | 13104379446.99 | 35657927 | 0.2721%
Economic Affairs | Public Works Corporation | 24.06% | 5 | 5 | 18759748093 | 2382711091.72 | 12.7%
Education Sector | Ministry of Education | 49.68% | 10 | 10 | 10275697837.97 | 4243907386 | 41.3%
Education Sector | Ministry of Tertiary Education | 0% | 3 | 3 | 852500000 | 0 | 0%
Education Sector | Special Committee on Rehabilitation of Public Schools (SCRPS) | 0.2817% | 70 | 71 | 20245298440.6 | 226361906.32 | 1.118%
Environmental Protection | Lagos State Parks and Garden Agency | 0.4912% | 6 | 7 | 909984500 | 114865000 | 12.62%
Environmental Protection | Lagos State Waste Management Authority | 4.615% | 7 | 7 | 24035665298 | 4084467125 | 16.99%
Environmental Protection | Office of Drainage Services | 4.538% | 12 | 13 | 43472888332 | 5331400000 | 12.26%
Environmental Protection | Office of Environmental Services | 0% | 1 | 60 | 1845002459 | 0 | 0%
General Public Services | Civil Service Commission | 31.44% | 4 | 6 | 259500000 | 0 | 0%
General Public Services | Ministry of Economic Planning and Budget | 19.4% | 8 | 79 | 1158888405.47 | 68808751 | 5.937%
General Public Services | Ministry of Establishments and Training | 0% | 8 | 8 | 1686741108 | 0 | 0%
General Public Services | Ministry of Finance | 36.78% | 13 | 14 | 521658659970.39 | 59849513407.27 | 11.47%
General Public Services | Ministry of Information and Strategy | 49.7% | 4 | 15 | 1512656624 | 0 | 0%
General Public Services | Ministry of Local Government and Community Affairs | 18.51% | 12 | 12 | 5423397757 | 427909869.67 | 7.89%
General Public Services | Ministry of Science and Technology | 4.923% | 10 | 14 | 6521771268.31 | 0 | 0%
General Public Services | Office of Chief of Staff | 0% | 6 | 6 | 1255161169.05 | 0 | 0%
General Public Services | Office of Civic Engagement | 15.47% | 10 | 16 | 1552000000 | 814097000 | 52.45%
General Public Services | Office of the Deputy Governor | 28.38% | 1 | 13 | 1574872000 | 379690000 | 24.11%
General Public Services | Public Procurement Agency | 0% | 12 | 12 | 702089103 | 0 | 0%
General Public Services | Public Service Office | 1.25% | 16 | 16 | 3607000000 | 10000000 | 0.2772%
Health Sector | Ministry of Health | 58.3% | 140 | 141 | 28547543016.2 | 0 | 0%
Housing and Community Amenities | Lands Bureau | 46.19% | 6 | 7 | 6537935032.46 | 767829491.38 | 11.74%
Housing and Community Amenities | Ministry of Housing | 8.839% | 12 | 12 | 13433880973.41 | 0 | 0%
Housing and Community Amenities | Ministry of Physical Planning and Urban Development | 0% | 1 | 13 | 440143859.71 | 0 | 0%
Housing and Community Amenities | New Town Development Authority | 75.83% | 12 | 12 | 1370002719.22 | 268568332.27 | 19.6%
Housing and Community Amenities | Office of the State Surveyor General | 0% | 6 | 7 | 264360086 | 0 | 0%
Public Order and Safety | Lagos State Judiciary | 29.29% | 25 | 43 | 14630341832.95 | 208935442 | 1.428%
Public Order and Safety | Ministry of Justice | 0% | 4 | 4 | 1066685722.25 | 106884434 | 10.02%
Public Order and Safety | Ministry of Special Duties and Intergovernmental Relations | 11.42% | 15 | 15 | 5163532184.74 | 0 | 0%
Recreation Culture and Religion | Lagos State Sports Commission | 11.11% | 9 | 9 | 6019097580 | 0 | 0%
Recreation Culture and Religion | Ministry of Home Affairs | 26.95% | 18 | 18 | 5667468354.32 | 671120000 | 11.84%
Recreation Culture and Religion | Ministry of Tourism, Arts and Culture | 13.33% | 19 | 20 | 9016585684.62 | 74152550 | 0.8224%
Social Protection | Ministry of Women Affairs and Poverty Alleviation | 25.5% | 31 | 31 | 3801408446.59 | 1729130505.29 | 45.49%
Social Protection | Ministry of Youth and Social Development | 4.135% | 16 | 16 | 2909239619.31 | 28216962.88 | 0.9699%
Grand Total |  | 18.63% | 741 | 969 | 1.0868e+12 | 106135269307.48

## ECONOMIC AFFAIRS SECTOR
FULL YEAR 2024 PERFORMANCE MANAGEMENT REPORT |  | Performance Legend
0% - 49%
50% - 69%
70% - 100%
Overall Budget Performance
21.31%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
82.41%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
100%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
21.31%
Overall Budget Performance
0.4895%
Budget Performance
40.27%
0%
0%
0%
0%
0%
0%
0%
0.4895%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
Overall Budget Performance
#N/A
Budget Performance
3.333%
5.487%
0%
21.2%
7.962%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Overall Budget Performance
0.2721%
Budget Performance
0%
0%
0%
0%
6.166%
0%
0.2721%
Overall Budget Performance
12.7%
Budget Performance
0%
7.168%
21.82%
28.43%
13.03%
12.7%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
3.513%
50.08%
0%
4.957%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Overall Budget Performance
9.35%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
13.8%
0%
4.412%
0%
25%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
9.35%
Overall Budget Performance
2.685%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
26.85%
0%
0%
99.62%
0%
0%
2.685%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%

## GENERAL PUBLIC SERVICES SECTOR
|  | FULL YEAR 2024 PERFORMANCE MANAGEMENT REPORT | [7 empty] | Performance Legend
0% - 49%
50% - 69%
70% - 100%
| LAGOS STATE PERFORMANCE MANAGEMENT REPORT |  | Y2023
#DIV/0!
| MDA | TOTAL NUMBER OF PROGRAMMES | TOTAL NUMBER OF KPIs | Y2023 APPROVED BUDGET | CUMMULATIVE BUDGET RELEASED | AVERAGE OUTPUT PERFORMANCE |  | AVERAGE BUDGET PERFORMANCE
| Grand Total | [5 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
[7 empty] | #REF! |  | #N/A
Overall Budget Performance
11.47%
Budget Performance
30.36%
85.48%
1.157%
0%
97.95%
62.86%
14.96%
37.04%
4.66%
8.344%
9.077%
34.4%
0%
7.089%
11.47%
`
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
Overall Budget Performance
5.937%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0.8375%
51.61%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
100%
0%
44.56%
0%
0%
0%
0%
0%
89.14%
0%
9.62%
5.937%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Overall Budget Performance
24.11%
Budget Performance
25%
25%
25%
81.42%
18.47%
24.87%
25%
26.58%
33.33%
25%
25%
25%
5%
24.11%
Overall Budget Performance
7.89%
Budget Performance
15.22%
0%
0%
28.71%
0%
0%
9.578%
7.764%
0%
23.2%
0%
0%
7.89%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Overall Budget Performance
0.2772%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
16.67%
0%
0%
0%
0%
0%
0%
0.2772%
Overall Budget Performance
0%
Budget Performance
0%
25%
0%
0%
75.94%
5.133%
100%
3.064%
0%
0%
0.875%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%

## POS SECTOR
| FULL YEAR 2024 PERFORMANCE MANAGEMENT REPORT | [7 empty] | Performance Legend
0% - 49%
50% - 69%
70% - 100%
LAGOS STATE PERFORMANCE MANAGEMENT REPORT |  | Y2023
#DIV/0!
MDA | TOTAL NUMBER OF PROGRAMMES | TOTAL NUMBER OF KPIs | Y2023 APPROVED BUDGET | CUMMULATIVE BUDGET RELEASED | AVERAGE OUTPUT PERFORMANCE |  | AVERAGE BUDGET PERFORMANCE
Grand Total | [5 empty] | #REF! |  | #N/A
[6 empty] | #REF! |  | #N/A
Overall Budget Performance
1.428%
Budget Performance
0%
0%
0%
0%
31.43%
0%
0%
0%
0%
100%
0%
0%
0%
0%
0%
2.837%
14.57%
16.63%
0%
17.63%
0%
11.8%
17.86%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
1.428%
Overall Budget Performance
#N/A
Budget Performance
9.407%
1.956%
0%
35.09%
10.02%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## ENV. PROT SECTOR
FULL YEAR 2024 PERFORMANCE MANAGEMENT REPORT |  | Performance Legend
0% - 49%
50% - 69%
70% - 100%
Overall Budget Performance
12.62%
Budget Performance
0%
0%
0%
0%
100%
0%
12.62%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Overall Budget Performance
12.26%
Budget Performance
0%
7.052%
0%
59.59%
0%
0%
0%
0%
0%
0%
60%
12.26%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%

## SOC. PROT SECTOR
| FULL YEAR 2024 PERFORMANCE MANAGEMENT REPORT | [7 empty] | Performance Legend
0% - 49%
50% - 69%
70% - 100%
LAGOS STATE PERFORMANCE MANAGEMENT REPORT |  | Y2023
#DIV/0!
MDA | TOTAL NUMBER OF PROGRAMMES | TOTAL NUMBER OF KPIs | Y2023 APPROVED BUDGET | CUMMULATIVE BUDGET RELEASED | AVERAGE OUTPUT PERFORMANCE |  | AVERAGE BUDGET PERFORMANCE
Grand Total | [5 empty] | #REF! |  | #N/A
[6 empty] | #REF! |  | #N/A
Overall Budget Performance
0.9699%
Budget Performance
0%
0%
15.83%
0%
0%
0%
99.72%
0%
0%
0%
0%
0%
0%
0%
0%
0.2814%
0.9699%
Overall Budget Performance
45.49%
Budget Performance
0%
99.8%
0%
0%
100%
0%
83.33%
53.61%
0%
0%
87.72%
0%
0%
0%
100%
99.92%
0%
0%
8.849%
0%
0%
0%
44.95%
0%
99.83%
0%
0%
33.33%
61.86%
0%
45.49%

## H&C AMEN SECTOR
| FULL YEAR 2024 PERFORMANCE MANAGEMENT REPORT | [7 empty] | Performance Legend
0% - 49%
50% - 69%
70% - 100%
LAGOS STATE PERFORMANCE MANAGEMENT REPORT |  | Y2023
#DIV/0!
MDA | TOTAL NUMBER OF PROGRAMMES | TOTAL NUMBER OF KPIs | Y2023 APPROVED BUDGET | CUMMULATIVE BUDGET RELEASED | AVERAGE OUTPUT PERFORMANCE |  | AVERAGE BUDGET PERFORMANCE
Grand Total | [5 empty] | #REF! |  | #N/A
[6 empty] | #REF! |  | #N/A
[6 empty] | #REF! |  | #N/A
[6 empty] | #REF! |  | #N/A
[6 empty] | #REF! |  | #N/A
Overall Budget Performance
19.6%
Budget Performance
0%
0%
0%
100%
66.7%
0%
99.36%
75.38%
0%
0%
83.32%
0%
19.6%
Overall Budget Performance
11.74%
Budget Performance
70%
40%
0%
15.64%
0%
0%
11.74%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%

## HEALTH
| FULL YEAR 2024 PERFORMANCE MANAGEMENT REPORT | [7 empty] | Performance Legend
0% - 49%
50% - 69%
70% - 100%
LAGOS STATE PERFORMANCE MANAGEMENT REPORT |  | Y2023
#DIV/0!
MDA | TOTAL NUMBER OF PROGRAMMES | TOTAL NUMBER OF KPIs | Y2023 APPROVED BUDGET | CUMMULATIVE BUDGET RELEASED | AVERAGE OUTPUT PERFORMANCE |  | AVERAGE BUDGET PERFORMANCE
Grand Total | [5 empty] | #N/A |  | #N/A
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## EDUCATION SECTOR
| FULL YEAR 2024 PERFORMANCE MANAGEMENT REPORT | [7 empty] | Performance Legend
0% - 49%
50% - 69%
70% - 100%
LAGOS STATE PERFORMANCE MANAGEMENT REPORT |  | Y2023
#DIV/0!
MDA | TOTAL NUMBER OF PROGRAMMES | TOTAL NUMBER OF KPIs | Y2023 APPROVED BUDGET | CUMMULATIVE BUDGET RELEASED | AVERAGE OUTPUT PERFORMANCE |  | AVERAGE BUDGET PERFORMANCE
Grand Total | [5 empty] | #N/A |  | #N/A
Overall Budget Performance
41.3%
Budget Performance
0%
0%
100%
0%
0%
100%
100%
79.76%
40%
100%
41.3%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
5.761%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## RECR, CULT, RELIGION SECTOR
FULL YEAR 2024 PERFORMANCE MANAGEMENT REPORT |  | Performance Legend
0% - 49%
50% - 69%
70% - 100%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
73.69%
85.47%
99.83%
100%
0%
Overall Budget Performance
0%
Budget Performance
0%
0%
0%
0%
0%
0%
0%
0%
0%
Overall Budget Performance
#N/A
Budget Performance
0%
0%
0%
0%
0%
0%
0%
60%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
100%
100%
0.8224%